## Store Dev Schedule FY23
updated | 2022-11-21 |  | 77 stores / 70 pipeline
STORE COUNT | STORE # | STORE PROTO | HAND |  | L (LEASE) P (PURCHASE) | STORE ADDRESS | CITY | ST | APPROVAL | CLOSING DATE (total 39) | PERMITS | NTP (CONSTRUCTION START DATE) | APPLY FOR NEW BRANCH CNPJ | IT HARDWARE ORDER DATE | STORE MANAGER TRAINING | POGS ATTACH ACTIVE DATE | FIXTURE ORDER DATE | MDSE INITAL ORDER | BUYER 6 ORDER DATE | PHONE LINES | LP ALARMS & SAFES | TEMP LABOR CONTRACTED | MDSE SECOND ORDER | STORE AUTOZONERS TRAINING (foundations) | SET-UP CREW DATE | DAYS CHG FROM LAST WEEK | MDSE FIRST DELIVERY | SETUP COMPLETION | EST. STORE OPEN DATE | SETUP (# days) | TOTAL STORES FY | PLAN FY23 | LE | FY
[8 empty] | ST | pproval |  | pproval
|  |  |  | remodel |  |  | Sorocaba I
|  |  |  | remodel |  |  | Osasco
|  |  |  | remodel |  |  | Guarapiranga
9 | 7618 | 7N | L | remodel |  | Rua Padre Bernardo da Silva, 1249 (Tenda) | Campinas amoreiras | SP |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | OPENED 04/02/2017 |  |  |  |  | FY17
10 | 7623 | 65W | R | remodel |  | Rua da Abolição (Extra) | Campinas abolição | SP |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | OPENED 24/05/2017 |  |  |  |  | FY17
11 | 7619 | 7N | R | ground up |  | Av. Charles Schnneider, 850 (Tenda) | Taubaté | SP |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | OPENED 20/07/2017 |  |  |  |  | FY17
12 | 7617 | 7N | L | ground up |  | Rua do Ósmio esquina com Rua Antonio Idair Mollon (Tenda) | Sta. Barbara | SP |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | OPENED 02/08/2017 |  |  |  |  | FY17
13 | 7622 | 7N | R | ground up |  | Rodovia da Convenção (Tenda) | Salto | SP |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | OPENED 17/08/2017 |  |  |  |  | FY17
14 | 7620 | 7N | R | ground up |  | Av. Getúlio Vargas esquina com Rua Rocha Pombo | São Carlos | SP |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | OPENED 24/08/2017 |  |  |  |  | FY17
15 | 7625 | 7N | L | remodel |  | Av. Presidente Kennedy, 2930 loja 01 | Praia Grande | SP |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | OPENED 20/12/2017 |  |  |  |  | FY18
16 | 7616 | 65W | R | ground up |  | Av. Prof. Alberto Vollet Sachs, 2030 loja 16 (COOP) | Piracicaba | SP |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | OPENED 02/01/2018 |  |  |  |  | FY18
17 | 7630 | 7N | L | ground up |  | Av. Dona Renata, 3535 (ao lado Savegnago) | Araras | SP |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | OPENED 20/07/2018 |  |  |  |  | FY18
18 | 7631 | 7N | L | ground up |  | Av. Dr. Quinzinho | Jaú | SP |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | OPENED 25/07/2018 |  |  |  |  | FY18
19 | 7627 | 65W | R | remodel |  | Av. Vital Brasil (Pão de Açúcar) | Botucatu | SP |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | OPENED 20/08/2018 |  |  |  |  | FY18
20 | 7629 | 65W | L | ground up |  | Rua. Mal. Deodoro, 2785 (WalMart) | S. B. Campo | SP |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | OPENED 20/08/2018 |  |  |  |  | FY18
21 | 7639 | 7N | L | ground up |  | Av. Marechal Tito, 2813 | São Paulo | SP | 2018-04-29 | 2018-07-17 |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | OPENED 21/12/2018 | - | 1 | - | P5 | FY19
22 | 7638 | 65 | L | ground up |  | Av. São Francisco de Assis, 1915 | Hortolândia | SP | 2018-02-28 | 2018-05-09 |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | OPENED 20/12/2018 | - | 2 | - | P5 | FY19
23 | 7642 | 7N | R | remodel |  | Av. Geronimo de Carvalho, 5964 | Atibaia | SP | 2018-07-10 | 2018-08-28 |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | OPENED 16/03/2019 | - | 3 | - | P8 | FY19
24 | 7632 | 7N | R | ground up |  | Avenida Nações Unidas, s/n Quadra 06 - loja 1 | Bauru | SP | 2017-08-20 | 2018-03-22 |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | OPENED 02/05/2019 | - | 4 | - | P9 | FY19
25 | 7636 | 7N | L | ground up |  | Av. Eugen Wissmann, 600 | Itu | SP | 2018-08-07 | 2018-10-29 |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | OPENED 02/05/2019 | - | 5 | - | P9 | FY19
26 | 7645 | 7N | L | ground up |  | Av. Av. José Paulino, 2638 | Paulinia | SP | 2018-08-24 | 2018-10-19 |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | OPENED 06/06/2019 | - | 6 | - | P11 | FY19
27 | 7640 | 65W | R | ground up |  | Av. Des. Dr. Eduardo Cunha de Abreu, 1455 | Carapicuiba | SP | 2018-06-04 | 2018-12-14 |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | OPENED 13/06/2019 | - | 7 | - | P11 | FY19
28 | 7643 | 7N | L | ground up |  | Av. José de Almeida Carvalho, 786 | Itapetininga | SP | 2018-07-10 | 2018-08-23 |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | OPENED 25/06/2019 | - | 8 | - | P11 | FY19
29 | 7637 | 7N | R | ground up |  | Av. Adhemar de Barros, s/n - quadra 3 | Guarujá | SP | 2018-03-29 | 2018-06-12 |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | OPENED 17/07/2019 | - | 9 | - | P12 | FY19
30 | 7646 | 7N | R | remodel |  | Av. Carlo Bonfanti, 40 | Leme | SP | 2018-09-21 | 2018-11-01 |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | OPENED 13/08/2019 | - | 10 | - | P13 | FY19
31 | 7641 | 7N | R | ground up |  | Av. Mogi Mirim, 970 | Mogi Guaçu | SP | 2018-06-04 | 2018-10-29 |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | OPENED 20/08/2019 | - | 11 | - | P13 | FY19
32 | 7652 | 7N | L | remodel |  | Av. dos Esportes, 1241 - Lado A | Valinhos | SP | 2018-12-14 | 2019-02-15 |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | OPENED 21/08/2019 | - | 12 | - | P13 | FY19
33 | 7655 | 7N | L | ground up |  | Estrada Kizaemon Takeuti, 1047 | Taboão | SP | 2019-02-01 | 2019-05-15 |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | OPENED 28/08/2019 | - | 13 | - | P13 | FY19
34 | 7644 | 7N | L | ground up |  | Av. Presidente Tancredo de Almeida Neves, 535 | Rio Claro | SP | 2018-08-07 | 2018-10-24 |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | OPENED 29/08/2019 | - | 14 | - | P13 | FY19
35 | 7649 | 7N | L | ground up |  | Av. Vereador João Batista Fitipaldi, 330 | Suzano | SP | 2018-10-25 | 2019-01-11 |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | OPENED 30/08/2019 | - | 15 | - | P13 | FY19
36 | 7624 | 65W | R | remodel | L | Rua Cica, 201 - loja 2 | Jundiaí | SP | 2016-12-15 | 2017-07-14 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | OPENED 20/09/2019 | - | 1 | P2 | P1 | FY20
37 | 7647 | 65W | L | ground up | P | Av. Onze de Agosto, 2846 | Tatuí | SP | 2018-09-21 | 2018-12-17 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | OPENED 21/11/2019 | - | 2 | P3 | P3 | FY20
38 | 7663 | 7N | R | ground up | L | Av. Goiás, 49 | Caraguatatuba | SP | 2019-05-31 | 2019-09-04 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | OPENED 15/02/2020 | - | 3 | P5 | P6 | FY20
39 | 7658 | 7N | R | ground up | L | Av. Sampaio Vidal, 977 | Marília | SP | 2019-03-22 | 2019-07-19 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | OPENED 29/05/2020 | - | 4 | P6 | P10 | FY20
40 | 7653 | 65UL | R | ground up | L | Av. Francisco Ferreira Lopes, 3181 | Mogi Cruzes | SP | 2018-11-27 | 2018-12-27 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | OPENED 06/06/2020 | - | 5 | P7 | P10 | FY20
41 | 7665 | 7N | L | ground up | L | Av. 43, 435 | Barretos | SP | 2019-06-27 | 2019-08-09 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | OPENED 12/06/2020 | - | 6 | P8 | P11 | FY20
42 | 7648 | 7N | L | ground up | L | Av. Pres. Tancredo Neves, 10 | SJC | SP | 2018-10-25 | 2019-05-03 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | OPENED 11/07/2020 | - | 7 | P8 | P12 | FY20
43 | 7659 | 7N | R | ground up | L | Av. Paulista, 985 | Americana | SP | 2019-03-22 | 2019-07-25 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | OPENED 26/08/2020 | - | 8 | P9 | P13 | FY20
44 | 7657 | 7N | R | ground up | L | Av. Itavuvu, 3621, Lote B - Bairro Região Norte - CEP: 18078-005 | Sorocaba II | SP | 2019-07-19 | 2019-10-30 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | OPENED 31/10/2020 | - | 1 | P1 | P3 | FY21
45 | 7671 | 65W | R | ground up | L | Av. Antonio Paschoal, nº 901 - Centro - CEP:14160-005 | Sertãozinho | SP | 2019-08-30 | 22-Out-2019 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | OPENED 18/11/2020 | - | 2 | P2 | P3 | FY21
46 | 7668 | 65W | R | ground up | L | Av. Doutor Nelson D'avila, 1757 - Vila das Acacias - CEP:12.245-030 | S.J.Campos | SP | 2019-07-19 | 2019-09-05 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | OPENED 11/02/2021 | - | 3 | P3 | P6 | FY21
47 | 7682 | 40N | R | ground up | L | Av. Antônio Piranga, nº 779 - Bairro Centro - CEP:09911-160 | Diadema | SP | 2020-07-10 | 2020-10-02 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | OPENED 27/04/2021 | - | 4 | P3 | P9 | FY21
48 | 7670 | 7N | R | ground up | P | Av. Marechal Castelo Branco, Nº 0, nº 450/480 e lote 9 - Bairro do Engenho - CEP: 13255-350 | Itatiba | SP | 2019-08-30 | 2019-12-20 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | OPENED 04/06/2021 | - | 5 | P4 | P10 | FY21
49 | 7672 | 65W | L | ground up | L | Av. Dona Francisca, nº167 - Vila Rezende - CEP: 13405-140 | Piracicaba II | SP | 2019-11-13 | 2019-12-06 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | OPENED 18/06/2021 | - | 6 | P4 | P11 | FY21
50 | 7675 | 40N | L | ground up | L | Av. Presidente Wilson, nº 1504 - Itararé - CEP: 11320-001 | São Vicente | SP | 2020-01-29 | 2020-08-26 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | OPENED 08/06/2021 | - | 7 | P7 | P13 | FY21
51 | 7678 | 65W | L | ground up | P+L | Av. Nossa Senhora do Bom Sucesso, nº s/n e nº 1555 - Bairro Cardoso - CEP: 12420-010 | Pindamonhangaba | SP | 2020-04-29 | 2020-07-29 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | OPENED 09/08/2021 | - | 8 | P8 | P13 | FY21
52 | 7677 | 7N | R | ground up | L | Av. da Amizade, nº 112, 2373, 2371 e 2437 - Chacara Jardim Bela Vsista - CEP: 13170-000 | Sumaré | SP | 2020-04-29 | 2020-07-07 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | OPENED 21/08/2021 | - | 9 | P9 | P13 | FY21
53 | 7679 | 65UL | R | groundup | P+L | Rua Amazonas, nº 33 e 63 - Bairro: Centro - CEP: 15800-032 | Catanduva | SP | 2020-06-12 | 2020-07-20 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | OPENED 08/11/2021 | - | 1 | P3 | P3 | FY22
54 | 7681 | 7N | R | groundup | L | Av. Dr. Lauro Corrêa da Silva, Nº4005 fundo com a Rua Maximo Jacon - Bairro: Jardim Solar dos Nobres - | Limeira | SP | 2020-06-12 | 2020-07-27 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | OPENED 20/12/2021 | - | 2 | P3 | P5 | FY22
55 | 7676 | 7N | R | groundup | P | Av. Euclides Miragaia, nº 1639-1649 - Birro: Vila Germano - CEP: 16200-130 | Birigui | SP | 2020-04-09 | 2020-07-07 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | OPENED 20/12/2021 | - | 3 | P5 | P5 | FY22
56 | 7650 | 40N | R | groundup | L | Av. Sport Club Corinthians Paulista, nº1130 - Bairro Santo Antonio - CEP: 06132-380 | Osasco | SP | 2018-11-27 | 2019-10-22 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | OPENED 31/03/2022 | - | 4 | P5 | P8 | FY22
57 | 7694 | 65W | R | groundup | L | Av. Dom Pedro I, nº 1844 - Bairro: Ipiranga - CEP:14055100 | Rib. Preto | SP | 2021-01-15 | 2021-03-31 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | OPENED 30/04/2022 | - | 5 | P7 | P9 | FY22
58 | 7603 | 7N | L | groundup | L | Av. Pinto Cobra, nº 0 - Bairro: Centro - Pouso Alegre - MG - CEP: 37.550-145 | Pouso Alegre | MG | 2021-03-12 | 2021-06-30 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | OPENED 02/05/2022 | - | 6 | P6 | P9 | FY22
59 | 7699 | 7N | L | groundup | L | Av. Juscelino Kubitchek de Oliveira, nº 895 - Bairro: Campo do Galvão - Compl: Ponto 02 - Guaratinguetá - SP -CEP:12505300 | Guaratinguetá | SP | 2021-04-30 | 2021-08-05 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | OPENED 12/05/2022 | - | 7 | P7 | P10 | FY22
60 | 7687 | 65W | R | groundup | P | Av. Da Glória, nº 55 - Bairro: Vila Glória - CEP: 19806-095 | Assis | SP | 2020-12-02 | 2020-12-30 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | OPENED 19/05/2022 | - | 8 | P9 | P10 | FY22
61 | 9406 | 40N | L | groundup | L | Av. Andrômeda, nº 423 - Bairro: Floradas de São José - São José dos Campos - SP - CEP:12230-00 | S.J.Campos | SP | 2021-05-27 | 2021-06-30 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | OPENED 20/05/2022 | - | 9 | P10 | P10 | FY22
62 | 7689 | 40N | R | groundup | L | Av. Conselheiro Nebias, nº 627 - Bairro: Paquetá - CEP: 11045-003 | Santos | SP | 2020-10-30 | 2021-01-11 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | OPENED 20/05/2022 | - | 10 | P11 | P10 | FY22
63 | 7698 | 65W | R | groundup | L | Av. Rondon Pacheco , nº 455 esq. Com a rua do Carioca - Bairro: Maracanã - Uberlândia - MG - CEP:38400-242 | Uberlândia | MG | 2021-04-09 | 2021-05-19 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | OPENED 17/06/2022 | - | 11 | P11 | P11 | FY22
64 | 7691 | 65W | R | groundup | P | Av. Governador Mário Covas, s/n - Bairro: Vila Industrial - Araçatuba - SP - Cep: 16072005 | Araçatuba | SP | 2021-02-18 | 2021-07-08 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | OPENED 06/07/2022 | - | 12 | P12 | P12 | FY22
65 | 7690 | 7N | L | groundup | L | Av. João Pinheiro - nº 1900 (LOTE 3A) - Bairro Vila Cruz - Poços de Caldas - MG - CEP: 37701-386 | Poços de Caldas | MG | 2021-02-18 | 2021-03-31 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | OPENED 18/07/2022 | - | 13 | P12 | P12 | FY22
66 | 9411 | 7N | L | groundup | P | Av. Juscelino Kubitschek | Patos de Minas | MG | 2021-06-02 | 2021-09-21 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | OPENED 03/08/2022 | - | 14 | P12 | P13 | FY22
67 | 7674 | 7N | R | groundup | P | Av. Brasil, nº 1049, 1063, 1073 - Vila Aparecida - CEP:14402-440 | Franca | SP | 2019-11-13 | 2019-12-06 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | OPENED 05/08/2022 | - | 15 | P13 | P13 | FY22
68 | 7685 | 7N | R | groundup | P | Av. Brasil, nº 4734 - Bairro: Jardim São Judas Tadeu - CEP: 15500-051 | Votuporanga | SP | 2020-09-24 | 2020-12-15 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | OPENED 23/08/2022 | - | 16 | P13 | P13 | FY22
69 | 9452 | 65W | R | remodel | L | Av. Taboão, 3762 | S. B. do Campo | SP | 2022-04-15 | 2022-04-25 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | OPENED 24/08/2022 | - | 17 | P13 | P13 | FY22
70 | 9410 | 65W | R | groundup | P | Av. Saul Elkind, 3825 - Bairro: Perigot de Souza - Londrina - PR - CEP: 86083-040 | Londrina | PR | 2021-06-02 | 2021-08-05 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | OPENED 26/08/2022 | - | 18 | P13 | P13 | FY22
71 | 9407 | 7N | R | groundup | P | Av. Roberto Conceição, S/N, Bairro: Lotes e Chacaras - Cambé - PR - CEP:86192-550 | Cambé | PR | 2021-06-02 | 2021-09-09 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | OPENED 26/08/2022 | - | 19 | P13 | P13 | FY22
72 | 9412 | 7N | L | groundup | L | Av. João Paulo II, 2 - Bairro: Centro - Araxá - MG - CEP: 38180-029 | Araxá | MG | 2021-07-22 | 2021-11-25 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | OPENED 26/08/2022 | - | 20 | P13 | P13 | FY22
73 | 7695 | 7N | L | groundup | L | Av. Dom Pedro I, nº 3614 - Bairro: Vila Americana - Santo André - SP - CEP:09132-032 | Sto. André | SP | 2020-12-17 | 2021-03-24 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | OPENED 22/10/2022 | - | 1 | P2 | P2 | FY23
74 | 9416 | 7N | R | groundup | L | Av. Minas Gerais, nº 999 Bairro: Jardim Apucarana - PR - CEP: 86804-000 | Apucarana | PR | 2021-09-03 | 2021-12-22 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | OPENED 02/11/2022 | - | 2 | P2 | P2 | FY23
75 | 7693 | 65W | L | groundup | P | Av. Brasil, nº 1686 - Bairro: Vila São Jorge - CEP: 19013250 | Pres. Prudente | SP | 2021-01-15 | 2021-03-02 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | OPENED 07/11/2022 | - | 3 | P3 | P3 | FY23
76 | 7692 | 40N | L | groundup | P | Av. Dep. Cantidio Sampaio, nº 6845- 6849 - Bairro: Cachoeirinha - SP - CEP:02857-010 (Taipas) | São Paulo | SP | 2021-05-27 | 2021-07-08 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | OPENED 18/11/2022 | - | 4 | P3 | P3 | FY23
77 | 7696 | 65W | R | groundup | P | Rua do Expedicionário, nº 447 Bairro: Centro, Ourinhos - SP, 19900-041 | Ourinhos | SP | 2021-03-12 | 2021-04-01 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | OPENED 18/11/2022 | - | 5 | P3 | P3 | FY23
78 | 9423 | 7N | L | remodel | L | Av. Dos Estados, nº 5911 - Parque Central - Santo André - SP - CEP: 09210-580 | Sto. André ll | SP | 2022-04-01 | 2022-04-25 | 2022-06-10 | 2022-08-15 | 2022-08-06 | 2022-08-12 | 2022-08-06 | 2022-10-11 | 2022-09-20 | 2022-09-23 | 2022-09-23 | 2022-09-23 | 2022-09-23 | 2022-10-21 | 2022-10-28 | 2022-11-03 | 2022-11-04 |  | 2022-11-11 | 2022-11-25 | 2022-11-25 | 21 | 6 | P4 | P4 | FY23
79 | 9419 | 40N | L | groundup | L | Av. Tiradentes, nº 929 - Bairro: Jardim Shangri Lá - Londrina - PR - CEP:86070-545 | Londrina II | PR | 2021-09-24 | 2022-01-28 | 2022-06-06 | 2022-07-25 | 2022-09-20 | 2022-09-26 | 2022-09-20 | 2022-12-02 | 2022-11-04 | 2022-11-07 | 2022-11-07 | 2022-11-07 | 2022-11-07 | 2022-12-05 | 2022-12-12 | 2022-12-18 | 2022-12-19 |  | 2022-12-26 | 2023-01-09 | 2023-01-16 | 28 | 7 | P4 | P6 | FY23
80 | 9464 | 7N | L | groundup | L | Avenida Raulina F Paschoal, 1532 | Catalão | GO | 2022-05-27 | 2022-06-09 | 2022-08-08 | 2022-10-06 | 2022-09-27 | 2022-10-03 | 2022-09-27 | 2022-12-09 | 2022-11-11 | 2022-11-14 | 2022-11-14 | 2022-11-14 | 2022-11-14 | 2022-12-12 | 2022-12-19 | 2022-12-25 | 2022-12-26 |  | 2023-01-02 | 2023-01-16 | 2023-01-23 | 28 | 8 | P4 | P6 | FY23
81 | 9444 | 65W | R | groundup | P | Av. Goioerê, 3133 3237 | Campo Mourão | PR | 2022-03-11 | 2022-04-22 | 2022-09-09 | 2022-10-10 | 2022-10-11 | 2022-10-17 | 2022-10-11 | 2022-12-23 | 2022-11-25 | 2022-11-28 | 2022-11-28 | 2022-11-28 | 2022-11-28 | 2022-12-26 | 2023-01-02 | 2023-01-08 | 2023-01-09 |  | 2023-01-16 | 2023-01-30 | 2023-02-06 | 28 | 9 | P5 | P6 | FY23
82 | 9449 | 7N | L | groundup | L | Av. Afonso Pena, 309 | Itumbiara | GO | 2022-04-15 | 2022-05-23 | 2022-09-30 | 2022-10-27 | 2022-10-23 | 2022-10-29 | 2022-10-23 | 2023-01-04 | 2022-12-07 | 2022-12-10 | 2022-12-10 | 2022-12-10 | 2022-12-10 | 2023-01-07 | 2023-01-14 | 2023-01-20 | 2023-01-21 |  | 2023-01-28 | 2023-02-11 | 2023-02-18 | 28 | 10 | P5 | P7 | FY23
83 | 9436 | 7N | R | groundup | L | Av. Padre Natal Pigatto, nº 615 Bairro: Centro - Campo Largo - PR - CEP: | Campo Largo | PR | 2021-12-17 | 2022-02-23 | 2022-10-03 | 2022-11-07 | 2022-11-08 | 2022-11-14 | 2022-11-08 | 2023-01-20 | 2022-12-23 | 2022-12-26 | 2022-12-26 | 2022-12-26 | 2022-12-26 | 2023-01-23 | 2023-01-30 | 2023-02-05 | 2023-02-06 |  | 2023-02-13 | 2023-02-27 | 2023-03-06 | 28 | 11 | P6 | P7 | FY23
85 | 9414 | 65W | R | groundup | P | Av. Francisco Junqueira, 1319 - Bairro: Jardim Mosteiro - Ribeirão Preto - SP - CEP: 14085-310 | Rib. Preto ll | SP | 2021-08-20 | 2022-03-30 | 2022-12-09 | 2022-12-19 | 2022-12-15 | 2022-12-21 | 2022-12-15 | 2023-02-19 | 2023-01-29 | 2023-02-01 | 2023-02-01 | 2023-02-01 | 2023-02-01 | 2023-03-01 | 2023-03-08 | 2023-03-14 | 2023-03-15 |  | 2023-03-22 | 2023-04-05 | 2023-04-05 | 21 | 12 | P7 | P8 | FY23
84 | 9438 | 65W | L | groundup | P | Av. General Carlos Cavalcanti, nº 692 / 748 - Ponta Grossa - PR - CEP: | Ponta Grossa | PR | 2022-01-14 | 2022-04-07 | 2022-12-13 | 2022-12-23 | 2022-12-19 | 2022-12-25 | 2022-12-19 | 2023-03-02 | 2023-02-02 | 2023-02-05 | 2023-02-05 | 2023-02-05 | 2023-02-05 | 2023-03-05 | 2023-03-12 | 2023-03-18 | 2023-03-19 |  | 2023-03-26 | 2023-04-09 | 2023-04-16 | 28 | 13 | P7 | P8 | FY23
86 | 7697 | 65W | R | groundup | P | Av. Santos Dumont, nº 268 - Bairro Vila Santos Dumont - Uberaba - MG - CEP: 38010-370 | Uberaba | MG | 2021-03-12 | 2021-07-26 | 2022-12-09 | 2022-12-19 | 2022-12-20 | 2022-12-26 | 2022-12-20 | 2023-03-03 | 2023-02-03 | 2023-02-06 | 2023-02-06 | 2023-02-06 | 2023-02-06 | 2023-03-06 | 2023-03-13 | 2023-03-19 | 2023-03-20 |  | 2023-03-27 | 2023-04-10 | 2023-04-17 | 28 | 14 | P8 | P8 | FY23
87 | 9446 | 7N | R | groundup | P | Av. Sen. Attilio Fontana, 5635 | Toledo | PR | 2022-04-01 | 2022-05-27 | 2022-12-20 | 2022-12-30 | 2022-12-31 | 2023-01-06 | 2022-12-31 | 2023-03-14 | 2023-02-14 | 2023-02-17 | 2023-02-17 | 2023-02-17 | 2023-02-17 | 2023-03-17 | 2023-03-24 | 2023-03-30 | 2023-03-31 |  | 2023-04-07 | 2023-04-21 | 2023-04-28 | 28 | 15 | P8 | P9 | FY23
88 | 9430 | 40N | L | groundup | P | Av. Brigadeiro Faria Lima, 695 - Bairro: Jardim Cocaia - Guarulhos - SP - CEP: 07130-000 (Cocaia) | Guarulhos ll | SP | 2021-11-23 | 2022-04-04 | 2022-12-08 | 2022-12-18 | 2023-01-08 | 2023-01-14 | 2023-01-08 | 2023-03-15 | 2023-02-22 | 2023-02-25 | 2023-02-25 | 2023-02-25 | 2023-02-25 | 2023-03-25 | 2023-04-01 | 2023-04-07 | 2023-04-08 |  | 2023-04-15 | 2023-04-29 | 2023-04-29 | 21 | 16 | P9 | P9 | FY23
89 | 7610 | 7N | R | groundup | L | Av. Maracanã, nº 1547/1644 - Bairro: Vila Industrial - Arapongas - PR - CEP: | Arapongas | PR | 2021-10-27 | 2022-07-05 | 2023-01-10 | 2023-01-20 | 2023-01-11 | 2023-01-17 | 2023-01-11 | 2023-03-25 | 2023-02-25 | 2023-02-28 | 2023-02-28 | 2023-02-28 | 2023-02-28 | 2023-03-28 | 2023-04-04 | 2023-04-10 | 2023-04-11 |  | 2023-04-18 | 2023-05-02 | 2023-05-09 | 28 | 17 | P9 | P10 | FY23
90 | 9456 | 7N | L | groundup | L | Av. Chico Júlio, 2.996 | Franca ll | SP | 2022-04-29 | 2022-07-05 | 2023-01-16 | 2023-01-26 | 2023-01-22 | 2023-01-28 | 2023-01-22 | 2023-03-29 | 2023-03-08 | 2023-03-11 | 2023-03-11 | 2023-03-11 | 2023-03-11 | 2023-04-08 | 2023-04-15 | 2023-04-21 | 2023-04-22 |  | 2023-04-29 | 2023-05-13 | 2023-05-13 | 21 | 18 | P9 | P10 | FY23
91 | 9431 | 7N | L | groundup | L | Av. Padre Francisco Salles Culturato, 1107 - Bairro: Centro - Araraquara - SP - CEP: 14801-250 | Araraquara ll | SP | 2022-03-11 | 2022-06-09 | 2023-01-20 | 2023-01-30 | 2023-01-26 | 2023-02-01 | 2023-01-26 | 2023-04-09 | 2023-03-12 | 2023-03-15 | 2023-03-15 | 2023-03-15 | 2023-03-15 | 2023-04-12 | 2023-04-19 | 2023-04-25 | 2023-04-26 |  | 2023-05-03 | 2023-05-17 | 2023-05-24 | 28 | 19 | P10 | P10 | FY23
92 | 9465 | 7N | L | groundup | L | Rua Iririú, 2659 | Joinville | SC | 2022-05-27 | 2022-08-10 | 2023-01-20 | 2023-01-30 | 2023-01-26 | 2023-02-01 | 2023-01-26 | 2023-04-09 | 2023-03-12 | 2023-03-15 | 2023-03-15 | 2023-03-15 | 2023-03-15 | 2023-04-12 | 2023-04-19 | 2023-04-25 | 2023-04-26 |  | 2023-05-03 | 2023-05-17 | 2023-05-24 | 28 | 20 | P10 | P10 | FY23
93 | 9440 | 65W | L | groundup | L | Rua Izaac Ferreira da Cruz, 4158 - Bairro: Sítio Cercado - Curitiba - PR - CEP:81910-000 | Curitiba II | PR | 2022-01-21 | 2022-04-18 | 2023-01-20 | 2023-01-30 | 2023-01-26 | 2023-02-01 | 2023-01-26 | 2023-04-09 | 2023-03-12 | 2023-03-15 | 2023-03-15 | 2023-03-15 | 2023-03-15 | 2023-04-12 | 2023-04-19 | 2023-04-25 | 2023-04-26 |  | 2023-05-03 | 2023-05-17 | 2023-05-24 | 28 | 21 | P11 | P10 | FY23
95 | 9460 | 7N | L | groundup | P | Av. Ver. Hamilton Reis Alves | Barra Mansa | RJ | 2022-05-13 | - | 2023-01-30 | 2023-02-09 | 2023-02-05 | 2023-02-11 | 2023-02-05 | 2023-04-19 | 2023-03-22 | 2023-03-25 | 2023-03-25 | 2023-03-25 | 2023-03-25 | 2023-04-22 | 2023-04-29 | 2023-05-05 | 2023-05-06 |  | 2023-05-13 | 2023-05-27 | 2023-06-03 | 28 | 22 | P11 | P10 | FY23
96 | 9435 | 65W | R | groundup | P | Estrada Alberto Hinoto, nº 1150 - Bairro: Jardim Claudia - Iataquaquecetuba - SP - CEP:08576-015 | Itaquaquecetuba | SP | 2021-12-17 | 2022-02-18 | 2023-01-30 | 2023-02-09 | 2023-02-15 | 2023-02-21 | 2023-02-15 | 2023-04-22 | 2023-04-01 | 2023-04-04 | 2023-04-04 | 2023-04-04 | 2023-04-04 | 2023-05-02 | 2023-05-09 | 2023-05-15 | 2023-05-16 |  | 2023-05-23 | 2023-06-06 | 2023-06-06 | 21 | 23 | P11 | P11 | FY23
98 | 9448 | 7N | R | groundup | P | Av. Independência | Aparecida de GO | GO | 2022-04-15 | 2022-04-28 | 2023-02-15 | 2023-02-25 | 2023-02-21 | 2023-02-27 | 2023-02-21 | 2023-05-05 | 2023-04-07 | 2023-04-10 | 2023-04-10 | 2023-04-10 | 2023-04-10 | 2023-05-08 | 2023-05-15 | 2023-05-21 | 2023-05-22 |  | 2023-05-29 | 2023-06-12 | 2023-06-19 | 28 | 24 | P11 | P11 | FY23
99 | 9421 | 7N | L | groundup | P+L | Av. José Fonseca e Silva, nº 615 - Bairro: Jardim Patrícia - Uberlândia - MG - CEP: 38.414-016 | Uberlândia ll | MG | 2021-10-15 | 2021-12-22 | 2023-02-17 | 2023-02-27 | 2023-02-23 | 2023-03-01 | 2023-02-23 | 2023-05-07 | 2023-04-09 | 2023-04-12 | 2023-04-12 | 2023-04-12 | 2023-04-12 | 2023-05-10 | 2023-05-17 | 2023-05-23 | 2023-05-24 |  | 2023-05-31 | 2023-06-14 | 2023-06-21 | 28 | 25 | P11 | P11 | FY23
100 | 7680 | 7N | L | groundup | P | Av. dos Estudantes, nº 2645 e 2585 - Bairro Jardim Canaa - CEP: 15025-310 | S. J. Rio Preto | SP | 2020-06-12 | 2020-09-01 | 2023-02-20 | 2023-03-02 | 2023-02-26 | 2023-03-04 | 2023-02-26 | 2023-05-10 | 2023-04-12 | 2023-04-15 | 2023-04-15 | 2023-04-15 | 2023-04-15 | 2023-05-13 | 2023-05-20 | 2023-05-26 | 2023-05-27 |  | 2023-06-03 | 2023-06-17 | 2023-06-24 | 28 | 26 | P12 | P11 | FY23
101 | 9417 | 7N | L | groundup | L | Av. JK, nº 1820 - Bairro: Bom Pastor - Divinópolis - MG - CEP: 35500-155 | Divinópolis | MG | 2021-09-24 | 2022-01-28 | 2023-02-24 | 2023-03-06 | 2023-03-07 | 2023-03-13 | 2023-03-07 | 2023-05-19 | 2023-04-21 | 2023-04-24 | 2023-04-24 | 2023-04-24 | 2023-04-24 | 2023-05-22 | 2023-05-29 | 2023-06-04 | 2023-06-05 |  | 2023-06-12 | 2023-06-26 | 2023-07-03 | 28 | 27 | P12 | P12 | FY23
102 | 9454 | 7N | R | groundup | P | Av. Nerópolis x Av. Goiás Norte | Goiânia | GO | 2022-04-29 | - | 2023-03-10 | 2023-03-20 | 2023-03-16 | 2023-03-22 | 2023-03-16 | 2023-05-28 | 2023-04-30 | 2023-05-03 | 2023-05-03 | 2023-05-03 | 2023-05-03 | 2023-05-31 | 2023-06-07 | 2023-06-13 | 2023-06-14 |  | 2023-06-21 | 2023-07-05 | 2023-07-12 | 28 | 28 | P12 | P12 | FY23
103 | 7664 | 7N | L | groundup | L | Av. Ruy Rodrigues, nº 1960 - Bairro: Chacara Santa Leticia - CEP: 13054-044 | Campinas III | SP | 2022-01-21 | 2022-02-15 | 2023-03-15 | 2023-03-25 | 2023-03-26 | 2023-04-01 | 2023-03-26 | 2023-05-31 | 2023-05-10 | 2023-05-13 | 2023-05-13 | 2023-05-13 | 2023-05-13 | 2023-06-10 | 2023-06-17 | 2023-06-23 | 2023-06-24 |  | 2023-07-01 | 2023-07-15 | 2023-07-15 | 21 | 29 | P12 | P12 | FY23
97 | 9424 | 40N | L | groundup | L | Rua Parapuã, nº 1984 - 1988, 2210 e 2024 - Vila Brasilândia - São Paulo - SP - CEP: 02831-001 | São Paulo | SP | 2021-10-15 | 2021-12-22 | 2023-02-14 | 2023-02-24 | 2023-03-27 | 2023-04-02 | 2023-03-27 | 2023-06-01 | 2023-05-11 | 2023-05-14 | 2023-05-14 | 2023-05-14 | 2023-05-14 | 2023-06-11 | 2023-06-18 | 2023-06-24 | 2023-06-25 |  | 2023-07-02 | 2023-07-16 | 2023-07-16 | 21 | 30 | P12 | P12 | FY23
104 | 9427 | 7N | R | groundup | P | Av. Colombo, nº 2888 - Bairro: Zona 7 - Maringá - PR – CEP: | Maringá | PR | 2021-10-27 | 19-Sep-2022 | 2023-03-10 | 2023-03-20 | 2023-03-21 | 2023-03-27 | 2023-03-21 | 2023-06-02 | 2023-05-05 | 2023-05-08 | 2023-05-08 | 2023-05-08 | 2023-05-08 | 2023-06-05 | 2023-06-12 | 2023-06-18 | 2023-06-19 |  | 2023-06-26 | 2023-07-10 | 2023-07-17 | 28 | 31 | P13 | P12 | FY23
105 | 9413 | 7N | L | groundup | P | Av. Dr. Antônio Marques dos Santos, nº 150 Bairro: Jardim Seyon - São José do Rio Preto - SP - CEP:15050-500 | S. J. Rio Preto II | SP | 2021-08-20 | - | 2023-03-15 | 2023-03-25 | 2023-03-21 | 2023-03-27 | 2023-03-21 | 2023-06-02 | 2023-05-05 | 2023-05-08 | 2023-05-08 | 2023-05-08 | 2023-05-08 | 2023-06-05 | 2023-06-12 | 2023-06-18 | 2023-06-19 |  | 2023-06-26 | 2023-07-10 | 2023-07-17 | 28 | 32 | P13 | P12 | FY23
106 | 9463 | 7N | L | groundup | L | Av. Ellis Maas, 844 - Capão Redondo | São Paulo | SP | 2022-05-13 | - | 2023-03-25 | 2023-04-04 | 2023-03-31 | 2023-04-06 | 2023-03-31 | 2023-06-05 | 2023-05-15 | 2023-05-18 | 2023-05-18 | 2023-05-18 | 2023-05-18 | 2023-06-15 | 2023-06-22 | 2023-06-28 | 2023-06-29 |  | 2023-07-06 | 2023-07-20 | 2023-07-20 | 21 | 33 | P13 | P12 | FY23
107 | 9443 | 7N | L | groundup | L | Av. das Américas, 700 | Betim | MG | 2022-03-11 | - | 2023-03-10 | 2023-03-20 | 2023-03-26 | 2023-04-01 | 2023-03-26 | 2023-06-07 | 2023-05-10 | 2023-05-13 | 2023-05-13 | 2023-05-13 | 2023-05-13 | 2023-06-10 | 2023-06-17 | 2023-06-23 | 2023-06-24 |  | 2023-07-01 | 2023-07-15 | 2023-07-22 | 28 | 34 | P13 | P12 | FY23
108 | 9439 | 7N | L | groundup | L | Av. Iraí, 861 - Bairro: Weissópolis - Pinhais - PR - CEP: 83321-000 | Pinhais | PR | 2022-01-21 | - | 2023-03-20 | 2023-03-30 | 2023-03-26 | 2023-04-01 | 2023-03-26 | 2023-06-07 | 2023-05-10 | 2023-05-13 | 2023-05-13 | 2023-05-13 | 2023-05-13 | 2023-06-10 | 2023-06-17 | 2023-06-23 | 2023-06-24 |  | 2023-07-01 | 2023-07-15 | 2023-07-22 | 28 | 35 | P13 | P12 | FY23
109 | 9403 | 7N | R | groundup | P | Av. Rio das Pedras, 1488 -Bairro: Jardim Aricanduva São Paulo - SP - CEP: 03452-100 (Rio das Pedras) | São Paulo | SP | 2021-04-30 | 2021-06-02 | 2023-02-20 | 2023-04-11 | 2023-04-07 | 2023-04-13 | 2023-04-07 | 2023-06-12 | 2023-05-22 | 2023-05-25 | 2023-05-25 | 2023-05-25 | 2023-05-25 | 2023-06-22 | 2023-06-29 | 2023-07-05 | 2023-07-06 |  | 2023-07-13 | 2023-07-27 | 2023-07-27 | 21 | 36 | - | P12 | FY23
110 | 9429 | 40N | R | groundup | L | Av. Abílio Machado com a Av. Brigadeiro Eduardo Gomes, nº 2510 e 3050 - Bairro: Coqueiro - Belo Horizonte - MG - CEP: 30870-100 (Alípio de Melo) | Belo Horizonte | MG | 2021-10-27 | 2022-06-09 | 2023-02-28 | 2023-03-10 | 2023-03-31 | 2023-04-06 | 2023-03-31 | 2023-06-12 | 2023-05-15 | 2023-05-18 | 2023-05-18 | 2023-05-18 | 2023-05-18 | 2023-06-15 | 2023-06-22 | 2023-06-28 | 2023-06-29 |  | 2023-07-06 | 2023-07-20 | 2023-07-27 | 28 | 37 | - | P12 | FY23
111 | 9442 | 65W | R | groundup | P | Rua Dr. Curvelo Cavante, 579 | Itaguaí | RJ | 2022-04-01 | 2022-03-11 | 2023-03-27 | 2023-04-06 | 2023-04-02 | 2023-04-08 | 2023-04-02 | 2023-06-14 | 2023-05-17 | 2023-05-20 | 2023-05-20 | 2023-05-20 | 2023-05-20 | 2023-06-17 | 2023-06-24 | 2023-06-30 | 2023-07-01 |  | 2023-07-08 | 2023-07-22 | 2023-07-29 | 28 | 38 | - | P12 | FY23
112 | 9432 | 65W | R | groundup | P | Av. Vilarinho, 1461 - Bairro: Venda Nova - Belo Horizonte - MG - CEP: 31615-250 (Venda Nova) | Belo Horizonte ll | MG | 2021-11-23 | 2021-12-22 | 2023-03-25 | 2023-04-04 | 2023-04-05 | 2023-04-11 | 2023-04-05 | 2023-06-17 | 2023-05-20 | 2023-05-23 | 2023-05-23 | 2023-05-23 | 2023-05-23 | 2023-06-20 | 2023-06-27 | 2023-07-03 | 2023-07-04 |  | 2023-07-11 | 2023-07-25 | 2023-08-01 | 28 | 39 | - | P13 | FY23
113 | 9451 | 7N | L | groundup | L | Av. Vinte e Dois de Maio, 4.791 | Itaboraí | RJ | 2022-04-15 | 2022-08-15 | 2023-04-10 | 2023-04-20 | 2023-04-16 | 2023-04-22 | 2023-04-16 | 2023-06-28 | 2023-05-31 | 2023-06-03 | 2023-06-03 | 2023-06-03 | 2023-06-03 | 2023-07-01 | 2023-07-08 | 2023-07-14 | 2023-07-15 |  | 2023-07-22 | 2023-08-05 | 2023-08-12 | 28 | 40 | - | P13 | FY23
114 | 7660 | 7N | R | groundup | L | Av. Mauricio Galli, 0 - Bairro: Loteamento Jardim Marivam - CEP:14806-095 (Savegnago) | Araraquara | SP | 2019-04-12 | 2019-08-14 | 2023-04-24 | 2023-05-04 | 2023-04-30 | 2023-05-06 | 2023-04-30 | 2023-07-05 | 2023-06-14 | 2023-06-17 | 2023-06-17 | 2023-06-17 | 2023-06-17 | 2023-07-15 | 2023-07-22 | 2023-07-28 | 2023-07-29 |  | 2023-08-05 | 2023-08-19 | 2023-08-19 | 21 | 41 | - | P13 | FY23
115 | 9405 | 40W | L | groundup | P | Praça Manoel de Souza Araújo, nº 3 - Jardim Sao Jose, São Paulo - SP, 02969-120 (Pirituba) | São Paulo | SP | 2021-05-10 | 2021-06-09 | 2023-03-20 | 2023-03-30 | 2023-05-05 | 2023-05-11 | 2023-05-05 | 2023-07-10 | 2023-06-19 | 2023-06-22 | 2023-06-22 | 2023-06-22 | 2023-06-22 | 2023-07-20 | 2023-07-27 | 2023-08-02 | 2023-08-03 |  | 2023-08-10 | 2023-08-24 | 2023-08-24 | 21 | 42 | - | P13 | FY23
116 | 9458 | 7N | L | groundup | L | Av. Cristiano Machado, 2540 | Belo Horizonte lll | MG | 2022-05-13 | - | 2023-04-23 | 2023-05-03 | 2023-04-29 | 2023-05-05 | 2023-04-29 | 2023-07-11 | 2023-06-13 | 2023-06-16 | 2023-06-16 | 2023-06-16 | 2023-06-16 | 2023-07-14 | 2023-07-21 | 2023-07-27 | 2023-07-28 |  | 2023-08-04 | 2023-08-18 | 2023-08-25 | 28 | 43 | - | P13 | FY23
117 | 9459 | 7N | L | groundup | L | Av. Jove Soares | Itaúna | MG | 2022-05-13 | - | 2023-04-23 | 2023-05-03 | 2023-04-29 | 2023-05-05 | 2023-04-29 | 2023-07-11 | 2023-06-13 | 2023-06-16 | 2023-06-16 | 2023-06-16 | 2023-06-16 | 2023-07-14 | 2023-07-21 | 2023-07-27 | 2023-07-28 |  | 2023-08-04 | 2023-08-18 | 2023-08-25 | 28 | 44 | - | P13 | FY23
118 | 9461 | 65W | R | groundup | L | Rua Domicio da Gama, 386 | Maricá | RJ | 2022-05-13 | - | 2023-04-23 | 2023-05-03 | 2023-04-29 | 2023-05-05 | 2023-04-29 | 2023-07-11 | 2023-06-13 | 2023-06-16 | 2023-06-16 | 2023-06-16 | 2023-06-16 | 2023-07-14 | 2023-07-21 | 2023-07-27 | 2023-07-28 |  | 2023-08-04 | 2023-08-18 | 2023-08-25 | 28 | 45 | - | P13 | FY23
119 | 9462 | 65W | R | groundup | L | Estrada do Monteiro | Rio de Janeiro | RJ | 2022-05-13 | 31-Aug-2022 | 2023-04-23 | 2023-05-03 | 2023-04-29 | 2023-05-05 | 2023-04-29 | 2023-07-11 | 2023-06-13 | 2023-06-16 | 2023-06-16 | 2023-06-16 | 2023-06-16 | 2023-07-14 | 2023-07-21 | 2023-07-27 | 2023-07-28 |  | 2023-08-04 | 2023-08-18 | 2023-08-25 | 28 | 46 | - | P13 | FY23
94 | 9437 | 7N | R | groundup | P | Av. Francisco Krueger, nº 6305 - Almirante Tamandaré - Curitiba - PR - CEP: | Curitiba | PR | 2022-01-14 | 2022-04-28 | 2023-04-25 | 2023-05-05 | 2023-05-01 | 2023-05-07 | 2023-05-01 | 2023-07-13 | 2023-06-15 | 2023-06-18 | 2023-06-18 | 2023-06-18 | 2023-06-18 | 2023-07-16 | 2023-07-23 | 2023-07-29 | 2023-07-30 |  | 2023-08-06 | 2023-08-20 | 2023-08-27 | 28 | 47 | - | P13 | FY23
120 | 9473 | 7N | L | groundup | P | Av. São Miguel, 6259 - Ponte Rasa | São Paulo | SP | 2022-07-29 | - | 2023-07-03 | 2023-07-13 | 2023-07-09 | 2023-07-15 | 2023-07-09 | 2023-09-13 | 2023-08-23 | 2023-08-26 | 2023-08-26 | 2023-08-26 | 2023-08-26 | 2023-09-23 | 2023-09-30 | 2023-10-06 | 2023-10-07 |  | 2023-10-14 | 2023-10-28 | 2023-10-28 | 21 | 1 | - | P2 | FY24
121 | 9468 | 7N | R | groundup | P | Av. Conselheiro Július ARP, 230 | Nova Friburgo | RJ | 2022-07-29 | - | 2023-07-03 | 2023-07-13 | 2023-07-09 | 2023-07-15 | 2023-07-09 | 2023-09-20 | 2023-08-23 | 2023-08-26 | 2023-08-26 | 2023-08-26 | 2023-08-26 | 2023-09-23 | 2023-09-30 | 2023-10-06 | 2023-10-07 |  | 2023-10-14 | 2023-10-28 | 2023-11-04 | 28 | 2 | - | P3 | FY24
122 | 9469 | 65W | R | groundup | P | Av. Independência, 3229, setor Leste | Goiânia ll | GO | 2022-07-29 | - | 2023-07-03 | 2023-07-13 | 2023-07-09 | 2023-07-15 | 2023-07-09 | 2023-09-20 | 2023-08-23 | 2023-08-26 | 2023-08-26 | 2023-08-26 | 2023-08-26 | 2023-09-23 | 2023-09-30 | 2023-10-06 | 2023-10-07 |  | 2023-10-14 | 2023-10-28 | 2023-11-04 | 28 | 3 | - | P3 | FY24
123 | 9472 | 7N | L | groundup | P | Av. Anhanguera, LT 5 QD 7 | Goiânia lll | GO | 2022-07-29 | - | 2023-07-03 | 2023-07-13 | 2023-07-09 | 2023-07-15 | 2023-07-09 | 2023-09-20 | 2023-08-23 | 2023-08-26 | 2023-08-26 | 2023-08-26 | 2023-08-26 | 2023-09-23 | 2023-09-30 | 2023-10-06 | 2023-10-07 |  | 2023-10-14 | 2023-10-28 | 2023-11-04 | 28 | 4 | - | P3 | FY24
124 | 9467 | 7N | L | groundup | P | Av. Centenário, 4334 | Criciúma | SC | 2022-08-05 | 2022-08-23 | 2023-07-10 | 2023-07-20 | 2023-07-16 | 2023-07-22 | 2023-07-16 | 2023-09-27 | 2023-08-30 | 2023-09-02 | 2023-09-02 | 2023-09-02 | 2023-09-02 | 2023-09-30 | 2023-10-07 | 2023-10-13 | 2023-10-14 |  | 2023-10-21 | 2023-11-04 | 2023-11-11 | 28 | 5 | - | P3 | FY24
125 | 9471 | 7N | L | groundup | L | R. Gen. Potiguara, 2890 Fazendinha | Curitiba lll | PR | 2022-08-05 | 06-Sep-2022 | 2023-07-10 | 2023-07-20 | 2023-07-16 | 2023-07-22 | 2023-07-16 | 2023-09-27 | 2023-08-30 | 2023-09-02 | 2023-09-02 | 2023-09-02 | 2023-09-02 | 2023-09-30 | 2023-10-07 | 2023-10-13 | 2023-10-14 |  | 2023-10-21 | 2023-11-04 | 2023-11-11 | 28 | 6 | - | P3 | FY24
126 | 9466 | 7N | L | groundup | L | R. Benjamim Constant, 200 | Barbacena | MG | 2022-08-05 | - | 2023-07-10 | 2023-07-20 | 2023-07-16 | 2023-07-22 | 2023-07-16 | 2023-09-27 | 2023-08-30 | 2023-09-02 | 2023-09-02 | 2023-09-02 | 2023-09-02 | 2023-09-30 | 2023-10-07 | 2023-10-13 | 2023-10-14 |  | 2023-10-21 | 2023-11-04 | 2023-11-11 | 28 | 7 | - | P3 | FY24
127 | 9476 | 7N | L | groundup | L | Estrada Dom João Nery, 4856 | Guaianazes | SP | 2022-08-19 | - | 2023-07-25 | 2023-08-04 | 2023-07-31 | 2023-08-06 | 2023-07-31 | 2023-10-12 | 2023-09-14 | 2023-09-17 | 2023-09-17 | 2023-09-17 | 2023-09-17 | 2023-10-15 | 2023-10-22 | 2023-10-28 | 2023-10-29 |  | 2023-11-05 | 2023-11-19 | 2023-11-26 | 28 | 8 | - | P4 | FY24
128 | 9474 | 65W | L | groundup | P | Av Sapopemba, 6851 | São Paulo | SP | 2022-08-19 | - | 2023-07-25 | 2023-08-04 | 2023-07-31 | 2023-08-06 | 2023-07-31 | 2023-10-12 | 2023-09-14 | 2023-09-17 | 2023-09-17 | 2023-09-17 | 2023-09-17 | 2023-10-15 | 2023-10-22 | 2023-10-28 | 2023-10-29 |  | 2023-11-05 | 2023-11-19 | 2023-11-26 | 28 | 9 | - | P4 | FY24
129 | 9470 | 40N | R | groundup | P | Estrada dos Bandeirantes, 867 | Rio de Janeiro ll | RJ | 2022-08-05 | - | 2023-07-10 | 2023-07-20 | 2023-08-10 | 2023-08-16 | 2023-08-10 | 2023-10-22 | 2023-09-24 | 2023-09-27 | 2023-09-27 | 2023-09-27 | 2023-09-27 | 2023-10-25 | 2023-11-01 | 2023-11-07 | 2023-11-08 |  | 2023-11-15 | 2023-11-29 | 2023-12-06 | 28 | 10 | - | P3 | FY24
130 | tbd | 7N | L | groundup | P | Av. Teixeira e Souza, 2424 | Cabo Frio | RJ | 2022-10-28 | - | 2023-08-04 | 2023-08-14 | 2023-08-10 | 2023-08-16 | 2023-08-10 | 2023-10-22 | 2023-09-24 | 2023-09-27 | 2023-09-27 | 2023-09-27 | 2023-09-27 | 2023-10-25 | 2023-11-01 | 2023-11-07 | 2023-11-08 |  | 2023-11-15 | 2023-11-29 | 2023-12-06 | 28 | 11 | - | P5 | FY24
131 | tbd | 7N | R | groundup | P | Av. Rubem bento Alves, 829 | Caxias do Sul | RS | 2022-09-09 | - | 2023-08-14 | 2023-08-24 | 2023-08-20 | 2023-08-26 | 2023-08-20 | 2023-11-01 | 2023-10-04 | 2023-10-07 | 2023-10-07 | 2023-10-07 | 2023-10-07 | 2023-11-04 | 2023-11-11 | 2023-11-17 | 2023-11-18 |  | 2023-11-25 | 2023-12-09 | 2023-12-16 | 28 | 12 | - | P5 | FY24
132 | tbd | 7N | R | groundup | L | Rua Estefano José Vanolli, 1729 | Itajaí | SC | 2022-09-09 | - | 2023-08-14 | 2023-08-24 | 2023-08-20 | 2023-08-26 | 2023-08-20 | 2023-11-01 | 2023-10-04 | 2023-10-07 | 2023-10-07 | 2023-10-07 | 2023-10-07 | 2023-11-04 | 2023-11-11 | 2023-11-17 | 2023-11-18 |  | 2023-11-25 | 2023-12-09 | 2023-12-16 | 28 | 13 | - | P5 | FY24
133 | tbd | 65W | R | groundup | P | Av. Parobé, 722 | São Leopoldo | RS | 2022-09-09 | - | 2023-08-14 | 2023-08-24 | 2023-08-20 | 2023-08-26 | 2023-08-20 | 2023-11-01 | 2023-10-04 | 2023-10-07 | 2023-10-07 | 2023-10-07 | 2023-10-07 | 2023-11-04 | 2023-11-11 | 2023-11-17 | 2023-11-18 |  | 2023-11-25 | 2023-12-09 | 2023-12-16 | 28 | 14 | - | P5 | FY24
134 | tbd | 7N | L | groundup | L | R. Cândido Benício, 2113 (praça seca) | Rio de Janeiro lll | RJ | 2022-09-29 | - | 2023-09-04 | 2023-09-14 | 2023-09-10 | 2023-09-16 | 2023-09-10 | 2023-11-22 | 2023-10-25 | 2023-10-28 | 2023-10-28 | 2023-10-28 | 2023-10-28 | 2023-11-25 | 2023-12-02 | 2023-12-08 | 2023-12-09 |  | 2023-12-16 | 2023-12-30 | 2024-01-06 | 28 | 15 | - | P5 | FY24
135 | tbd | 65W | L | groundup | L | Av. Londrina, 3.860 | Umuarama | PR | 2022-09-29 | - | 2023-09-04 | 2023-09-14 | 2023-09-10 | 2023-09-16 | 2023-09-10 | 2023-11-22 | 2023-10-25 | 2023-10-28 | 2023-10-28 | 2023-10-28 | 2023-10-28 | 2023-11-25 | 2023-12-02 | 2023-12-08 | 2023-12-09 |  | 2023-12-16 | 2023-12-30 | 2024-01-06 | 28 | 16 | - | P5 | FY24
136 | tbd | 7N | R | remodel | L | Av. Pereira Barreto, 1536 | Sto. André lll | SP | 2022-10-14 | - | 2023-09-15 | 2023-09-25 | 2023-09-06 | 2023-09-12 | 2023-09-06 | 2023-11-18 | 2023-10-21 | 2023-10-24 | 2023-10-24 | 2023-10-24 | 2023-10-24 | 2023-11-21 | 2023-11-28 | 2023-12-04 | 2023-12-05 |  | 2023-12-12 | 2023-12-26 | 2024-01-02 | 28 | 17 | - | P5 | FY24
137 | tbd | 7N | R | groundup | P | Avenida Moacyr Silvestre, 1268 | Guarapuava | PR | 2022-10-14 | - | 2023-09-15 | 2023-09-25 | 2023-09-21 | 2023-09-27 | 2023-09-21 | 2023-12-03 | 2023-11-05 | 2023-11-08 | 2023-11-08 | 2023-11-08 | 2023-11-08 | 2023-12-06 | 2023-12-13 | 2023-12-19 | 2023-12-20 |  | 2023-12-27 | 2024-01-10 | 2024-01-17 | 28 | 18 | - | P6 | FY24
138 | tbd | 7N | L | groundup | L | R. General Rondon, 890 | Petrópolis | RJ | 2022-10-14 | - | 2023-09-15 | 2023-09-25 | 2023-09-21 | 2023-09-27 | 2023-09-21 | 2023-12-03 | 2023-11-05 | 2023-11-08 | 2023-11-08 | 2023-11-08 | 2023-11-08 | 2023-12-06 | 2023-12-13 | 2023-12-19 | 2023-12-20 |  | 2023-12-27 | 2024-01-10 | 2024-01-17 | 28 | 19 | - | P6 | FY24
139 | tbd | 7N | R | groundup | L | Av. Brasil, 2065 | Cascavel | PR | 2022-10-14 | - | 2023-09-15 | 2023-09-25 | 2023-09-21 | 2023-09-27 | 2023-09-21 | 2023-12-03 | 2023-11-05 | 2023-11-08 | 2023-11-08 | 2023-11-08 | 2023-11-08 | 2023-12-06 | 2023-12-13 | 2023-12-19 | 2023-12-20 |  | 2023-12-27 | 2024-01-10 | 2024-01-17 | 28 | 20 | - | P6 | FY24
140 | tbd | 7N Hub | R | groundup | L | Av. Rio Verde, 2694 | Goiânia V | GO | 2022-09-09 | 07-Oct-2022 | 2023-08-14 | 2023-08-24 | 2023-10-04 | 2023-10-10 | 2023-10-04 | 2023-12-16 | 2023-11-18 | 2023-11-21 | 2023-11-21 | 2023-11-21 | 2023-11-21 | 2023-12-19 | 2023-12-26 | 2024-01-01 | 2024-01-02 |  | 2024-01-09 | 2024-01-23 | 2024-01-30 | 28 | 21 | - | P6 | FY24
141 | tbd | 7N Hub | L | groundup | P | Av. Boqueirão, 2354 | Canoas | RS | 2022-10-28 | - | 2023-08-14 | 2023-08-24 | 2023-10-04 | 2023-10-10 | 2023-10-04 | 2023-12-16 | 2023-11-18 | 2023-11-21 | 2023-11-21 | 2023-11-21 | 2023-11-21 | 2023-12-19 | 2023-12-26 | 2024-01-01 | 2024-01-02 |  | 2024-01-09 | 2024-01-23 | 2024-01-30 | 28 | 22 | - | P6 | FY24
142 | tbd | 7N | R | groundup | P | Rua Presidente Epitácio Pessoa | Jaraguá do Sul | RS | 2022-10-28 | - | 2023-09-30 | 2023-10-10 | 2023-10-06 | 2023-10-12 | 2023-10-06 | 2023-12-18 | 2023-11-20 | 2023-11-23 | 2023-11-23 | 2023-11-23 | 2023-11-23 | 2023-12-21 | 2023-12-28 | 2024-01-03 | 2024-01-04 |  | 2024-01-11 | 2024-01-25 | 2024-02-01 | 28 | 23 | - | P6 | FY24
143 | tbd | 7N | L | groundup | P | Av. Major Rangel | Avaré | SP | 2022-11-04 | - | 2023-10-10 | 2023-10-20 | 2023-10-16 | 2023-10-22 | 2023-10-16 | 2023-12-21 | 2023-11-30 | 2023-12-03 | 2023-12-03 | 2023-12-03 | 2023-12-03 | 2023-12-31 | 2024-01-07 | 2024-01-13 | 2024-01-14 |  | 2024-01-21 | 2024-02-04 | 2024-02-04 | 21 | 24 | - | P6 | FY24
144 | tbd | 7N | R | groundup | L | Av. Conselheiro Carrão, 1353 | São Paulo | SP | 2022-11-04 | - | 2023-10-10 | 2023-10-20 | 2023-10-21 | 2023-10-27 | 2023-10-21 | 2023-12-26 | 2023-12-05 | 2023-12-08 | 2023-12-08 | 2023-12-08 | 2023-12-08 | 2024-01-05 | 2024-01-12 | 2024-01-18 | 2024-01-19 |  | 2024-01-26 | 2024-02-09 | 2024-02-09 | 21 | 25 | - | P6 | FY24
145 | tbd | 7N | L | groundup | P | Av. Pres. Getúlio Vargas, 418 | Alvorada | RS | 2022-11-04 | - | 2023-10-10 | 2023-10-20 | 2023-10-16 | 2023-10-22 | 2023-10-16 | 2023-12-28 | 2023-11-30 | 2023-12-03 | 2023-12-03 | 2023-12-03 | 2023-12-03 | 2023-12-31 | 2024-01-07 | 2024-01-13 | 2024-01-14 |  | 2024-01-21 | 2024-02-04 | 2024-02-11 | 28 | 26 | - | P6 | FY24
146 | tbd | 65W | L | remodel | L | Av. Antônio Luiz Faedo, 1779 | F. Beltrão | PR | 2022-11-17 | - | 2023-10-25 | 2023-11-04 | 2023-10-11 | 2023-10-17 | 2023-10-11 | 2023-12-23 | 2023-11-25 | 2023-11-28 | 2023-11-28 | 2023-11-28 | 2023-11-28 | 2023-12-26 | 2024-01-02 | 2024-01-08 | 2024-01-09 |  | 2024-01-16 | 2024-01-30 | 2024-02-06 | 28 | 27 | - | P6 | FY24
147 | tbd | 7N | L | groundup | L | R. Márcio Beck Machado, 80 (Cidade Tiradentes) | São Paulo | SP | 2022-11-17 | - | 2023-10-25 | 2023-11-04 | 2023-10-31 | 2023-11-06 | 2023-10-31 | 2024-01-05 | 2023-12-15 | 2023-12-18 | 2023-12-18 | 2023-12-18 | 2023-12-18 | 2024-01-15 | 2024-01-22 | 2024-01-28 | 2024-01-29 |  | 2024-02-05 | 2024-02-19 | 2024-02-19 | 21 | 28 | - | P7 | FY24
DROP SITES
| 9409 | 7N | R | groundup | L | Av. Conselheiro Moreira Barros, 4156 - Bairro: Lauzane Paulista - SP - CEP:02430-002 (Lauzane Pta.) | São Paulo lauzane | SP | 2021-06-11 | - | 2022-08-05 | 2022-08-15 | 2022-08-21 | 2022-08-27 | 2022-08-21 | 2022-10-26 | 2022-10-05 | 2022-10-08 | 2022-10-08 | 2022-10-08 | 2022-10-08 | 2022-11-05 | 2022-11-12 | 2022-11-18 | 2022-11-19 |  | 2022-11-26 | 2022-12-10 | 2022-12-10
| 9422 | 65W | L | ground up | L | Rua Úrsula Paulino, 1292 | Belo Horizonte jd.betânia | MG | 2021-10-15 | - | 2023-02-15 | 2023-02-25 | 2023-02-26 | 2023-03-04 | 2023-02-26 | 2023-05-10 | 2023-04-12 | 2023-04-15 | 2023-04-15 | 2023-04-15 | 2023-04-15 | 2023-05-13 | 2023-05-20 | 2023-05-26 | 2023-05-27 |  | 2023-06-03 | 2023-06-17 | 2023-06-24
| 7669 | 65W | R | remodel | L | Av. dos Imigrantes, nº 2.345 (Galpão Área 4) - Lavapes - CEP: 12902-000 | Bragança Pta. | SP | 2019-08-20 | - | 2022-10-05 | 2022-10-12 | 2022-08-29 | 2022-09-04 | 2022-08-29 | 2022-10-31 | 2022-10-13 | 2022-10-16 | 2022-10-16 | 2022-10-16 | 2022-10-16 | 2022-11-13 | 2022-11-20 | 2022-11-26 | 2022-11-27 |  | 2022-12-04 | 2022-12-18 | 2022-12-15
| 9420 | 7N | R | ground up | L | Av. Princesa do Sul, 690 | Varginha | MG | 2021-09-24 | - | 2023-01-15 | 2023-01-25 | 2023-01-21 | 2023-01-27 | 2023-01-21 | 2023-04-04 | 2023-03-07 | 2023-03-10 | 2023-03-10 | 2023-03-10 | 2023-03-10 | 2023-04-07 | 2023-04-14 | 2023-04-20 | 2023-04-21 |  | 2023-04-28 | 2023-05-12 | 2023-05-19
| 9428 | 65W | R | ground up | L | Av. Santa Catarina, nº 1225 - Bairro: Vila Mascote - São Paulo - SP - CEP 04378-300 (Vila Mascote) | São Paulo v.mascote | SP | 2021-10-27 | - | 2023-02-01 | 2023-02-11 | 2023-02-07 | 2023-02-13 | 2023-02-07 | 2023-04-14 | 2023-03-24 | 2023-03-27 | 2023-03-27 | 2023-03-27 | 2023-03-27 | 2023-04-24 | 2023-05-01 | 2023-05-07 | 2023-05-08 |  | 2023-05-15 | 2023-05-29 | 2023-05-29
| TBD | 7N | R | ground up | L | Rua Izaac Ferreira da Cruz, nº 3900 - Bairro: Sítio Cercado - Curitiba - PR - CEP: (Sítio Cercado) | Curitiba | PR | 2021-12-02 | - | 2023-03-15 | 2023-03-25 | 2023-03-21 | 2023-03-27 | 2023-03-21 | 2023-05-26 | 2023-05-05 | 2023-05-08 | 2023-05-08 | 2023-05-08 | 2023-05-08 | 2023-06-05 | 2023-06-12 | 2023-06-18 | 2023-06-19 |  | 2023-06-26 | 2023-07-10 | 2023-07-10
| 9425 | 7N | R | ground up | L | Av. Souza Ramos, nº 108 - Guaianazes - São Paulo - SP - CEP: 08490-490 (Cidade Tiradentes) | São Paulo cid.tiradentes | SP | 2021-10-15 | - | 2023-01-15 | 2023-01-25 | 2023-01-21 | 2023-01-27 | 2023-01-21 | 2023-03-28 | 2023-03-07 | 2023-03-10 | 2023-03-10 | 2023-03-10 | 2023-03-10 | 2023-04-07 | 2023-04-14 | 2023-04-20 | 2023-04-21 |  | 2023-04-28 | 2023-05-12 | 2023-05-12
| 9441 | 7N | R | ground up | P | Av. Antônio de Almeida, 752 | Volta Redonda | RJ | 2022-02-04 | - | 2023-05-02 | 2023-05-12 | 2023-05-18 | 2023-05-24 | 2023-05-18 | 2023-07-30 | 2023-07-02 | 2023-07-05 | 2023-07-05 | 2023-07-05 | 2023-07-05 | 2023-08-02 | 2023-08-09 | 2023-08-15 | 2023-08-16 |  | 2023-08-23 | 2023-09-06 | 2023-09-13
| 9415 | 7N | L | ground up | P | Av. Sapopemba, 16426 - Bairro: Jardim Vera Cruz (Zona Leste) - São Paulo - SP - CEP: 08330-180 | São Paulo sapopemba | SP | 2021-08-20 | - | 2022-11-17 | 2022-11-27 | 2022-11-23 | 2022-11-29 | 2022-11-23 | 2023-01-28 | 2023-01-07 | 2023-01-10 | 2023-01-10 | 2023-01-10 | 2023-01-10 | 2023-02-07 | 2023-02-14 | 2023-02-20 | 2023-02-21 |  | 2023-02-28 | 2023-03-14 | 2023-03-14
| 9445 | 7N | L | ground up | L | Estrada do Monteiro, 582 | Campo Grande | RJ | 2022-03-11 | - | 2023-04-05 | 2023-04-15 | 2023-04-11 | 2023-04-17 | 2023-04-11 | 2023-06-23 | 2023-05-26 | 2023-05-29 | 2023-05-29 | 2023-05-29 | 2023-05-29 | 2023-06-26 | 2023-07-03 | 2023-07-09 | 2023-07-10 |  | 2023-07-17 | 2023-07-31 | 2023-08-07
| 9433 | 7N | R | ground up | L | Av.dos Andradas nº 4000, Bairro: Pompéia - Belo Horizonte - MG - CEP: 30280-020 (Pompéia) | Belo Horizonte lV | MG | 2021-12-17 | - | 2023-03-07 | 2023-03-17 | 2023-03-13 | 2023-03-19 | 2023-03-13 | 2023-05-25 | 2023-04-27 | 2023-04-30 | 2023-04-30 | 2023-04-30 | 2023-04-30 | 2023-05-28 | 2023-06-04 | 2023-06-10 | 2023-06-11 |  | 2023-06-18 | 2023-07-02 | 2023-07-09
| 9418 | 65W | R | ground up | L | Rua Waldomiro Lobo, nº 86 - Bairro: Guarani - Belo Horizonte - MG - CEP: 31814-620 | Belo Horizonte ll | MG | 2021-12-17 | - | 2023-03-07 | 2023-03-17 | 2023-03-13 | 2023-03-19 | 2023-03-13 | 2023-05-25 | 2023-04-27 | 2023-04-30 | 2023-04-30 | 2023-04-30 | 2023-04-30 | 2023-05-28 | 2023-06-04 | 2023-06-10 | 2023-06-11 |  | 2023-06-18 | 2023-07-02 | 2023-07-09
118 | 9455 | 7N | L | ground up | P | Av. Pref Waldemar Grubba, 1.471 | Jaraguá do Sul | SC | 2022-04-29 | - | 2023-04-14 | 2023-04-24 | 2023-04-25 | 2023-05-01 | 2023-04-25 | -45 | 2023-06-09 | 2023-06-12 | 2023-06-12 | 2023-06-12 | 2023-06-12 | 2023-07-10 | 2023-07-17 | 2023-07-23 | 2023-07-24 |  | 2023-07-31 | 2023-08-14
112 | 9447 | 65W | L | ground up | L | Av. Inocêncio Seráfico, 4040 | Carapicuíba ll | SP | 2022-05-13 | - | 2023-03-20 | 2023-03-30 | 2023-03-26 | 2023-04-01 | 2023-03-26 | -45 | 2023-05-10 | 2023-05-13 | 2023-05-13 | 2023-05-13 | 2023-05-13 | 2023-06-10 | 2023-06-17 | 2023-06-23 | 2023-06-24 |  | 2023-07-01 | 2023-07-15
108 | 9457 | 7N | R | ground up | P | Av. Igualdade | Aparecida de GO ll | GO | 2022-05-13 | - | 2023-03-15 | 2023-03-25 | 2023-03-21 | 2023-03-27 | 2023-03-21 | -45 | 2023-05-05 | 2023-05-08 | 2023-05-08 | 2023-05-08 | 2023-05-08 | 2023-06-05 | 2023-06-12 | 2023-06-18 | 2023-06-19 |  | 2023-06-26 | 2023-07-10
79 | 9404 | 7N | R | remodel | L | Av. Francisco Monteiro, Nº 061/1055 - Bairro: Vila Fiorentino - Ribeirão Pires - SP - CEP:9406-310 | Rib. Pires | SP | 2021-04-30 | - | - | 2022-08-29 | 2022-08-20 | 2022-08-26 | 2022-08-20 | -45 | 2022-10-04 | 2022-10-07 | 2022-10-07 | 2022-10-07 | 2022-10-07 | 2022-11-04 | 2022-11-11 | 2022-11-17 | 2022-11-18 |  | 2022-11-25 | 2022-12-09
117 | 9453 | 7N | L | ground up | P | Estr. Gen. Canrobert Pereira da Costa , 202 | Realengo | RJ | 2022-04-29 | - | 2023-04-19 | 2023-04-29 | 2023-04-25 | 2023-05-01 | 2023-04-25 | -45 | 2023-06-09 | 2023-06-12 | 2023-06-12 | 2023-06-12 | 2023-06-12 | 2023-07-10 | 2023-07-17 | 2023-07-23 | 2023-07-24 |  | 2023-07-31 | 2023-08-14
107 | 9450 | 7N | R | ground up | P | Av. Princesa do Sul, 900 | Varginha | MG | 2022-04-15 | - | 2023-03-10 | 2023-03-20 | 2023-03-21 | 2023-03-27 | 2023-03-21 | -45 | 2023-05-05 | 2023-05-08 | 2023-05-08 | 2023-05-08 | 2023-05-08 | 2023-06-05 | 2023-06-12 | 2023-06-18 | 2023-06-19 |  | 2023-06-26 | 2023-07-10
85 | 9426 | 7N | L | ground up | L | Av. Waldemar Carlos Pereira, nº 1410 Bairro: Vila Matilde - SP - CEP: 03533-002 | São Paulo vmatilde | SP | 2021-10-15 | 2021-11-25 | 2022-10-30 | 2022-11-09 | 2022-11-05 | 2022-11-11 | 2022-11-05 | -45 | 2022-12-20 | 2022-12-23 | 2022-12-23 | 2022-12-23 | 2022-12-23 | 2023-01-20 | 2023-01-27 | 2023-02-02 | 2023-02-03 |  | 2023-02-10 | 2023-02-24
102 | 9408 | 65W | R | groundup | L | Av. Tenente Marques, nº 2391 - Bairro: Chácara Polvilho - Cajamar - SP - CEP: 07790-500 | Cajamar | SP | 2021-07-22 | - | 2023-03-15 | 2023-03-25 | 2023-03-26 | 2023-04-01 | 2023-03-26 | -45 | 2023-05-10 | 2023-05-13 | 2023-05-13 | 2023-05-13 | 2023-05-13 | 2023-06-10 | 2023-06-17 | 2023-06-23 | 2023-06-24 |  | 2023-07-01 | 2023-07-15
137 | tbd | 65W | R | groundup | P | Av. Dorival Cândido Luz de Oliveira, 4120 | Gravataí | RS | 2022-09-29 | - | 2023-09-04 | 2023-09-14 | 2023-09-10 | 2023-09-16 | 2023-09-10 | -45 | 2023-10-25 | 2023-10-28 | 2023-10-28 | 2023-10-28 | 2023-10-28 | 2023-11-25 | 2023-12-02 | 2023-12-08 | 2023-12-09 |  | 2023-12-16 | 2023-12-30
127 | 9475 | 65W | R | groundup | L | Av. Milão, 58 | Goiânia lV | GO | 2022-08-19 | - | 2023-07-25 | 2023-08-04 | 2023-07-31 | 2023-08-06 | 2023-07-31 | -45 | 2023-09-14 | 2023-09-17 | 2023-09-17 | 2023-09-17 | 2023-09-17 | 2023-10-15 | 2023-10-22 | 2023-10-28 | 2023-10-29 |  | 2023-11-05 | 2023-11-19
Formulas:
NTP (CONSTRUCTION START DATE) = [PERMITS]+66
NTP (CONSTRUCTION START DATE) = [PERMITS]+10+15+34
APPLY FOR NEW BRANCH CNPJ = [SET-UP CREW DATE]-90
IT HARDWARE ORDER DATE = [SET-UP CREW DATE]-84
STORE MANAGER TRAINING = [SET-UP CREW DATE]-90
POGS ATTACH ACTIVE DATE = [EST. STORE OPEN DATE]-45
FIXTURE ORDER DATE = [SET-UP CREW DATE]-45
MDSE INITAL ORDER = [SET-UP CREW DATE]-42
BUYER 6 ORDER DATE = [SET-UP CREW DATE]-42
PHONE LINES = [SET-UP CREW DATE]-42
LP ALARMS & SAFES = [SET-UP CREW DATE]-42
TEMP LABOR CONTRACTED = [SET-UP CREW DATE]-14
MDSE SECOND ORDER = [SET-UP CREW DATE]-7
STORE AUTOZONERS TRAINING (foundations) = [SET-UP CREW DATE]-1
SET-UP CREW DATE = [NTP (CONSTRUCTION START DATE)]+60+1+20
SET-UP CREW DATE = [NTP (CONSTRUCTION START DATE)]+80+1
MDSE FIRST DELIVERY = [SET-UP CREW DATE]+7
SETUP COMPLETION = [SET-UP CREW DATE]+21
EST. STORE OPEN DATE = [SET-UP CREW DATE]+21
PERMITS = [APPROVAL]+490
Note on L51: Santos, Jaine: Contrato assinado 29/07/2020 Locação e Aquisição. Escritura efetuada em 28/08/2020

## calendar (hidden)
DaybyPeriod | DATA | DIA SEMANA | SEMANA FY | PERÍODO | WK by P | P&WK | FY | FY_P
1 | 2011-09-04 | 1 | WK1 | P1 | W1 | P1W1 | FY12 | FY12P1
2 | 2011-09-05 | 2 | WK1 | P1 | W1 | P1W1 | FY12 | FY12P1
3 | 2011-09-06 | 3 | WK1 | P1 | W1 | P1W1 | FY12 | FY12P1
4 | 2011-09-07 | 4 | WK1 | P1 | W1 | P1W1 | FY12 | FY12P1
5 | 2011-09-08 | 5 | WK1 | P1 | W1 | P1W1 | FY12 | FY12P1
6 | 2011-09-09 | 6 | WK1 | P1 | W1 | P1W1 | FY12 | FY12P1
7 | 2011-09-10 | 7 | WK1 | P1 | W1 | P1W1 | FY12 | FY12P1
8 | 2011-09-11 | 1 | WK2 | P1 | W2 | P1W2 | FY12 | FY12P1
9 | 2011-09-12 | 2 | WK2 | P1 | W2 | P1W2 | FY12 | FY12P1
10 | 2011-09-13 | 3 | WK2 | P1 | W2 | P1W2 | FY12 | FY12P1
11 | 2011-09-14 | 4 | WK2 | P1 | W2 | P1W2 | FY12 | FY12P1
12 | 2011-09-15 | 5 | WK2 | P1 | W2 | P1W2 | FY12 | FY12P1
13 | 2011-09-16 | 6 | WK2 | P1 | W2 | P1W2 | FY12 | FY12P1
14 | 2011-09-17 | 7 | WK2 | P1 | W2 | P1W2 | FY12 | FY12P1
15 | 2011-09-18 | 1 | WK3 | P1 | W3 | P1W3 | FY12 | FY12P1
16 | 2011-09-19 | 2 | WK3 | P1 | W3 | P1W3 | FY12 | FY12P1
17 | 2011-09-20 | 3 | WK3 | P1 | W3 | P1W3 | FY12 | FY12P1
18 | 2011-09-21 | 4 | WK3 | P1 | W3 | P1W3 | FY12 | FY12P1
19 | 2011-09-22 | 5 | WK3 | P1 | W3 | P1W3 | FY12 | FY12P1
20 | 2011-09-23 | 6 | WK3 | P1 | W3 | P1W3 | FY12 | FY12P1
21 | 2011-09-24 | 7 | WK3 | P1 | W3 | P1W3 | FY12 | FY12P1
22 | 2011-09-25 | 1 | WK4 | P1 | W4 | P1W4 | FY12 | FY12P1
23 | 2011-09-26 | 2 | WK4 | P1 | W4 | P1W4 | FY12 | FY12P1
24 | 2011-09-27 | 3 | WK4 | P1 | W4 | P1W4 | FY12 | FY12P1
25 | 2011-09-28 | 4 | WK4 | P1 | W4 | P1W4 | FY12 | FY12P1
26 | 2011-09-29 | 5 | WK4 | P1 | W4 | P1W4 | FY12 | FY12P1
27 | 2011-09-30 | 6 | WK4 | P1 | W4 | P1W4 | FY12 | FY12P1
28 | 2011-10-01 | 7 | WK4 | P1 | W4 | P1W4 | FY12 | FY12P1
1 | 2011-10-02 | 1 | WK5 | P2 | W1 | P2W1 | FY12 | FY12P2
2 | 2011-10-03 | 2 | WK5 | P2 | W1 | P2W1 | FY12 | FY12P2
3 | 2011-10-04 | 3 | WK5 | P2 | W1 | P2W1 | FY12 | FY12P2
4 | 2011-10-05 | 4 | WK5 | P2 | W1 | P2W1 | FY12 | FY12P2
5 | 2011-10-06 | 5 | WK5 | P2 | W1 | P2W1 | FY12 | FY12P2
6 | 2011-10-07 | 6 | WK5 | P2 | W1 | P2W1 | FY12 | FY12P2
7 | 2011-10-08 | 7 | WK5 | P2 | W1 | P2W1 | FY12 | FY12P2
8 | 2011-10-09 | 1 | WK6 | P2 | W2 | P2W2 | FY12 | FY12P2
9 | 2011-10-10 | 2 | WK6 | P2 | W2 | P2W2 | FY12 | FY12P2
10 | 2011-10-11 | 3 | WK6 | P2 | W2 | P2W2 | FY12 | FY12P2
11 | 2011-10-12 | 4 | WK6 | P2 | W2 | P2W2 | FY12 | FY12P2
12 | 2011-10-13 | 5 | WK6 | P2 | W2 | P2W2 | FY12 | FY12P2
13 | 2011-10-14 | 6 | WK6 | P2 | W2 | P2W2 | FY12 | FY12P2
14 | 2011-10-15 | 7 | WK6 | P2 | W2 | P2W2 | FY12 | FY12P2
15 | 2011-10-16 | 1 | WK7 | P2 | W3 | P2W3 | FY12 | FY12P2
16 | 2011-10-17 | 2 | WK7 | P2 | W3 | P2W3 | FY12 | FY12P2
17 | 2011-10-18 | 3 | WK7 | P2 | W3 | P2W3 | FY12 | FY12P2
18 | 2011-10-19 | 4 | WK7 | P2 | W3 | P2W3 | FY12 | FY12P2
19 | 2011-10-20 | 5 | WK7 | P2 | W3 | P2W3 | FY12 | FY12P2
20 | 2011-10-21 | 6 | WK7 | P2 | W3 | P2W3 | FY12 | FY12P2
21 | 2011-10-22 | 7 | WK7 | P2 | W3 | P2W3 | FY12 | FY12P2
22 | 2011-10-23 | 1 | WK8 | P2 | W4 | P2W4 | FY12 | FY12P2
23 | 2011-10-24 | 2 | WK8 | P2 | W4 | P2W4 | FY12 | FY12P2
24 | 2011-10-25 | 3 | WK8 | P2 | W4 | P2W4 | FY12 | FY12P2
25 | 2011-10-26 | 4 | WK8 | P2 | W4 | P2W4 | FY12 | FY12P2
26 | 2011-10-27 | 5 | WK8 | P2 | W4 | P2W4 | FY12 | FY12P2
27 | 2011-10-28 | 6 | WK8 | P2 | W4 | P2W4 | FY12 | FY12P2
28 | 2011-10-29 | 7 | WK8 | P2 | W4 | P2W4 | FY12 | FY12P2
1 | 2011-10-30 | 1 | WK9 | P3 | W1 | P3W1 | FY12 | FY12P3
2 | 2011-10-31 | 2 | WK9 | P3 | W1 | P3W1 | FY12 | FY12P3
3 | 2011-11-01 | 3 | WK9 | P3 | W1 | P3W1 | FY12 | FY12P3
4 | 2011-11-02 | 4 | WK9 | P3 | W1 | P3W1 | FY12 | FY12P3
5 | 2011-11-03 | 5 | WK9 | P3 | W1 | P3W1 | FY12 | FY12P3
6 | 2011-11-04 | 6 | WK9 | P3 | W1 | P3W1 | FY12 | FY12P3
7 | 2011-11-05 | 7 | WK9 | P3 | W1 | P3W1 | FY12 | FY12P3
8 | 2011-11-06 | 1 | WK10 | P3 | W2 | P3W2 | FY12 | FY12P3
9 | 2011-11-07 | 2 | WK10 | P3 | W2 | P3W2 | FY12 | FY12P3
10 | 2011-11-08 | 3 | WK10 | P3 | W2 | P3W2 | FY12 | FY12P3
11 | 2011-11-09 | 4 | WK10 | P3 | W2 | P3W2 | FY12 | FY12P3
12 | 2011-11-10 | 5 | WK10 | P3 | W2 | P3W2 | FY12 | FY12P3
13 | 2011-11-11 | 6 | WK10 | P3 | W2 | P3W2 | FY12 | FY12P3
14 | 2011-11-12 | 7 | WK10 | P3 | W2 | P3W2 | FY12 | FY12P3
15 | 2011-11-13 | 1 | WK11 | P3 | W3 | P3W3 | FY12 | FY12P3
16 | 2011-11-14 | 2 | WK11 | P3 | W3 | P3W3 | FY12 | FY12P3
17 | 2011-11-15 | 3 | WK11 | P3 | W3 | P3W3 | FY12 | FY12P3
18 | 2011-11-16 | 4 | WK11 | P3 | W3 | P3W3 | FY12 | FY12P3
19 | 2011-11-17 | 5 | WK11 | P3 | W3 | P3W3 | FY12 | FY12P3
20 | 2011-11-18 | 6 | WK11 | P3 | W3 | P3W3 | FY12 | FY12P3
21 | 2011-11-19 | 7 | WK11 | P3 | W3 | P3W3 | FY12 | FY12P3
22 | 2011-11-20 | 1 | WK12 | P3 | W4 | P3W4 | FY12 | FY12P3
23 | 2011-11-21 | 2 | WK12 | P3 | W4 | P3W4 | FY12 | FY12P3
24 | 2011-11-22 | 3 | WK12 | P3 | W4 | P3W4 | FY12 | FY12P3
25 | 2011-11-23 | 4 | WK12 | P3 | W4 | P3W4 | FY12 | FY12P3
26 | 2011-11-24 | 5 | WK12 | P3 | W4 | P3W4 | FY12 | FY12P3
27 | 2011-11-25 | 6 | WK12 | P3 | W4 | P3W4 | FY12 | FY12P3
28 | 2011-11-26 | 7 | WK12 | P3 | W4 | P3W4 | FY12 | FY12P3
1 | 2011-11-27 | 1 | WK13 | P4 | W1 | P4W1 | FY12 | FY12P4
2 | 2011-11-28 | 2 | WK13 | P4 | W1 | P4W1 | FY12 | FY12P4
3 | 2011-11-29 | 3 | WK13 | P4 | W1 | P4W1 | FY12 | FY12P4
4 | 2011-11-30 | 4 | WK13 | P4 | W1 | P4W1 | FY12 | FY12P4
5 | 2011-12-01 | 5 | WK13 | P4 | W1 | P4W1 | FY12 | FY12P4
6 | 2011-12-02 | 6 | WK13 | P4 | W1 | P4W1 | FY12 | FY12P4
7 | 2011-12-03 | 7 | WK13 | P4 | W1 | P4W1 | FY12 | FY12P4
8 | 2011-12-04 | 1 | WK14 | P4 | W2 | P4W2 | FY12 | FY12P4
9 | 2011-12-05 | 2 | WK14 | P4 | W2 | P4W2 | FY12 | FY12P4
10 | 2011-12-06 | 3 | WK14 | P4 | W2 | P4W2 | FY12 | FY12P4
11 | 2011-12-07 | 4 | WK14 | P4 | W2 | P4W2 | FY12 | FY12P4
12 | 2011-12-08 | 5 | WK14 | P4 | W2 | P4W2 | FY12 | FY12P4
13 | 2011-12-09 | 6 | WK14 | P4 | W2 | P4W2 | FY12 | FY12P4
14 | 2011-12-10 | 7 | WK14 | P4 | W2 | P4W2 | FY12 | FY12P4
15 | 2011-12-11 | 1 | WK15 | P4 | W3 | P4W3 | FY12 | FY12P4
16 | 2011-12-12 | 2 | WK15 | P4 | W3 | P4W3 | FY12 | FY12P4
17 | 2011-12-13 | 3 | WK15 | P4 | W3 | P4W3 | FY12 | FY12P4
18 | 2011-12-14 | 4 | WK15 | P4 | W3 | P4W3 | FY12 | FY12P4
19 | 2011-12-15 | 5 | WK15 | P4 | W3 | P4W3 | FY12 | FY12P4
20 | 2011-12-16 | 6 | WK15 | P4 | W3 | P4W3 | FY12 | FY12P4
21 | 2011-12-17 | 7 | WK15 | P4 | W3 | P4W3 | FY12 | FY12P4
22 | 2011-12-18 | 1 | WK16 | P4 | W4 | P4W4 | FY12 | FY12P4
23 | 2011-12-19 | 2 | WK16 | P4 | W4 | P4W4 | FY12 | FY12P4
24 | 2011-12-20 | 3 | WK16 | P4 | W4 | P4W4 | FY12 | FY12P4
25 | 2011-12-21 | 4 | WK16 | P4 | W4 | P4W4 | FY12 | FY12P4
26 | 2011-12-22 | 5 | WK16 | P4 | W4 | P4W4 | FY12 | FY12P4
27 | 2011-12-23 | 6 | WK16 | P4 | W4 | P4W4 | FY12 | FY12P4
28 | 2011-12-24 | 7 | WK16 | P4 | W4 | P4W4 | FY12 | FY12P4
1 | 2011-12-25 | 1 | WK17 | P5 | W1 | P5W1 | FY12 | FY12P5
2 | 2011-12-26 | 2 | WK17 | P5 | W1 | P5W1 | FY12 | FY12P5
3 | 2011-12-27 | 3 | WK17 | P5 | W1 | P5W1 | FY12 | FY12P5
4 | 2011-12-28 | 4 | WK17 | P5 | W1 | P5W1 | FY12 | FY12P5
5 | 2011-12-29 | 5 | WK17 | P5 | W1 | P5W1 | FY12 | FY12P5
6 | 2011-12-30 | 6 | WK17 | P5 | W1 | P5W1 | FY12 | FY12P5
7 | 2011-12-31 | 7 | WK17 | P5 | W1 | P5W1 | FY12 | FY12P5
8 | 2012-01-01 | 1 | WK18 | P5 | W2 | P5W2 | FY12 | FY12P5
9 | 2012-01-02 | 2 | WK18 | P5 | W2 | P5W2 | FY12 | FY12P5
10 | 2012-01-03 | 3 | WK18 | P5 | W2 | P5W2 | FY12 | FY12P5
11 | 2012-01-04 | 4 | WK18 | P5 | W2 | P5W2 | FY12 | FY12P5
12 | 2012-01-05 | 5 | WK18 | P5 | W2 | P5W2 | FY12 | FY12P5
13 | 2012-01-06 | 6 | WK18 | P5 | W2 | P5W2 | FY12 | FY12P5
14 | 2012-01-07 | 7 | WK18 | P5 | W2 | P5W2 | FY12 | FY12P5
15 | 2012-01-08 | 1 | WK19 | P5 | W3 | P5W3 | FY12 | FY12P5
16 | 2012-01-09 | 2 | WK19 | P5 | W3 | P5W3 | FY12 | FY12P5
17 | 2012-01-10 | 3 | WK19 | P5 | W3 | P5W3 | FY12 | FY12P5
18 | 2012-01-11 | 4 | WK19 | P5 | W3 | P5W3 | FY12 | FY12P5
19 | 2012-01-12 | 5 | WK19 | P5 | W3 | P5W3 | FY12 | FY12P5
20 | 2012-01-13 | 6 | WK19 | P5 | W3 | P5W3 | FY12 | FY12P5
21 | 2012-01-14 | 7 | WK19 | P5 | W3 | P5W3 | FY12 | FY12P5
22 | 2012-01-15 | 1 | WK20 | P5 | W4 | P5W4 | FY12 | FY12P5
23 | 2012-01-16 | 2 | WK20 | P5 | W4 | P5W4 | FY12 | FY12P5
24 | 2012-01-17 | 3 | WK20 | P5 | W4 | P5W4 | FY12 | FY12P5
25 | 2012-01-18 | 4 | WK20 | P5 | W4 | P5W4 | FY12 | FY12P5
26 | 2012-01-19 | 5 | WK20 | P5 | W4 | P5W4 | FY12 | FY12P5
27 | 2012-01-20 | 6 | WK20 | P5 | W4 | P5W4 | FY12 | FY12P5
28 | 2012-01-21 | 7 | WK20 | P5 | W4 | P5W4 | FY12 | FY12P5
1 | 2012-01-22 | 1 | WK21 | P6 | W1 | P6W1 | FY12 | FY12P6
2 | 2012-01-23 | 2 | WK21 | P6 | W1 | P6W1 | FY12 | FY12P6
3 | 2012-01-24 | 3 | WK21 | P6 | W1 | P6W1 | FY12 | FY12P6
4 | 2012-01-25 | 4 | WK21 | P6 | W1 | P6W1 | FY12 | FY12P6
5 | 2012-01-26 | 5 | WK21 | P6 | W1 | P6W1 | FY12 | FY12P6
6 | 2012-01-27 | 6 | WK21 | P6 | W1 | P6W1 | FY12 | FY12P6
7 | 2012-01-28 | 7 | WK21 | P6 | W1 | P6W1 | FY12 | FY12P6
8 | 2012-01-29 | 1 | WK22 | P6 | W2 | P6W2 | FY12 | FY12P6
9 | 2012-01-30 | 2 | WK22 | P6 | W2 | P6W2 | FY12 | FY12P6
10 | 2012-01-31 | 3 | WK22 | P6 | W2 | P6W2 | FY12 | FY12P6
11 | 2012-02-01 | 4 | WK22 | P6 | W2 | P6W2 | FY12 | FY12P6
12 | 2012-02-02 | 5 | WK22 | P6 | W2 | P6W2 | FY12 | FY12P6
13 | 2012-02-03 | 6 | WK22 | P6 | W2 | P6W2 | FY12 | FY12P6
14 | 2012-02-04 | 7 | WK22 | P6 | W2 | P6W2 | FY12 | FY12P6
15 | 2012-02-05 | 1 | WK23 | P6 | W3 | P6W3 | FY12 | FY12P6
16 | 2012-02-06 | 2 | WK23 | P6 | W3 | P6W3 | FY12 | FY12P6
17 | 2012-02-07 | 3 | WK23 | P6 | W3 | P6W3 | FY12 | FY12P6
18 | 2012-02-08 | 4 | WK23 | P6 | W3 | P6W3 | FY12 | FY12P6
19 | 2012-02-09 | 5 | WK23 | P6 | W3 | P6W3 | FY12 | FY12P6
20 | 2012-02-10 | 6 | WK23 | P6 | W3 | P6W3 | FY12 | FY12P6
21 | 2012-02-11 | 7 | WK23 | P6 | W3 | P6W3 | FY12 | FY12P6
22 | 2012-02-12 | 1 | WK24 | P6 | W4 | P6W4 | FY12 | FY12P6
23 | 2012-02-13 | 2 | WK24 | P6 | W4 | P6W4 | FY12 | FY12P6
24 | 2012-02-14 | 3 | WK24 | P6 | W4 | P6W4 | FY12 | FY12P6
25 | 2012-02-15 | 4 | WK24 | P6 | W4 | P6W4 | FY12 | FY12P6
26 | 2012-02-16 | 5 | WK24 | P6 | W4 | P6W4 | FY12 | FY12P6
27 | 2012-02-17 | 6 | WK24 | P6 | W4 | P6W4 | FY12 | FY12P6
28 | 2012-02-18 | 7 | WK24 | P6 | W4 | P6W4 | FY12 | FY12P6
1 | 2012-02-19 | 1 | WK25 | P7 | W1 | P7W1 | FY12 | FY12P7
2 | 2012-02-20 | 2 | WK25 | P7 | W1 | P7W1 | FY12 | FY12P7
3 | 2012-02-21 | 3 | WK25 | P7 | W1 | P7W1 | FY12 | FY12P7
4 | 2012-02-22 | 4 | WK25 | P7 | W1 | P7W1 | FY12 | FY12P7
5 | 2012-02-23 | 5 | WK25 | P7 | W1 | P7W1 | FY12 | FY12P7
6 | 2012-02-24 | 6 | WK25 | P7 | W1 | P7W1 | FY12 | FY12P7
7 | 2012-02-25 | 7 | WK25 | P7 | W1 | P7W1 | FY12 | FY12P7
8 | 2012-02-26 | 1 | WK26 | P7 | W2 | P7W2 | FY12 | FY12P7
9 | 2012-02-27 | 2 | WK26 | P7 | W2 | P7W2 | FY12 | FY12P7
10 | 2012-02-28 | 3 | WK26 | P7 | W2 | P7W2 | FY12 | FY12P7
11 | 2012-02-29 | 4 | WK26 | P7 | W2 | P7W2 | FY12 | FY12P7
12 | 2012-03-01 | 5 | WK26 | P7 | W2 | P7W2 | FY12 | FY12P7
13 | 2012-03-02 | 6 | WK26 | P7 | W2 | P7W2 | FY12 | FY12P7
14 | 2012-03-03 | 7 | WK26 | P7 | W2 | P7W2 | FY12 | FY12P7
15 | 2012-03-04 | 1 | WK27 | P7 | W3 | P7W3 | FY12 | FY12P7
16 | 2012-03-05 | 2 | WK27 | P7 | W3 | P7W3 | FY12 | FY12P7
17 | 2012-03-06 | 3 | WK27 | P7 | W3 | P7W3 | FY12 | FY12P7
18 | 2012-03-07 | 4 | WK27 | P7 | W3 | P7W3 | FY12 | FY12P7
19 | 2012-03-08 | 5 | WK27 | P7 | W3 | P7W3 | FY12 | FY12P7
20 | 2012-03-09 | 6 | WK27 | P7 | W3 | P7W3 | FY12 | FY12P7
21 | 2012-03-10 | 7 | WK27 | P7 | W3 | P7W3 | FY12 | FY12P7
22 | 2012-03-11 | 1 | WK28 | P7 | W4 | P7W4 | FY12 | FY12P7
23 | 2012-03-12 | 2 | WK28 | P7 | W4 | P7W4 | FY12 | FY12P7
24 | 2012-03-13 | 3 | WK28 | P7 | W4 | P7W4 | FY12 | FY12P7
25 | 2012-03-14 | 4 | WK28 | P7 | W4 | P7W4 | FY12 | FY12P7
26 | 2012-03-15 | 5 | WK28 | P7 | W4 | P7W4 | FY12 | FY12P7
27 | 2012-03-16 | 6 | WK28 | P7 | W4 | P7W4 | FY12 | FY12P7
28 | 2012-03-17 | 7 | WK28 | P7 | W4 | P7W4 | FY12 | FY12P7
1 | 2012-03-18 | 1 | WK29 | P8 | W1 | P8W1 | FY12 | FY12P8
2 | 2012-03-19 | 2 | WK29 | P8 | W1 | P8W1 | FY12 | FY12P8
3 | 2012-03-20 | 3 | WK29 | P8 | W1 | P8W1 | FY12 | FY12P8
4 | 2012-03-21 | 4 | WK29 | P8 | W1 | P8W1 | FY12 | FY12P8
5 | 2012-03-22 | 5 | WK29 | P8 | W1 | P8W1 | FY12 | FY12P8
6 | 2012-03-23 | 6 | WK29 | P8 | W1 | P8W1 | FY12 | FY12P8
7 | 2012-03-24 | 7 | WK29 | P8 | W1 | P8W1 | FY12 | FY12P8
8 | 2012-03-25 | 1 | WK30 | P8 | W2 | P8W2 | FY12 | FY12P8
9 | 2012-03-26 | 2 | WK30 | P8 | W2 | P8W2 | FY12 | FY12P8
10 | 2012-03-27 | 3 | WK30 | P8 | W2 | P8W2 | FY12 | FY12P8
11 | 2012-03-28 | 4 | WK30 | P8 | W2 | P8W2 | FY12 | FY12P8
12 | 2012-03-29 | 5 | WK30 | P8 | W2 | P8W2 | FY12 | FY12P8
13 | 2012-03-30 | 6 | WK30 | P8 | W2 | P8W2 | FY12 | FY12P8
14 | 2012-03-31 | 7 | WK30 | P8 | W2 | P8W2 | FY12 | FY12P8
15 | 2012-04-01 | 1 | WK31 | P8 | W3 | P8W3 | FY12 | FY12P8
16 | 2012-04-02 | 2 | WK31 | P8 | W3 | P8W3 | FY12 | FY12P8
17 | 2012-04-03 | 3 | WK31 | P8 | W3 | P8W3 | FY12 | FY12P8
18 | 2012-04-04 | 4 | WK31 | P8 | W3 | P8W3 | FY12 | FY12P8
19 | 2012-04-05 | 5 | WK31 | P8 | W3 | P8W3 | FY12 | FY12P8
20 | 2012-04-06 | 6 | WK31 | P8 | W3 | P8W3 | FY12 | FY12P8
21 | 2012-04-07 | 7 | WK31 | P8 | W3 | P8W3 | FY12 | FY12P8
22 | 2012-04-08 | 1 | WK32 | P8 | W4 | P8W4 | FY12 | FY12P8
23 | 2012-04-09 | 2 | WK32 | P8 | W4 | P8W4 | FY12 | FY12P8
24 | 2012-04-10 | 3 | WK32 | P8 | W4 | P8W4 | FY12 | FY12P8
25 | 2012-04-11 | 4 | WK32 | P8 | W4 | P8W4 | FY12 | FY12P8
26 | 2012-04-12 | 5 | WK32 | P8 | W4 | P8W4 | FY12 | FY12P8
27 | 2012-04-13 | 6 | WK32 | P8 | W4 | P8W4 | FY12 | FY12P8
28 | 2012-04-14 | 7 | WK32 | P8 | W4 | P8W4 | FY12 | FY12P8
1 | 2012-04-15 | 1 | WK33 | P9 | W1 | P9W1 | FY12 | FY12P9
2 | 2012-04-16 | 2 | WK33 | P9 | W1 | P9W1 | FY12 | FY12P9
3 | 2012-04-17 | 3 | WK33 | P9 | W1 | P9W1 | FY12 | FY12P9
4 | 2012-04-18 | 4 | WK33 | P9 | W1 | P9W1 | FY12 | FY12P9
5 | 2012-04-19 | 5 | WK33 | P9 | W1 | P9W1 | FY12 | FY12P9
6 | 2012-04-20 | 6 | WK33 | P9 | W1 | P9W1 | FY12 | FY12P9
7 | 2012-04-21 | 7 | WK33 | P9 | W1 | P9W1 | FY12 | FY12P9
8 | 2012-04-22 | 1 | WK34 | P9 | W2 | P9W2 | FY12 | FY12P9
9 | 2012-04-23 | 2 | WK34 | P9 | W2 | P9W2 | FY12 | FY12P9
10 | 2012-04-24 | 3 | WK34 | P9 | W2 | P9W2 | FY12 | FY12P9
11 | 2012-04-25 | 4 | WK34 | P9 | W2 | P9W2 | FY12 | FY12P9
12 | 2012-04-26 | 5 | WK34 | P9 | W2 | P9W2 | FY12 | FY12P9
13 | 2012-04-27 | 6 | WK34 | P9 | W2 | P9W2 | FY12 | FY12P9
14 | 2012-04-28 | 7 | WK34 | P9 | W2 | P9W2 | FY12 | FY12P9
15 | 2012-04-29 | 1 | WK35 | P9 | W3 | P9W3 | FY12 | FY12P9
16 | 2012-04-30 | 2 | WK35 | P9 | W3 | P9W3 | FY12 | FY12P9
17 | 2012-05-01 | 3 | WK35 | P9 | W3 | P9W3 | FY12 | FY12P9
18 | 2012-05-02 | 4 | WK35 | P9 | W3 | P9W3 | FY12 | FY12P9
19 | 2012-05-03 | 5 | WK35 | P9 | W3 | P9W3 | FY12 | FY12P9
20 | 2012-05-04 | 6 | WK35 | P9 | W3 | P9W3 | FY12 | FY12P9
21 | 2012-05-05 | 7 | WK35 | P9 | W3 | P9W3 | FY12 | FY12P9
22 | 2012-05-06 | 1 | WK36 | P9 | W4 | P9W4 | FY12 | FY12P9
23 | 2012-05-07 | 2 | WK36 | P9 | W4 | P9W4 | FY12 | FY12P9
24 | 2012-05-08 | 3 | WK36 | P9 | W4 | P9W4 | FY12 | FY12P9
25 | 2012-05-09 | 4 | WK36 | P9 | W4 | P9W4 | FY12 | FY12P9
26 | 2012-05-10 | 5 | WK36 | P9 | W4 | P9W4 | FY12 | FY12P9
27 | 2012-05-11 | 6 | WK36 | P9 | W4 | P9W4 | FY12 | FY12P9
28 | 2012-05-12 | 7 | WK36 | P9 | W4 | P9W4 | FY12 | FY12P9
1 | 2012-05-13 | 1 | WK37 | P10 | W1 | P10W1 | FY12 | FY12P10
2 | 2012-05-14 | 2 | WK37 | P10 | W1 | P10W1 | FY12 | FY12P10
3 | 2012-05-15 | 3 | WK37 | P10 | W1 | P10W1 | FY12 | FY12P10
4 | 2012-05-16 | 4 | WK37 | P10 | W1 | P10W1 | FY12 | FY12P10
5 | 2012-05-17 | 5 | WK37 | P10 | W1 | P10W1 | FY12 | FY12P10
6 | 2012-05-18 | 6 | WK37 | P10 | W1 | P10W1 | FY12 | FY12P10
7 | 2012-05-19 | 7 | WK37 | P10 | W1 | P10W1 | FY12 | FY12P10
8 | 2012-05-20 | 1 | WK38 | P10 | W2 | P10W2 | FY12 | FY12P10
9 | 2012-05-21 | 2 | WK38 | P10 | W2 | P10W2 | FY12 | FY12P10
10 | 2012-05-22 | 3 | WK38 | P10 | W2 | P10W2 | FY12 | FY12P10
11 | 2012-05-23 | 4 | WK38 | P10 | W2 | P10W2 | FY12 | FY12P10
12 | 2012-05-24 | 5 | WK38 | P10 | W2 | P10W2 | FY12 | FY12P10
13 | 2012-05-25 | 6 | WK38 | P10 | W2 | P10W2 | FY12 | FY12P10
14 | 2012-05-26 | 7 | WK38 | P10 | W2 | P10W2 | FY12 | FY12P10
15 | 2012-05-27 | 1 | WK39 | P10 | W3 | P10W3 | FY12 | FY12P10
16 | 2012-05-28 | 2 | WK39 | P10 | W3 | P10W3 | FY12 | FY12P10
17 | 2012-05-29 | 3 | WK39 | P10 | W3 | P10W3 | FY12 | FY12P10
18 | 2012-05-30 | 4 | WK39 | P10 | W3 | P10W3 | FY12 | FY12P10
19 | 2012-05-31 | 5 | WK39 | P10 | W3 | P10W3 | FY12 | FY12P10
20 | 2012-06-01 | 6 | WK39 | P10 | W3 | P10W3 | FY12 | FY12P10
21 | 2012-06-02 | 7 | WK39 | P10 | W3 | P10W3 | FY12 | FY12P10
22 | 2012-06-03 | 1 | WK40 | P10 | W4 | P10W4 | FY12 | FY12P10
23 | 2012-06-04 | 2 | WK40 | P10 | W4 | P10W4 | FY12 | FY12P10
24 | 2012-06-05 | 3 | WK40 | P10 | W4 | P10W4 | FY12 | FY12P10
25 | 2012-06-06 | 4 | WK40 | P10 | W4 | P10W4 | FY12 | FY12P10
26 | 2012-06-07 | 5 | WK40 | P10 | W4 | P10W4 | FY12 | FY12P10
27 | 2012-06-08 | 6 | WK40 | P10 | W4 | P10W4 | FY12 | FY12P10
28 | 2012-06-09 | 7 | WK40 | P10 | W4 | P10W4 | FY12 | FY12P10
1 | 2012-06-10 | 1 | WK41 | P11 | W1 | P11W1 | FY12 | FY12P11
2 | 2012-06-11 | 2 | WK41 | P11 | W1 | P11W1 | FY12 | FY12P11
3 | 2012-06-12 | 3 | WK41 | P11 | W1 | P11W1 | FY12 | FY12P11
4 | 2012-06-13 | 4 | WK41 | P11 | W1 | P11W1 | FY12 | FY12P11
5 | 2012-06-14 | 5 | WK41 | P11 | W1 | P11W1 | FY12 | FY12P11
6 | 2012-06-15 | 6 | WK41 | P11 | W1 | P11W1 | FY12 | FY12P11
7 | 2012-06-16 | 7 | WK41 | P11 | W1 | P11W1 | FY12 | FY12P11
8 | 2012-06-17 | 1 | WK42 | P11 | W2 | P11W2 | FY12 | FY12P11
9 | 2012-06-18 | 2 | WK42 | P11 | W2 | P11W2 | FY12 | FY12P11
10 | 2012-06-19 | 3 | WK42 | P11 | W2 | P11W2 | FY12 | FY12P11
11 | 2012-06-20 | 4 | WK42 | P11 | W2 | P11W2 | FY12 | FY12P11
12 | 2012-06-21 | 5 | WK42 | P11 | W2 | P11W2 | FY12 | FY12P11
13 | 2012-06-22 | 6 | WK42 | P11 | W2 | P11W2 | FY12 | FY12P11
14 | 2012-06-23 | 7 | WK42 | P11 | W2 | P11W2 | FY12 | FY12P11
15 | 2012-06-24 | 1 | WK43 | P11 | W3 | P11W3 | FY12 | FY12P11
16 | 2012-06-25 | 2 | WK43 | P11 | W3 | P11W3 | FY12 | FY12P11
17 | 2012-06-26 | 3 | WK43 | P11 | W3 | P11W3 | FY12 | FY12P11
18 | 2012-06-27 | 4 | WK43 | P11 | W3 | P11W3 | FY12 | FY12P11
19 | 2012-06-28 | 5 | WK43 | P11 | W3 | P11W3 | FY12 | FY12P11
20 | 2012-06-29 | 6 | WK43 | P11 | W3 | P11W3 | FY12 | FY12P11
21 | 2012-06-30 | 7 | WK43 | P11 | W3 | P11W3 | FY12 | FY12P11
22 | 2012-07-01 | 1 | WK44 | P11 | W4 | P11W4 | FY12 | FY12P11
23 | 2012-07-02 | 2 | WK44 | P11 | W4 | P11W4 | FY12 | FY12P11
24 | 2012-07-03 | 3 | WK44 | P11 | W4 | P11W4 | FY12 | FY12P11
25 | 2012-07-04 | 4 | WK44 | P11 | W4 | P11W4 | FY12 | FY12P11
26 | 2012-07-05 | 5 | WK44 | P11 | W4 | P11W4 | FY12 | FY12P11
27 | 2012-07-06 | 6 | WK44 | P11 | W4 | P11W4 | FY12 | FY12P11
28 | 2012-07-07 | 7 | WK44 | P11 | W4 | P11W4 | FY12 | FY12P11
1 | 2012-07-08 | 1 | WK45 | P12 | W1 | P12W1 | FY12 | FY12P12
2 | 2012-07-09 | 2 | WK45 | P12 | W1 | P12W1 | FY12 | FY12P12
3 | 2012-07-10 | 3 | WK45 | P12 | W1 | P12W1 | FY12 | FY12P12
4 | 2012-07-11 | 4 | WK45 | P12 | W1 | P12W1 | FY12 | FY12P12
5 | 2012-07-12 | 5 | WK45 | P12 | W1 | P12W1 | FY12 | FY12P12
6 | 2012-07-13 | 6 | WK45 | P12 | W1 | P12W1 | FY12 | FY12P12
7 | 2012-07-14 | 7 | WK45 | P12 | W1 | P12W1 | FY12 | FY12P12
8 | 2012-07-15 | 1 | WK46 | P12 | W2 | P12W2 | FY12 | FY12P12
9 | 2012-07-16 | 2 | WK46 | P12 | W2 | P12W2 | FY12 | FY12P12
10 | 2012-07-17 | 3 | WK46 | P12 | W2 | P12W2 | FY12 | FY12P12
11 | 2012-07-18 | 4 | WK46 | P12 | W2 | P12W2 | FY12 | FY12P12
12 | 2012-07-19 | 5 | WK46 | P12 | W2 | P12W2 | FY12 | FY12P12
13 | 2012-07-20 | 6 | WK46 | P12 | W2 | P12W2 | FY12 | FY12P12
14 | 2012-07-21 | 7 | WK46 | P12 | W2 | P12W2 | FY12 | FY12P12
15 | 2012-07-22 | 1 | WK47 | P12 | W3 | P12W3 | FY12 | FY12P12
16 | 2012-07-23 | 2 | WK47 | P12 | W3 | P12W3 | FY12 | FY12P12
17 | 2012-07-24 | 3 | WK47 | P12 | W3 | P12W3 | FY12 | FY12P12
18 | 2012-07-25 | 4 | WK47 | P12 | W3 | P12W3 | FY12 | FY12P12
19 | 2012-07-26 | 5 | WK47 | P12 | W3 | P12W3 | FY12 | FY12P12
20 | 2012-07-27 | 6 | WK47 | P12 | W3 | P12W3 | FY12 | FY12P12
21 | 2012-07-28 | 7 | WK47 | P12 | W3 | P12W3 | FY12 | FY12P12
22 | 2012-07-29 | 1 | WK48 | P12 | W4 | P12W4 | FY12 | FY12P12
23 | 2012-07-30 | 2 | WK48 | P12 | W4 | P12W4 | FY12 | FY12P12
24 | 2012-07-31 | 3 | WK48 | P12 | W4 | P12W4 | FY12 | FY12P12
25 | 2012-08-01 | 4 | WK48 | P12 | W4 | P12W4 | FY12 | FY12P12
26 | 2012-08-02 | 5 | WK48 | P12 | W4 | P12W4 | FY12 | FY12P12
27 | 2012-08-03 | 6 | WK48 | P12 | W4 | P12W4 | FY12 | FY12P12
28 | 2012-08-04 | 7 | WK48 | P12 | W4 | P12W4 | FY12 | FY12P12
1 | 2012-08-05 | 1 | WK49 | P13 | W1 | P13W1 | FY12 | FY12P13
2 | 2012-08-06 | 2 | WK49 | P13 | W1 | P13W1 | FY12 | FY12P13
3 | 2012-08-07 | 3 | WK49 | P13 | W1 | P13W1 | FY12 | FY12P13
4 | 2012-08-08 | 4 | WK49 | P13 | W1 | P13W1 | FY12 | FY12P13
5 | 2012-08-09 | 5 | WK49 | P13 | W1 | P13W1 | FY12 | FY12P13
6 | 2012-08-10 | 6 | WK49 | P13 | W1 | P13W1 | FY12 | FY12P13
7 | 2012-08-11 | 7 | WK49 | P13 | W1 | P13W1 | FY12 | FY12P13
8 | 2012-08-12 | 1 | WK50 | P13 | W2 | P13W2 | FY12 | FY12P13
9 | 2012-08-13 | 2 | WK50 | P13 | W2 | P13W2 | FY12 | FY12P13
10 | 2012-08-14 | 3 | WK50 | P13 | W2 | P13W2 | FY12 | FY12P13
11 | 2012-08-15 | 4 | WK50 | P13 | W2 | P13W2 | FY12 | FY12P13
12 | 2012-08-16 | 5 | WK50 | P13 | W2 | P13W2 | FY12 | FY12P13
13 | 2012-08-17 | 6 | WK50 | P13 | W2 | P13W2 | FY12 | FY12P13
14 | 2012-08-18 | 7 | WK50 | P13 | W2 | P13W2 | FY12 | FY12P13
15 | 2012-08-19 | 1 | WK51 | P13 | W3 | P13W3 | FY12 | FY12P13
16 | 2012-08-20 | 2 | WK51 | P13 | W3 | P13W3 | FY12 | FY12P13
17 | 2012-08-21 | 3 | WK51 | P13 | W3 | P13W3 | FY12 | FY12P13
18 | 2012-08-22 | 4 | WK51 | P13 | W3 | P13W3 | FY12 | FY12P13
19 | 2012-08-23 | 5 | WK51 | P13 | W3 | P13W3 | FY12 | FY12P13
20 | 2012-08-24 | 6 | WK51 | P13 | W3 | P13W3 | FY12 | FY12P13
21 | 2012-08-25 | 7 | WK51 | P13 | W3 | P13W3 | FY12 | FY12P13
22 | 2012-08-26 | 1 | WK52 | P13 | W4 | P13W4 | FY12 | FY12P13
23 | 2012-08-27 | 2 | WK52 | P13 | W4 | P13W4 | FY12 | FY12P13
24 | 2012-08-28 | 3 | WK52 | P13 | W4 | P13W4 | FY12 | FY12P13
25 | 2012-08-29 | 4 | WK52 | P13 | W4 | P13W4 | FY12 | FY12P13
26 | 2012-08-30 | 5 | WK52 | P13 | W4 | P13W4 | FY12 | FY12P13
27 | 2012-08-31 | 6 | WK52 | P13 | W4 | P13W4 | FY12 | FY12P13
28 | 2012-09-01 | 7 | WK52 | P13 | W4 | P13W4 | FY12 | FY12P13
1 | 2012-09-02 | 1 | WK1 | P1 | W1 | P1W1 | FY13 | FY13P01
2 | 2012-09-03 | 2 | WK1 | P1 | W1 | P1W1 | FY13 | FY13P01
3 | 2012-09-04 | 3 | WK1 | P1 | W1 | P1W1 | FY13 | FY13P01
4 | 2012-09-05 | 4 | WK1 | P1 | W1 | P1W1 | FY13 | FY13P01
5 | 2012-09-06 | 5 | WK1 | P1 | W1 | P1W1 | FY13 | FY13P01
6 | 2012-09-07 | 6 | WK1 | P1 | W1 | P1W1 | FY13 | FY13P01
7 | 2012-09-08 | 7 | WK1 | P1 | W1 | P1W1 | FY13 | FY13P01
8 | 2012-09-09 | 1 | WK2 | P1 | W2 | P1W2 | FY13 | FY13P01
9 | 2012-09-10 | 2 | WK2 | P1 | W2 | P1W2 | FY13 | FY13P01
10 | 2012-09-11 | 3 | WK2 | P1 | W2 | P1W2 | FY13 | FY13P01
11 | 2012-09-12 | 4 | WK2 | P1 | W2 | P1W2 | FY13 | FY13P01
12 | 2012-09-13 | 5 | WK2 | P1 | W2 | P1W2 | FY13 | FY13P01
13 | 2012-09-14 | 6 | WK2 | P1 | W2 | P1W2 | FY13 | FY13P01
14 | 2012-09-15 | 7 | WK2 | P1 | W2 | P1W2 | FY13 | FY13P01
15 | 2012-09-16 | 1 | WK3 | P1 | W3 | P1W3 | FY13 | FY13P01
16 | 2012-09-17 | 2 | WK3 | P1 | W3 | P1W3 | FY13 | FY13P01
17 | 2012-09-18 | 3 | WK3 | P1 | W3 | P1W3 | FY13 | FY13P01
18 | 2012-09-19 | 4 | WK3 | P1 | W3 | P1W3 | FY13 | FY13P01
19 | 2012-09-20 | 5 | WK3 | P1 | W3 | P1W3 | FY13 | FY13P01
20 | 2012-09-21 | 6 | WK3 | P1 | W3 | P1W3 | FY13 | FY13P01
21 | 2012-09-22 | 7 | WK3 | P1 | W3 | P1W3 | FY13 | FY13P01
22 | 2012-09-23 | 1 | WK4 | P1 | W4 | P1W4 | FY13 | FY13P01
23 | 2012-09-24 | 2 | WK4 | P1 | W4 | P1W4 | FY13 | FY13P01
24 | 2012-09-25 | 3 | WK4 | P1 | W4 | P1W4 | FY13 | FY13P01
25 | 2012-09-26 | 4 | WK4 | P1 | W4 | P1W4 | FY13 | FY13P01
26 | 2012-09-27 | 5 | WK4 | P1 | W4 | P1W4 | FY13 | FY13P01
27 | 2012-09-28 | 6 | WK4 | P1 | W4 | P1W4 | FY13 | FY13P01
28 | 2012-09-29 | 7 | WK4 | P1 | W4 | P1W4 | FY13 | FY13P01
1 | 2012-09-30 | 1 | WK5 | P2 | W1 | P2W1 | FY13 | FY13P02
2 | 2012-10-01 | 2 | WK5 | P2 | W1 | P2W1 | FY13 | FY13P02
3 | 2012-10-02 | 3 | WK5 | P2 | W1 | P2W1 | FY13 | FY13P02
4 | 2012-10-03 | 4 | WK5 | P2 | W1 | P2W1 | FY13 | FY13P02
5 | 2012-10-04 | 5 | WK5 | P2 | W1 | P2W1 | FY13 | FY13P02
6 | 2012-10-05 | 6 | WK5 | P2 | W1 | P2W1 | FY13 | FY13P02
7 | 2012-10-06 | 7 | WK5 | P2 | W1 | P2W1 | FY13 | FY13P02
8 | 2012-10-07 | 1 | WK6 | P2 | W2 | P2W2 | FY13 | FY13P02
9 | 2012-10-08 | 2 | WK6 | P2 | W2 | P2W2 | FY13 | FY13P02
10 | 2012-10-09 | 3 | WK6 | P2 | W2 | P2W2 | FY13 | FY13P02
11 | 2012-10-10 | 4 | WK6 | P2 | W2 | P2W2 | FY13 | FY13P02
12 | 2012-10-11 | 5 | WK6 | P2 | W2 | P2W2 | FY13 | FY13P02
13 | 2012-10-12 | 6 | WK6 | P2 | W2 | P2W2 | FY13 | FY13P02
14 | 2012-10-13 | 7 | WK6 | P2 | W2 | P2W2 | FY13 | FY13P02
15 | 2012-10-14 | 1 | WK7 | P2 | W3 | P2W3 | FY13 | FY13P02
16 | 2012-10-15 | 2 | WK7 | P2 | W3 | P2W3 | FY13 | FY13P02
17 | 2012-10-16 | 3 | WK7 | P2 | W3 | P2W3 | FY13 | FY13P02
18 | 2012-10-17 | 4 | WK7 | P2 | W3 | P2W3 | FY13 | FY13P02
19 | 2012-10-18 | 5 | WK7 | P2 | W3 | P2W3 | FY13 | FY13P02
20 | 2012-10-19 | 6 | WK7 | P2 | W3 | P2W3 | FY13 | FY13P02
21 | 2012-10-20 | 7 | WK7 | P2 | W3 | P2W3 | FY13 | FY13P02
22 | 2012-10-21 | 1 | WK8 | P2 | W4 | P2W4 | FY13 | FY13P02
23 | 2012-10-22 | 2 | WK8 | P2 | W4 | P2W4 | FY13 | FY13P02
24 | 2012-10-23 | 3 | WK8 | P2 | W4 | P2W4 | FY13 | FY13P02
25 | 2012-10-24 | 4 | WK8 | P2 | W4 | P2W4 | FY13 | FY13P02
26 | 2012-10-25 | 5 | WK8 | P2 | W4 | P2W4 | FY13 | FY13P02
27 | 2012-10-26 | 6 | WK8 | P2 | W4 | P2W4 | FY13 | FY13P02
28 | 2012-10-27 | 7 | WK8 | P2 | W4 | P2W4 | FY13 | FY13P02
1 | 2012-10-28 | 1 | WK9 | P3 | W1 | P3W1 | FY13 | FY13P03
2 | 2012-10-29 | 2 | WK9 | P3 | W1 | P3W1 | FY13 | FY13P03
3 | 2012-10-30 | 3 | WK9 | P3 | W1 | P3W1 | FY13 | FY13P03
4 | 2012-10-31 | 4 | WK9 | P3 | W1 | P3W1 | FY13 | FY13P03
5 | 2012-11-01 | 5 | WK9 | P3 | W1 | P3W1 | FY13 | FY13P03
6 | 2012-11-02 | 6 | WK9 | P3 | W1 | P3W1 | FY13 | FY13P03
7 | 2012-11-03 | 7 | WK9 | P3 | W1 | P3W1 | FY13 | FY13P03
8 | 2012-11-04 | 1 | WK10 | P3 | W2 | P3W2 | FY13 | FY13P03
9 | 2012-11-05 | 2 | WK10 | P3 | W2 | P3W2 | FY13 | FY13P03
10 | 2012-11-06 | 3 | WK10 | P3 | W2 | P3W2 | FY13 | FY13P03
11 | 2012-11-07 | 4 | WK10 | P3 | W2 | P3W2 | FY13 | FY13P03
12 | 2012-11-08 | 5 | WK10 | P3 | W2 | P3W2 | FY13 | FY13P03
13 | 2012-11-09 | 6 | WK10 | P3 | W2 | P3W2 | FY13 | FY13P03
14 | 2012-11-10 | 7 | WK10 | P3 | W2 | P3W2 | FY13 | FY13P03
15 | 2012-11-11 | 1 | WK11 | P3 | W3 | P3W3 | FY13 | FY13P03
16 | 2012-11-12 | 2 | WK11 | P3 | W3 | P3W3 | FY13 | FY13P03
17 | 2012-11-13 | 3 | WK11 | P3 | W3 | P3W3 | FY13 | FY13P03
18 | 2012-11-14 | 4 | WK11 | P3 | W3 | P3W3 | FY13 | FY13P03
19 | 2012-11-15 | 5 | WK11 | P3 | W3 | P3W3 | FY13 | FY13P03
20 | 2012-11-16 | 6 | WK11 | P3 | W3 | P3W3 | FY13 | FY13P03
21 | 2012-11-17 | 7 | WK11 | P3 | W3 | P3W3 | FY13 | FY13P03
22 | 2012-11-18 | 1 | WK12 | P3 | W4 | P3W4 | FY13 | FY13P03
23 | 2012-11-19 | 2 | WK12 | P3 | W4 | P3W4 | FY13 | FY13P03
24 | 2012-11-20 | 3 | WK12 | P3 | W4 | P3W4 | FY13 | FY13P03
25 | 2012-11-21 | 4 | WK12 | P3 | W4 | P3W4 | FY13 | FY13P03
26 | 2012-11-22 | 5 | WK12 | P3 | W4 | P3W4 | FY13 | FY13P03
27 | 2012-11-23 | 6 | WK12 | P3 | W4 | P3W4 | FY13 | FY13P03
28 | 2012-11-24 | 7 | WK12 | P3 | W4 | P3W4 | FY13 | FY13P03
1 | 2012-11-25 | 1 | WK13 | P4 | W1 | P4W1 | FY13 | FY13P04
2 | 2012-11-26 | 2 | WK13 | P4 | W1 | P4W1 | FY13 | FY13P04
3 | 2012-11-27 | 3 | WK13 | P4 | W1 | P4W1 | FY13 | FY13P04
4 | 2012-11-28 | 4 | WK13 | P4 | W1 | P4W1 | FY13 | FY13P04
5 | 2012-11-29 | 5 | WK13 | P4 | W1 | P4W1 | FY13 | FY13P04
6 | 2012-11-30 | 6 | WK13 | P4 | W1 | P4W1 | FY13 | FY13P04
7 | 2012-12-01 | 7 | WK13 | P4 | W1 | P4W1 | FY13 | FY13P04
8 | 2012-12-02 | 1 | WK14 | P4 | W2 | P4W2 | FY13 | FY13P04
9 | 2012-12-03 | 2 | WK14 | P4 | W2 | P4W2 | FY13 | FY13P04
10 | 2012-12-04 | 3 | WK14 | P4 | W2 | P4W2 | FY13 | FY13P04
11 | 2012-12-05 | 4 | WK14 | P4 | W2 | P4W2 | FY13 | FY13P04
12 | 2012-12-06 | 5 | WK14 | P4 | W2 | P4W2 | FY13 | FY13P04
13 | 2012-12-07 | 6 | WK14 | P4 | W2 | P4W2 | FY13 | FY13P04
14 | 2012-12-08 | 7 | WK14 | P4 | W2 | P4W2 | FY13 | FY13P04
15 | 2012-12-09 | 1 | WK15 | P4 | W3 | P4W3 | FY13 | FY13P04
16 | 2012-12-10 | 2 | WK15 | P4 | W3 | P4W3 | FY13 | FY13P04
17 | 2012-12-11 | 3 | WK15 | P4 | W3 | P4W3 | FY13 | FY13P04
18 | 2012-12-12 | 4 | WK15 | P4 | W3 | P4W3 | FY13 | FY13P04
19 | 2012-12-13 | 5 | WK15 | P4 | W3 | P4W3 | FY13 | FY13P04
20 | 2012-12-14 | 6 | WK15 | P4 | W3 | P4W3 | FY13 | FY13P04
21 | 2012-12-15 | 7 | WK15 | P4 | W3 | P4W3 | FY13 | FY13P04
22 | 2012-12-16 | 1 | WK16 | P4 | W4 | P4W4 | FY13 | FY13P04
23 | 2012-12-17 | 2 | WK16 | P4 | W4 | P4W4 | FY13 | FY13P04
24 | 2012-12-18 | 3 | WK16 | P4 | W4 | P4W4 | FY13 | FY13P04
25 | 2012-12-19 | 4 | WK16 | P4 | W4 | P4W4 | FY13 | FY13P04
26 | 2012-12-20 | 5 | WK16 | P4 | W4 | P4W4 | FY13 | FY13P04
27 | 2012-12-21 | 6 | WK16 | P4 | W4 | P4W4 | FY13 | FY13P04
28 | 2012-12-22 | 7 | WK16 | P4 | W4 | P4W4 | FY13 | FY13P04
1 | 2012-12-23 | 1 | WK17 | P5 | W1 | P5W1 | FY13 | FY13P05
2 | 2012-12-24 | 2 | WK17 | P5 | W1 | P5W1 | FY13 | FY13P05
3 | 2012-12-25 | 3 | WK17 | P5 | W1 | P5W1 | FY13 | FY13P05
4 | 2012-12-26 | 4 | WK17 | P5 | W1 | P5W1 | FY13 | FY13P05
5 | 2012-12-27 | 5 | WK17 | P5 | W1 | P5W1 | FY13 | FY13P05
6 | 2012-12-28 | 6 | WK17 | P5 | W1 | P5W1 | FY13 | FY13P05
7 | 2012-12-29 | 7 | WK17 | P5 | W1 | P5W1 | FY13 | FY13P05
8 | 2012-12-30 | 1 | WK18 | P5 | W2 | P5W2 | FY13 | FY13P05
9 | 2012-12-31 | 2 | WK18 | P5 | W2 | P5W2 | FY13 | FY13P05
10 | 2013-01-01 | 3 | WK18 | P5 | W2 | P5W2 | FY13 | FY13P05
11 | 2013-01-02 | 4 | WK18 | P5 | W2 | P5W2 | FY13 | FY13P05
12 | 2013-01-03 | 5 | WK18 | P5 | W2 | P5W2 | FY13 | FY13P05
13 | 2013-01-04 | 6 | WK18 | P5 | W2 | P5W2 | FY13 | FY13P05
14 | 2013-01-05 | 7 | WK18 | P5 | W2 | P5W2 | FY13 | FY13P05
15 | 2013-01-06 | 1 | WK19 | P5 | W3 | P5W3 | FY13 | FY13P05
16 | 2013-01-07 | 2 | WK19 | P5 | W3 | P5W3 | FY13 | FY13P05
17 | 2013-01-08 | 3 | WK19 | P5 | W3 | P5W3 | FY13 | FY13P05
18 | 2013-01-09 | 4 | WK19 | P5 | W3 | P5W3 | FY13 | FY13P05
19 | 2013-01-10 | 5 | WK19 | P5 | W3 | P5W3 | FY13 | FY13P05
20 | 2013-01-11 | 6 | WK19 | P5 | W3 | P5W3 | FY13 | FY13P05
21 | 2013-01-12 | 7 | WK19 | P5 | W3 | P5W3 | FY13 | FY13P05
22 | 2013-01-13 | 1 | WK20 | P5 | W4 | P5W4 | FY13 | FY13P05
23 | 2013-01-14 | 2 | WK20 | P5 | W4 | P5W4 | FY13 | FY13P05
24 | 2013-01-15 | 3 | WK20 | P5 | W4 | P5W4 | FY13 | FY13P05
25 | 2013-01-16 | 4 | WK20 | P5 | W4 | P5W4 | FY13 | FY13P05
26 | 2013-01-17 | 5 | WK20 | P5 | W4 | P5W4 | FY13 | FY13P05
27 | 2013-01-18 | 6 | WK20 | P5 | W4 | P5W4 | FY13 | FY13P05
28 | 2013-01-19 | 7 | WK20 | P5 | W4 | P5W4 | FY13 | FY13P05
1 | 2013-01-20 | 1 | WK21 | P6 | W1 | P6W1 | FY13 | FY13P06
2 | 2013-01-21 | 2 | WK21 | P6 | W1 | P6W1 | FY13 | FY13P06
3 | 2013-01-22 | 3 | WK21 | P6 | W1 | P6W1 | FY13 | FY13P06
4 | 2013-01-23 | 4 | WK21 | P6 | W1 | P6W1 | FY13 | FY13P06
5 | 2013-01-24 | 5 | WK21 | P6 | W1 | P6W1 | FY13 | FY13P06
6 | 2013-01-25 | 6 | WK21 | P6 | W1 | P6W1 | FY13 | FY13P06
7 | 2013-01-26 | 7 | WK21 | P6 | W1 | P6W1 | FY13 | FY13P06
8 | 2013-01-27 | 1 | WK22 | P6 | W2 | P6W2 | FY13 | FY13P06
9 | 2013-01-28 | 2 | WK22 | P6 | W2 | P6W2 | FY13 | FY13P06
10 | 2013-01-29 | 3 | WK22 | P6 | W2 | P6W2 | FY13 | FY13P06
11 | 2013-01-30 | 4 | WK22 | P6 | W2 | P6W2 | FY13 | FY13P06
12 | 2013-01-31 | 5 | WK22 | P6 | W2 | P6W2 | FY13 | FY13P06
13 | 2013-02-01 | 6 | WK22 | P6 | W2 | P6W2 | FY13 | FY13P06
14 | 2013-02-02 | 7 | WK22 | P6 | W2 | P6W2 | FY13 | FY13P06
15 | 2013-02-03 | 1 | WK23 | P6 | W3 | P6W3 | FY13 | FY13P06
16 | 2013-02-04 | 2 | WK23 | P6 | W3 | P6W3 | FY13 | FY13P06
17 | 2013-02-05 | 3 | WK23 | P6 | W3 | P6W3 | FY13 | FY13P06
18 | 2013-02-06 | 4 | WK23 | P6 | W3 | P6W3 | FY13 | FY13P06
19 | 2013-02-07 | 5 | WK23 | P6 | W3 | P6W3 | FY13 | FY13P06
20 | 2013-02-08 | 6 | WK23 | P6 | W3 | P6W3 | FY13 | FY13P06
21 | 2013-02-09 | 7 | WK23 | P6 | W3 | P6W3 | FY13 | FY13P06
22 | 2013-02-10 | 1 | WK24 | P6 | W4 | P6W4 | FY13 | FY13P06
23 | 2013-02-11 | 2 | WK24 | P6 | W4 | P6W4 | FY13 | FY13P06
24 | 2013-02-12 | 3 | WK24 | P6 | W4 | P6W4 | FY13 | FY13P06
25 | 2013-02-13 | 4 | WK24 | P6 | W4 | P6W4 | FY13 | FY13P06
26 | 2013-02-14 | 5 | WK24 | P6 | W4 | P6W4 | FY13 | FY13P06
27 | 2013-02-15 | 6 | WK24 | P6 | W4 | P6W4 | FY13 | FY13P06
28 | 2013-02-16 | 7 | WK24 | P6 | W4 | P6W4 | FY13 | FY13P06
1 | 2013-02-17 | 1 | WK25 | P7 | W1 | P7W1 | FY13 | FY13P07
2 | 2013-02-18 | 2 | WK25 | P7 | W1 | P7W1 | FY13 | FY13P07
3 | 2013-02-19 | 3 | WK25 | P7 | W1 | P7W1 | FY13 | FY13P07
4 | 2013-02-20 | 4 | WK25 | P7 | W1 | P7W1 | FY13 | FY13P07
5 | 2013-02-21 | 5 | WK25 | P7 | W1 | P7W1 | FY13 | FY13P07
6 | 2013-02-22 | 6 | WK25 | P7 | W1 | P7W1 | FY13 | FY13P07
7 | 2013-02-23 | 7 | WK25 | P7 | W1 | P7W1 | FY13 | FY13P07
8 | 2013-02-24 | 1 | WK26 | P7 | W2 | P7W2 | FY13 | FY13P07
9 | 2013-02-25 | 2 | WK26 | P7 | W2 | P7W2 | FY13 | FY13P07
10 | 2013-02-26 | 3 | WK26 | P7 | W2 | P7W2 | FY13 | FY13P07
11 | 2013-02-27 | 4 | WK26 | P7 | W2 | P7W2 | FY13 | FY13P07
12 | 2013-02-28 | 5 | WK26 | P7 | W2 | P7W2 | FY13 | FY13P07
13 | 2013-03-01 | 6 | WK26 | P7 | W2 | P7W2 | FY13 | FY13P07
14 | 2013-03-02 | 7 | WK26 | P7 | W2 | P7W2 | FY13 | FY13P07
15 | 2013-03-03 | 1 | WK27 | P7 | W3 | P7W3 | FY13 | FY13P07
16 | 2013-03-04 | 2 | WK27 | P7 | W3 | P7W3 | FY13 | FY13P07
17 | 2013-03-05 | 3 | WK27 | P7 | W3 | P7W3 | FY13 | FY13P07
18 | 2013-03-06 | 4 | WK27 | P7 | W3 | P7W3 | FY13 | FY13P07
19 | 2013-03-07 | 5 | WK27 | P7 | W3 | P7W3 | FY13 | FY13P07
20 | 2013-03-08 | 6 | WK27 | P7 | W3 | P7W3 | FY13 | FY13P07
21 | 2013-03-09 | 7 | WK27 | P7 | W3 | P7W3 | FY13 | FY13P07
22 | 2013-03-10 | 1 | WK28 | P7 | W4 | P7W4 | FY13 | FY13P07
23 | 2013-03-11 | 2 | WK28 | P7 | W4 | P7W4 | FY13 | FY13P07
24 | 2013-03-12 | 3 | WK28 | P7 | W4 | P7W4 | FY13 | FY13P07
25 | 2013-03-13 | 4 | WK28 | P7 | W4 | P7W4 | FY13 | FY13P07
26 | 2013-03-14 | 5 | WK28 | P7 | W4 | P7W4 | FY13 | FY13P07
27 | 2013-03-15 | 6 | WK28 | P7 | W4 | P7W4 | FY13 | FY13P07
28 | 2013-03-16 | 7 | WK28 | P7 | W4 | P7W4 | FY13 | FY13P07
1 | 2013-03-17 | 1 | WK29 | P8 | W1 | P8W1 | FY13 | FY13P08
2 | 2013-03-18 | 2 | WK29 | P8 | W1 | P8W1 | FY13 | FY13P08
3 | 2013-03-19 | 3 | WK29 | P8 | W1 | P8W1 | FY13 | FY13P08
4 | 2013-03-20 | 4 | WK29 | P8 | W1 | P8W1 | FY13 | FY13P08
5 | 2013-03-21 | 5 | WK29 | P8 | W1 | P8W1 | FY13 | FY13P08
6 | 2013-03-22 | 6 | WK29 | P8 | W1 | P8W1 | FY13 | FY13P08
7 | 2013-03-23 | 7 | WK29 | P8 | W1 | P8W1 | FY13 | FY13P08
8 | 2013-03-24 | 1 | WK30 | P8 | W2 | P8W2 | FY13 | FY13P08
9 | 2013-03-25 | 2 | WK30 | P8 | W2 | P8W2 | FY13 | FY13P08
10 | 2013-03-26 | 3 | WK30 | P8 | W2 | P8W2 | FY13 | FY13P08
11 | 2013-03-27 | 4 | WK30 | P8 | W2 | P8W2 | FY13 | FY13P08
12 | 2013-03-28 | 5 | WK30 | P8 | W2 | P8W2 | FY13 | FY13P08
13 | 2013-03-29 | 6 | WK30 | P8 | W2 | P8W2 | FY13 | FY13P08
14 | 2013-03-30 | 7 | WK30 | P8 | W2 | P8W2 | FY13 | FY13P08
15 | 2013-03-31 | 1 | WK31 | P8 | W3 | P8W3 | FY13 | FY13P08
16 | 2013-04-01 | 2 | WK31 | P8 | W3 | P8W3 | FY13 | FY13P08
17 | 2013-04-02 | 3 | WK31 | P8 | W3 | P8W3 | FY13 | FY13P08
18 | 2013-04-03 | 4 | WK31 | P8 | W3 | P8W3 | FY13 | FY13P08
19 | 2013-04-04 | 5 | WK31 | P8 | W3 | P8W3 | FY13 | FY13P08
20 | 2013-04-05 | 6 | WK31 | P8 | W3 | P8W3 | FY13 | FY13P08
21 | 2013-04-06 | 7 | WK31 | P8 | W3 | P8W3 | FY13 | FY13P08
22 | 2013-04-07 | 1 | WK32 | P8 | W4 | P8W4 | FY13 | FY13P08
23 | 2013-04-08 | 2 | WK32 | P8 | W4 | P8W4 | FY13 | FY13P08
24 | 2013-04-09 | 3 | WK32 | P8 | W4 | P8W4 | FY13 | FY13P08
25 | 2013-04-10 | 4 | WK32 | P8 | W4 | P8W4 | FY13 | FY13P08
26 | 2013-04-11 | 5 | WK32 | P8 | W4 | P8W4 | FY13 | FY13P08
27 | 2013-04-12 | 6 | WK32 | P8 | W4 | P8W4 | FY13 | FY13P08
28 | 2013-04-13 | 7 | WK32 | P8 | W4 | P8W4 | FY13 | FY13P08
1 | 2013-04-14 | 1 | WK33 | P9 | W1 | P9W1 | FY13 | FY13P09
2 | 2013-04-15 | 2 | WK33 | P9 | W1 | P9W1 | FY13 | FY13P09
3 | 2013-04-16 | 3 | WK33 | P9 | W1 | P9W1 | FY13 | FY13P09
4 | 2013-04-17 | 4 | WK33 | P9 | W1 | P9W1 | FY13 | FY13P09
5 | 2013-04-18 | 5 | WK33 | P9 | W1 | P9W1 | FY13 | FY13P09
6 | 2013-04-19 | 6 | WK33 | P9 | W1 | P9W1 | FY13 | FY13P09
7 | 2013-04-20 | 7 | WK33 | P9 | W1 | P9W1 | FY13 | FY13P09
8 | 2013-04-21 | 1 | WK34 | P9 | W2 | P9W2 | FY13 | FY13P09
9 | 2013-04-22 | 2 | WK34 | P9 | W2 | P9W2 | FY13 | FY13P09
10 | 2013-04-23 | 3 | WK34 | P9 | W2 | P9W2 | FY13 | FY13P09
11 | 2013-04-24 | 4 | WK34 | P9 | W2 | P9W2 | FY13 | FY13P09
12 | 2013-04-25 | 5 | WK34 | P9 | W2 | P9W2 | FY13 | FY13P09
13 | 2013-04-26 | 6 | WK34 | P9 | W2 | P9W2 | FY13 | FY13P09
14 | 2013-04-27 | 7 | WK34 | P9 | W2 | P9W2 | FY13 | FY13P09
15 | 2013-04-28 | 1 | WK35 | P9 | W3 | P9W3 | FY13 | FY13P09
16 | 2013-04-29 | 2 | WK35 | P9 | W3 | P9W3 | FY13 | FY13P09
17 | 2013-04-30 | 3 | WK35 | P9 | W3 | P9W3 | FY13 | FY13P09
18 | 2013-05-01 | 4 | WK35 | P9 | W3 | P9W3 | FY13 | FY13P09
19 | 2013-05-02 | 5 | WK35 | P9 | W3 | P9W3 | FY13 | FY13P09
20 | 2013-05-03 | 6 | WK35 | P9 | W3 | P9W3 | FY13 | FY13P09
21 | 2013-05-04 | 7 | WK35 | P9 | W3 | P9W3 | FY13 | FY13P09
22 | 2013-05-05 | 1 | WK36 | P9 | W4 | P9W4 | FY13 | FY13P09
23 | 2013-05-06 | 2 | WK36 | P9 | W4 | P9W4 | FY13 | FY13P09
24 | 2013-05-07 | 3 | WK36 | P9 | W4 | P9W4 | FY13 | FY13P09
25 | 2013-05-08 | 4 | WK36 | P9 | W4 | P9W4 | FY13 | FY13P09
26 | 2013-05-09 | 5 | WK36 | P9 | W4 | P9W4 | FY13 | FY13P09
27 | 2013-05-10 | 6 | WK36 | P9 | W4 | P9W4 | FY13 | FY13P09
28 | 2013-05-11 | 7 | WK36 | P9 | W4 | P9W4 | FY13 | FY13P09
1 | 2013-05-12 | 1 | WK37 | P10 | W1 | P10W1 | FY13 | FY13P10
2 | 2013-05-13 | 2 | WK37 | P10 | W1 | P10W1 | FY13 | FY13P10
3 | 2013-05-14 | 3 | WK37 | P10 | W1 | P10W1 | FY13 | FY13P10
4 | 2013-05-15 | 4 | WK37 | P10 | W1 | P10W1 | FY13 | FY13P10
5 | 2013-05-16 | 5 | WK37 | P10 | W1 | P10W1 | FY13 | FY13P10
6 | 2013-05-17 | 6 | WK37 | P10 | W1 | P10W1 | FY13 | FY13P10
7 | 2013-05-18 | 7 | WK37 | P10 | W1 | P10W1 | FY13 | FY13P10
8 | 2013-05-19 | 1 | WK38 | P10 | W2 | P10W2 | FY13 | FY13P10
9 | 2013-05-20 | 2 | WK38 | P10 | W2 | P10W2 | FY13 | FY13P10
10 | 2013-05-21 | 3 | WK38 | P10 | W2 | P10W2 | FY13 | FY13P10
11 | 2013-05-22 | 4 | WK38 | P10 | W2 | P10W2 | FY13 | FY13P10
12 | 2013-05-23 | 5 | WK38 | P10 | W2 | P10W2 | FY13 | FY13P10
13 | 2013-05-24 | 6 | WK38 | P10 | W2 | P10W2 | FY13 | FY13P10
14 | 2013-05-25 | 7 | WK38 | P10 | W2 | P10W2 | FY13 | FY13P10
15 | 2013-05-26 | 1 | WK39 | P10 | W3 | P10W3 | FY13 | FY13P10
16 | 2013-05-27 | 2 | WK39 | P10 | W3 | P10W3 | FY13 | FY13P10
17 | 2013-05-28 | 3 | WK39 | P10 | W3 | P10W3 | FY13 | FY13P10
18 | 2013-05-29 | 4 | WK39 | P10 | W3 | P10W3 | FY13 | FY13P10
19 | 2013-05-30 | 5 | WK39 | P10 | W3 | P10W3 | FY13 | FY13P10
20 | 2013-05-31 | 6 | WK39 | P10 | W3 | P10W3 | FY13 | FY13P10
21 | 2013-06-01 | 7 | WK39 | P10 | W3 | P10W3 | FY13 | FY13P10
22 | 2013-06-02 | 1 | WK40 | P10 | W4 | P10W4 | FY13 | FY13P10
23 | 2013-06-03 | 2 | WK40 | P10 | W4 | P10W4 | FY13 | FY13P10
24 | 2013-06-04 | 3 | WK40 | P10 | W4 | P10W4 | FY13 | FY13P10
25 | 2013-06-05 | 4 | WK40 | P10 | W4 | P10W4 | FY13 | FY13P10
26 | 2013-06-06 | 5 | WK40 | P10 | W4 | P10W4 | FY13 | FY13P10
27 | 2013-06-07 | 6 | WK40 | P10 | W4 | P10W4 | FY13 | FY13P10
28 | 2013-06-08 | 7 | WK40 | P10 | W4 | P10W4 | FY13 | FY13P10
1 | 2013-06-09 | 1 | WK41 | P11 | W1 | P11W1 | FY13 | FY13P11
2 | 2013-06-10 | 2 | WK41 | P11 | W1 | P11W1 | FY13 | FY13P11
3 | 2013-06-11 | 3 | WK41 | P11 | W1 | P11W1 | FY13 | FY13P11
4 | 2013-06-12 | 4 | WK41 | P11 | W1 | P11W1 | FY13 | FY13P11
5 | 2013-06-13 | 5 | WK41 | P11 | W1 | P11W1 | FY13 | FY13P11
6 | 2013-06-14 | 6 | WK41 | P11 | W1 | P11W1 | FY13 | FY13P11
7 | 2013-06-15 | 7 | WK41 | P11 | W1 | P11W1 | FY13 | FY13P11
8 | 2013-06-16 | 1 | WK42 | P11 | W2 | P11W2 | FY13 | FY13P11
9 | 2013-06-17 | 2 | WK42 | P11 | W2 | P11W2 | FY13 | FY13P11
10 | 2013-06-18 | 3 | WK42 | P11 | W2 | P11W2 | FY13 | FY13P11
11 | 2013-06-19 | 4 | WK42 | P11 | W2 | P11W2 | FY13 | FY13P11
12 | 2013-06-20 | 5 | WK42 | P11 | W2 | P11W2 | FY13 | FY13P11
13 | 2013-06-21 | 6 | WK42 | P11 | W2 | P11W2 | FY13 | FY13P11
14 | 2013-06-22 | 7 | WK42 | P11 | W2 | P11W2 | FY13 | FY13P11
15 | 2013-06-23 | 1 | WK43 | P11 | W3 | P11W3 | FY13 | FY13P11
16 | 2013-06-24 | 2 | WK43 | P11 | W3 | P11W3 | FY13 | FY13P11
17 | 2013-06-25 | 3 | WK43 | P11 | W3 | P11W3 | FY13 | FY13P11
18 | 2013-06-26 | 4 | WK43 | P11 | W3 | P11W3 | FY13 | FY13P11
19 | 2013-06-27 | 5 | WK43 | P11 | W3 | P11W3 | FY13 | FY13P11
20 | 2013-06-28 | 6 | WK43 | P11 | W3 | P11W3 | FY13 | FY13P11
21 | 2013-06-29 | 7 | WK43 | P11 | W3 | P11W3 | FY13 | FY13P11
22 | 2013-06-30 | 1 | WK44 | P11 | W4 | P11W4 | FY13 | FY13P11
23 | 2013-07-01 | 2 | WK44 | P11 | W4 | P11W4 | FY13 | FY13P11
24 | 2013-07-02 | 3 | WK44 | P11 | W4 | P11W4 | FY13 | FY13P11
25 | 2013-07-03 | 4 | WK44 | P11 | W4 | P11W4 | FY13 | FY13P11
26 | 2013-07-04 | 5 | WK44 | P11 | W4 | P11W4 | FY13 | FY13P11
27 | 2013-07-05 | 6 | WK44 | P11 | W4 | P11W4 | FY13 | FY13P11
28 | 2013-07-06 | 7 | WK44 | P11 | W4 | P11W4 | FY13 | FY13P11
1 | 2013-07-07 | 1 | WK45 | P12 | W1 | P12W1 | FY13 | FY13P12
2 | 2013-07-08 | 2 | WK45 | P12 | W1 | P12W1 | FY13 | FY13P12
3 | 2013-07-09 | 3 | WK45 | P12 | W1 | P12W1 | FY13 | FY13P12
4 | 2013-07-10 | 4 | WK45 | P12 | W1 | P12W1 | FY13 | FY13P12
5 | 2013-07-11 | 5 | WK45 | P12 | W1 | P12W1 | FY13 | FY13P12
6 | 2013-07-12 | 6 | WK45 | P12 | W1 | P12W1 | FY13 | FY13P12
7 | 2013-07-13 | 7 | WK45 | P12 | W1 | P12W1 | FY13 | FY13P12
8 | 2013-07-14 | 1 | WK46 | P12 | W2 | P12W2 | FY13 | FY13P12
9 | 2013-07-15 | 2 | WK46 | P12 | W2 | P12W2 | FY13 | FY13P12
10 | 2013-07-16 | 3 | WK46 | P12 | W2 | P12W2 | FY13 | FY13P12
11 | 2013-07-17 | 4 | WK46 | P12 | W2 | P12W2 | FY13 | FY13P12
12 | 2013-07-18 | 5 | WK46 | P12 | W2 | P12W2 | FY13 | FY13P12
13 | 2013-07-19 | 6 | WK46 | P12 | W2 | P12W2 | FY13 | FY13P12
14 | 2013-07-20 | 7 | WK46 | P12 | W2 | P12W2 | FY13 | FY13P12
15 | 2013-07-21 | 1 | WK47 | P12 | W3 | P12W3 | FY13 | FY13P12
16 | 2013-07-22 | 2 | WK47 | P12 | W3 | P12W3 | FY13 | FY13P12
17 | 2013-07-23 | 3 | WK47 | P12 | W3 | P12W3 | FY13 | FY13P12
18 | 2013-07-24 | 4 | WK47 | P12 | W3 | P12W3 | FY13 | FY13P12
19 | 2013-07-25 | 5 | WK47 | P12 | W3 | P12W3 | FY13 | FY13P12
20 | 2013-07-26 | 6 | WK47 | P12 | W3 | P12W3 | FY13 | FY13P12
21 | 2013-07-27 | 7 | WK47 | P12 | W3 | P12W3 | FY13 | FY13P12
22 | 2013-07-28 | 1 | WK48 | P12 | W4 | P12W4 | FY13 | FY13P12
23 | 2013-07-29 | 2 | WK48 | P12 | W4 | P12W4 | FY13 | FY13P12
24 | 2013-07-30 | 3 | WK48 | P12 | W4 | P12W4 | FY13 | FY13P12
25 | 2013-07-31 | 4 | WK48 | P12 | W4 | P12W4 | FY13 | FY13P12
26 | 2013-08-01 | 5 | WK48 | P12 | W4 | P12W4 | FY13 | FY13P12
27 | 2013-08-02 | 6 | WK48 | P12 | W4 | P12W4 | FY13 | FY13P12
28 | 2013-08-03 | 7 | WK48 | P12 | W4 | P12W4 | FY13 | FY13P12
1 | 2013-08-04 | 1 | WK49 | P13 | W1 | P13W1 | FY13 | FY13P13
2 | 2013-08-05 | 2 | WK49 | P13 | W1 | P13W1 | FY13 | FY13P13
3 | 2013-08-06 | 3 | WK49 | P13 | W1 | P13W1 | FY13 | FY13P13
4 | 2013-08-07 | 4 | WK49 | P13 | W1 | P13W1 | FY13 | FY13P13
5 | 2013-08-08 | 5 | WK49 | P13 | W1 | P13W1 | FY13 | FY13P13
6 | 2013-08-09 | 6 | WK49 | P13 | W1 | P13W1 | FY13 | FY13P13
7 | 2013-08-10 | 7 | WK49 | P13 | W1 | P13W1 | FY13 | FY13P13
8 | 2013-08-11 | 1 | WK50 | P13 | W2 | P13W2 | FY13 | FY13P13
9 | 2013-08-12 | 2 | WK50 | P13 | W2 | P13W2 | FY13 | FY13P13
10 | 2013-08-13 | 3 | WK50 | P13 | W2 | P13W2 | FY13 | FY13P13
11 | 2013-08-14 | 4 | WK50 | P13 | W2 | P13W2 | FY13 | FY13P13
12 | 2013-08-15 | 5 | WK50 | P13 | W2 | P13W2 | FY13 | FY13P13
13 | 2013-08-16 | 6 | WK50 | P13 | W2 | P13W2 | FY13 | FY13P13
14 | 2013-08-17 | 7 | WK50 | P13 | W2 | P13W2 | FY13 | FY13P13
15 | 2013-08-18 | 1 | WK51 | P13 | W3 | P13W3 | FY13 | FY13P13
16 | 2013-08-19 | 2 | WK51 | P13 | W3 | P13W3 | FY13 | FY13P13
17 | 2013-08-20 | 3 | WK51 | P13 | W3 | P13W3 | FY13 | FY13P13
18 | 2013-08-21 | 4 | WK51 | P13 | W3 | P13W3 | FY13 | FY13P13
19 | 2013-08-22 | 5 | WK51 | P13 | W3 | P13W3 | FY13 | FY13P13
20 | 2013-08-23 | 6 | WK51 | P13 | W3 | P13W3 | FY13 | FY13P13
21 | 2013-08-24 | 7 | WK51 | P13 | W3 | P13W3 | FY13 | FY13P13
22 | 2013-08-25 | 1 | WK52 | P13 | W4 | P13W4 | FY13 | FY13P13
23 | 2013-08-26 | 2 | WK52 | P13 | W4 | P13W4 | FY13 | FY13P13
24 | 2013-08-27 | 3 | WK52 | P13 | W4 | P13W4 | FY13 | FY13P13
25 | 2013-08-28 | 4 | WK52 | P13 | W4 | P13W4 | FY13 | FY13P13
26 | 2013-08-29 | 5 | WK52 | P13 | W4 | P13W4 | FY13 | FY13P13
27 | 2013-08-30 | 6 | WK52 | P13 | W4 | P13W4 | FY13 | FY13P13
28 | 2013-08-31 | 7 | WK52 | P13 | W4 | P13W4 | FY13 | FY13P13
1 | 2013-09-01 | 1 | WK1 | P1 | W1 | P1W1 | FY14 | FY14P01
2 | 2013-09-02 | 2 | WK1 | P1 | W1 | P1W1 | FY14 | FY14P01
3 | 2013-09-03 | 3 | WK1 | P1 | W1 | P1W1 | FY14 | FY14P01
4 | 2013-09-04 | 4 | WK1 | P1 | W1 | P1W1 | FY14 | FY14P01
5 | 2013-09-05 | 5 | WK1 | P1 | W1 | P1W1 | FY14 | FY14P01
6 | 2013-09-06 | 6 | WK1 | P1 | W1 | P1W1 | FY14 | FY14P01
7 | 2013-09-07 | 7 | WK1 | P1 | W1 | P1W1 | FY14 | FY14P01
8 | 2013-09-08 | 1 | WK2 | P1 | W2 | P1W2 | FY14 | FY14P01
9 | 2013-09-09 | 2 | WK2 | P1 | W2 | P1W2 | FY14 | FY14P01
10 | 2013-09-10 | 3 | WK2 | P1 | W2 | P1W2 | FY14 | FY14P01
11 | 2013-09-11 | 4 | WK2 | P1 | W2 | P1W2 | FY14 | FY14P01
12 | 2013-09-12 | 5 | WK2 | P1 | W2 | P1W2 | FY14 | FY14P01
13 | 2013-09-13 | 6 | WK2 | P1 | W2 | P1W2 | FY14 | FY14P01
14 | 2013-09-14 | 7 | WK2 | P1 | W2 | P1W2 | FY14 | FY14P01
15 | 2013-09-15 | 1 | WK3 | P1 | W3 | P1W3 | FY14 | FY14P01
16 | 2013-09-16 | 2 | WK3 | P1 | W3 | P1W3 | FY14 | FY14P01
17 | 2013-09-17 | 3 | WK3 | P1 | W3 | P1W3 | FY14 | FY14P01
18 | 2013-09-18 | 4 | WK3 | P1 | W3 | P1W3 | FY14 | FY14P01
19 | 2013-09-19 | 5 | WK3 | P1 | W3 | P1W3 | FY14 | FY14P01
20 | 2013-09-20 | 6 | WK3 | P1 | W3 | P1W3 | FY14 | FY14P01
21 | 2013-09-21 | 7 | WK3 | P1 | W3 | P1W3 | FY14 | FY14P01
22 | 2013-09-22 | 1 | WK4 | P1 | W4 | P1W4 | FY14 | FY14P01
23 | 2013-09-23 | 2 | WK4 | P1 | W4 | P1W4 | FY14 | FY14P01
24 | 2013-09-24 | 3 | WK4 | P1 | W4 | P1W4 | FY14 | FY14P01
25 | 2013-09-25 | 4 | WK4 | P1 | W4 | P1W4 | FY14 | FY14P01
26 | 2013-09-26 | 5 | WK4 | P1 | W4 | P1W4 | FY14 | FY14P01
27 | 2013-09-27 | 6 | WK4 | P1 | W4 | P1W4 | FY14 | FY14P01
28 | 2013-09-28 | 7 | WK4 | P1 | W4 | P1W4 | FY14 | FY14P01
1 | 2013-09-29 | 1 | WK5 | P2 | W1 | P2W1 | FY14 | FY14P02
2 | 2013-09-30 | 2 | WK5 | P2 | W1 | P2W1 | FY14 | FY14P02
3 | 2013-10-01 | 3 | WK5 | P2 | W1 | P2W1 | FY14 | FY14P02
4 | 2013-10-02 | 4 | WK5 | P2 | W1 | P2W1 | FY14 | FY14P02
5 | 2013-10-03 | 5 | WK5 | P2 | W1 | P2W1 | FY14 | FY14P02
6 | 2013-10-04 | 6 | WK5 | P2 | W1 | P2W1 | FY14 | FY14P02
7 | 2013-10-05 | 7 | WK5 | P2 | W1 | P2W1 | FY14 | FY14P02
8 | 2013-10-06 | 1 | WK6 | P2 | W2 | P2W2 | FY14 | FY14P02
9 | 2013-10-07 | 2 | WK6 | P2 | W2 | P2W2 | FY14 | FY14P02
10 | 2013-10-08 | 3 | WK6 | P2 | W2 | P2W2 | FY14 | FY14P02
11 | 2013-10-09 | 4 | WK6 | P2 | W2 | P2W2 | FY14 | FY14P02
12 | 2013-10-10 | 5 | WK6 | P2 | W2 | P2W2 | FY14 | FY14P02
13 | 2013-10-11 | 6 | WK6 | P2 | W2 | P2W2 | FY14 | FY14P02
14 | 2013-10-12 | 7 | WK6 | P2 | W2 | P2W2 | FY14 | FY14P02
15 | 2013-10-13 | 1 | WK7 | P2 | W3 | P2W3 | FY14 | FY14P02
16 | 2013-10-14 | 2 | WK7 | P2 | W3 | P2W3 | FY14 | FY14P02
17 | 2013-10-15 | 3 | WK7 | P2 | W3 | P2W3 | FY14 | FY14P02
18 | 2013-10-16 | 4 | WK7 | P2 | W3 | P2W3 | FY14 | FY14P02
19 | 2013-10-17 | 5 | WK7 | P2 | W3 | P2W3 | FY14 | FY14P02
20 | 2013-10-18 | 6 | WK7 | P2 | W3 | P2W3 | FY14 | FY14P02
21 | 2013-10-19 | 7 | WK7 | P2 | W3 | P2W3 | FY14 | FY14P02
22 | 2013-10-20 | 1 | WK8 | P2 | W4 | P2W4 | FY14 | FY14P02
23 | 2013-10-21 | 2 | WK8 | P2 | W4 | P2W4 | FY14 | FY14P02
24 | 2013-10-22 | 3 | WK8 | P2 | W4 | P2W4 | FY14 | FY14P02
25 | 2013-10-23 | 4 | WK8 | P2 | W4 | P2W4 | FY14 | FY14P02
26 | 2013-10-24 | 5 | WK8 | P2 | W4 | P2W4 | FY14 | FY14P02
27 | 2013-10-25 | 6 | WK8 | P2 | W4 | P2W4 | FY14 | FY14P02
28 | 2013-10-26 | 7 | WK8 | P2 | W4 | P2W4 | FY14 | FY14P02
1 | 2013-10-27 | 1 | WK9 | P3 | W1 | P3W1 | FY14 | FY14P03
2 | 2013-10-28 | 2 | WK9 | P3 | W1 | P3W1 | FY14 | FY14P03
3 | 2013-10-29 | 3 | WK9 | P3 | W1 | P3W1 | FY14 | FY14P03
4 | 2013-10-30 | 4 | WK9 | P3 | W1 | P3W1 | FY14 | FY14P03
5 | 2013-10-31 | 5 | WK9 | P3 | W1 | P3W1 | FY14 | FY14P03
6 | 2013-11-01 | 6 | WK9 | P3 | W1 | P3W1 | FY14 | FY14P03
7 | 2013-11-02 | 7 | WK9 | P3 | W1 | P3W1 | FY14 | FY14P03
8 | 2013-11-03 | 1 | WK10 | P3 | W2 | P3W2 | FY14 | FY14P03
9 | 2013-11-04 | 2 | WK10 | P3 | W2 | P3W2 | FY14 | FY14P03
10 | 2013-11-05 | 3 | WK10 | P3 | W2 | P3W2 | FY14 | FY14P03
11 | 2013-11-06 | 4 | WK10 | P3 | W2 | P3W2 | FY14 | FY14P03
12 | 2013-11-07 | 5 | WK10 | P3 | W2 | P3W2 | FY14 | FY14P03
13 | 2013-11-08 | 6 | WK10 | P3 | W2 | P3W2 | FY14 | FY14P03
14 | 2013-11-09 | 7 | WK10 | P3 | W2 | P3W2 | FY14 | FY14P03
15 | 2013-11-10 | 1 | WK11 | P3 | W3 | P3W3 | FY14 | FY14P03
16 | 2013-11-11 | 2 | WK11 | P3 | W3 | P3W3 | FY14 | FY14P03
17 | 2013-11-12 | 3 | WK11 | P3 | W3 | P3W3 | FY14 | FY14P03
18 | 2013-11-13 | 4 | WK11 | P3 | W3 | P3W3 | FY14 | FY14P03
19 | 2013-11-14 | 5 | WK11 | P3 | W3 | P3W3 | FY14 | FY14P03
20 | 2013-11-15 | 6 | WK11 | P3 | W3 | P3W3 | FY14 | FY14P03
21 | 2013-11-16 | 7 | WK11 | P3 | W3 | P3W3 | FY14 | FY14P03
22 | 2013-11-17 | 1 | WK12 | P3 | W4 | P3W4 | FY14 | FY14P03
23 | 2013-11-18 | 2 | WK12 | P3 | W4 | P3W4 | FY14 | FY14P03
24 | 2013-11-19 | 3 | WK12 | P3 | W4 | P3W4 | FY14 | FY14P03
25 | 2013-11-20 | 4 | WK12 | P3 | W4 | P3W4 | FY14 | FY14P03
26 | 2013-11-21 | 5 | WK12 | P3 | W4 | P3W4 | FY14 | FY14P03
27 | 2013-11-22 | 6 | WK12 | P3 | W4 | P3W4 | FY14 | FY14P03
28 | 2013-11-23 | 7 | WK12 | P3 | W4 | P3W4 | FY14 | FY14P03
1 | 2013-11-24 | 1 | WK13 | P4 | W1 | P4W1 | FY14 | FY14P04
2 | 2013-11-25 | 2 | WK13 | P4 | W1 | P4W1 | FY14 | FY14P04
3 | 2013-11-26 | 3 | WK13 | P4 | W1 | P4W1 | FY14 | FY14P04
4 | 2013-11-27 | 4 | WK13 | P4 | W1 | P4W1 | FY14 | FY14P04
5 | 2013-11-28 | 5 | WK13 | P4 | W1 | P4W1 | FY14 | FY14P04
6 | 2013-11-29 | 6 | WK13 | P4 | W1 | P4W1 | FY14 | FY14P04
7 | 2013-11-30 | 7 | WK13 | P4 | W1 | P4W1 | FY14 | FY14P04
8 | 2013-12-01 | 1 | WK14 | P4 | W2 | P4W2 | FY14 | FY14P04
9 | 2013-12-02 | 2 | WK14 | P4 | W2 | P4W2 | FY14 | FY14P04
10 | 2013-12-03 | 3 | WK14 | P4 | W2 | P4W2 | FY14 | FY14P04
11 | 2013-12-04 | 4 | WK14 | P4 | W2 | P4W2 | FY14 | FY14P04
12 | 2013-12-05 | 5 | WK14 | P4 | W2 | P4W2 | FY14 | FY14P04
13 | 2013-12-06 | 6 | WK14 | P4 | W2 | P4W2 | FY14 | FY14P04
14 | 2013-12-07 | 7 | WK14 | P4 | W2 | P4W2 | FY14 | FY14P04
15 | 2013-12-08 | 1 | WK15 | P4 | W3 | P4W3 | FY14 | FY14P04
16 | 2013-12-09 | 2 | WK15 | P4 | W3 | P4W3 | FY14 | FY14P04
17 | 2013-12-10 | 3 | WK15 | P4 | W3 | P4W3 | FY14 | FY14P04
18 | 2013-12-11 | 4 | WK15 | P4 | W3 | P4W3 | FY14 | FY14P04
19 | 2013-12-12 | 5 | WK15 | P4 | W3 | P4W3 | FY14 | FY14P04
20 | 2013-12-13 | 6 | WK15 | P4 | W3 | P4W3 | FY14 | FY14P04
21 | 2013-12-14 | 7 | WK15 | P4 | W3 | P4W3 | FY14 | FY14P04
22 | 2013-12-15 | 1 | WK16 | P4 | W4 | P4W4 | FY14 | FY14P04
23 | 2013-12-16 | 2 | WK16 | P4 | W4 | P4W4 | FY14 | FY14P04
24 | 2013-12-17 | 3 | WK16 | P4 | W4 | P4W4 | FY14 | FY14P04
25 | 2013-12-18 | 4 | WK16 | P4 | W4 | P4W4 | FY14 | FY14P04
26 | 2013-12-19 | 5 | WK16 | P4 | W4 | P4W4 | FY14 | FY14P04
27 | 2013-12-20 | 6 | WK16 | P4 | W4 | P4W4 | FY14 | FY14P04
28 | 2013-12-21 | 7 | WK16 | P4 | W4 | P4W4 | FY14 | FY14P04
1 | 2013-12-22 | 1 | WK17 | P5 | W1 | P5W1 | FY14 | FY14P05
2 | 2013-12-23 | 2 | WK17 | P5 | W1 | P5W1 | FY14 | FY14P05
3 | 2013-12-24 | 3 | WK17 | P5 | W1 | P5W1 | FY14 | FY14P05
4 | 2013-12-25 | 4 | WK17 | P5 | W1 | P5W1 | FY14 | FY14P05
5 | 2013-12-26 | 5 | WK17 | P5 | W1 | P5W1 | FY14 | FY14P05
6 | 2013-12-27 | 6 | WK17 | P5 | W1 | P5W1 | FY14 | FY14P05
7 | 2013-12-28 | 7 | WK17 | P5 | W1 | P5W1 | FY14 | FY14P05
8 | 2013-12-29 | 1 | WK18 | P5 | W2 | P5W2 | FY14 | FY14P05
9 | 2013-12-30 | 2 | WK18 | P5 | W2 | P5W2 | FY14 | FY14P05
10 | 2013-12-31 | 3 | WK18 | P5 | W2 | P5W2 | FY14 | FY14P05
11 | 2014-01-01 | 4 | WK18 | P5 | W2 | P5W2 | FY14 | FY14P05
12 | 2014-01-02 | 5 | WK18 | P5 | W2 | P5W2 | FY14 | FY14P05
13 | 2014-01-03 | 6 | WK18 | P5 | W2 | P5W2 | FY14 | FY14P05
14 | 2014-01-04 | 7 | WK18 | P5 | W2 | P5W2 | FY14 | FY14P05
15 | 2014-01-05 | 1 | WK19 | P5 | W3 | P5W3 | FY14 | FY14P05
16 | 2014-01-06 | 2 | WK19 | P5 | W3 | P5W3 | FY14 | FY14P05
17 | 2014-01-07 | 3 | WK19 | P5 | W3 | P5W3 | FY14 | FY14P05
18 | 2014-01-08 | 4 | WK19 | P5 | W3 | P5W3 | FY14 | FY14P05
19 | 2014-01-09 | 5 | WK19 | P5 | W3 | P5W3 | FY14 | FY14P05
20 | 2014-01-10 | 6 | WK19 | P5 | W3 | P5W3 | FY14 | FY14P05
21 | 2014-01-11 | 7 | WK19 | P5 | W3 | P5W3 | FY14 | FY14P05
22 | 2014-01-12 | 1 | WK20 | P5 | W4 | P5W4 | FY14 | FY14P05
23 | 2014-01-13 | 2 | WK20 | P5 | W4 | P5W4 | FY14 | FY14P05
24 | 2014-01-14 | 3 | WK20 | P5 | W4 | P5W4 | FY14 | FY14P05
25 | 2014-01-15 | 4 | WK20 | P5 | W4 | P5W4 | FY14 | FY14P05
26 | 2014-01-16 | 5 | WK20 | P5 | W4 | P5W4 | FY14 | FY14P05
27 | 2014-01-17 | 6 | WK20 | P5 | W4 | P5W4 | FY14 | FY14P05
28 | 2014-01-18 | 7 | WK20 | P5 | W4 | P5W4 | FY14 | FY14P05
1 | 2014-01-19 | 1 | WK21 | P6 | W1 | P6W1 | FY14 | FY14P06
2 | 2014-01-20 | 2 | WK21 | P6 | W1 | P6W1 | FY14 | FY14P06
3 | 2014-01-21 | 3 | WK21 | P6 | W1 | P6W1 | FY14 | FY14P06
4 | 2014-01-22 | 4 | WK21 | P6 | W1 | P6W1 | FY14 | FY14P06
5 | 2014-01-23 | 5 | WK21 | P6 | W1 | P6W1 | FY14 | FY14P06
6 | 2014-01-24 | 6 | WK21 | P6 | W1 | P6W1 | FY14 | FY14P06
7 | 2014-01-25 | 7 | WK21 | P6 | W1 | P6W1 | FY14 | FY14P06
8 | 2014-01-26 | 1 | WK22 | P6 | W2 | P6W2 | FY14 | FY14P06
9 | 2014-01-27 | 2 | WK22 | P6 | W2 | P6W2 | FY14 | FY14P06
10 | 2014-01-28 | 3 | WK22 | P6 | W2 | P6W2 | FY14 | FY14P06
11 | 2014-01-29 | 4 | WK22 | P6 | W2 | P6W2 | FY14 | FY14P06
12 | 2014-01-30 | 5 | WK22 | P6 | W2 | P6W2 | FY14 | FY14P06
13 | 2014-01-31 | 6 | WK22 | P6 | W2 | P6W2 | FY14 | FY14P06
14 | 2014-02-01 | 7 | WK22 | P6 | W2 | P6W2 | FY14 | FY14P06
15 | 2014-02-02 | 1 | WK23 | P6 | W3 | P6W3 | FY14 | FY14P06
16 | 2014-02-03 | 2 | WK23 | P6 | W3 | P6W3 | FY14 | FY14P06
17 | 2014-02-04 | 3 | WK23 | P6 | W3 | P6W3 | FY14 | FY14P06
18 | 2014-02-05 | 4 | WK23 | P6 | W3 | P6W3 | FY14 | FY14P06
19 | 2014-02-06 | 5 | WK23 | P6 | W3 | P6W3 | FY14 | FY14P06
20 | 2014-02-07 | 6 | WK23 | P6 | W3 | P6W3 | FY14 | FY14P06
21 | 2014-02-08 | 7 | WK23 | P6 | W3 | P6W3 | FY14 | FY14P06
22 | 2014-02-09 | 1 | WK24 | P6 | W4 | P6W4 | FY14 | FY14P06
23 | 2014-02-10 | 2 | WK24 | P6 | W4 | P6W4 | FY14 | FY14P06
24 | 2014-02-11 | 3 | WK24 | P6 | W4 | P6W4 | FY14 | FY14P06
25 | 2014-02-12 | 4 | WK24 | P6 | W4 | P6W4 | FY14 | FY14P06
26 | 2014-02-13 | 5 | WK24 | P6 | W4 | P6W4 | FY14 | FY14P06
27 | 2014-02-14 | 6 | WK24 | P6 | W4 | P6W4 | FY14 | FY14P06
28 | 2014-02-15 | 7 | WK24 | P6 | W4 | P6W4 | FY14 | FY14P06
1 | 2014-02-16 | 1 | WK25 | P7 | W1 | P7W1 | FY14 | FY14P07
2 | 2014-02-17 | 2 | WK25 | P7 | W1 | P7W1 | FY14 | FY14P07
3 | 2014-02-18 | 3 | WK25 | P7 | W1 | P7W1 | FY14 | FY14P07
4 | 2014-02-19 | 4 | WK25 | P7 | W1 | P7W1 | FY14 | FY14P07
5 | 2014-02-20 | 5 | WK25 | P7 | W1 | P7W1 | FY14 | FY14P07
6 | 2014-02-21 | 6 | WK25 | P7 | W1 | P7W1 | FY14 | FY14P07
7 | 2014-02-22 | 7 | WK25 | P7 | W1 | P7W1 | FY14 | FY14P07
8 | 2014-02-23 | 1 | WK26 | P7 | W2 | P7W2 | FY14 | FY14P07
9 | 2014-02-24 | 2 | WK26 | P7 | W2 | P7W2 | FY14 | FY14P07
10 | 2014-02-25 | 3 | WK26 | P7 | W2 | P7W2 | FY14 | FY14P07
11 | 2014-02-26 | 4 | WK26 | P7 | W2 | P7W2 | FY14 | FY14P07
12 | 2014-02-27 | 5 | WK26 | P7 | W2 | P7W2 | FY14 | FY14P07
13 | 2014-02-28 | 6 | WK26 | P7 | W2 | P7W2 | FY14 | FY14P07
14 | 2014-03-01 | 7 | WK26 | P7 | W2 | P7W2 | FY14 | FY14P07
15 | 2014-03-02 | 1 | WK27 | P7 | W3 | P7W3 | FY14 | FY14P07
16 | 2014-03-03 | 2 | WK27 | P7 | W3 | P7W3 | FY14 | FY14P07
17 | 2014-03-04 | 3 | WK27 | P7 | W3 | P7W3 | FY14 | FY14P07
18 | 2014-03-05 | 4 | WK27 | P7 | W3 | P7W3 | FY14 | FY14P07
19 | 2014-03-06 | 5 | WK27 | P7 | W3 | P7W3 | FY14 | FY14P07
20 | 2014-03-07 | 6 | WK27 | P7 | W3 | P7W3 | FY14 | FY14P07
21 | 2014-03-08 | 7 | WK27 | P7 | W3 | P7W3 | FY14 | FY14P07
22 | 2014-03-09 | 1 | WK28 | P7 | W4 | P7W4 | FY14 | FY14P07
23 | 2014-03-10 | 2 | WK28 | P7 | W4 | P7W4 | FY14 | FY14P07
24 | 2014-03-11 | 3 | WK28 | P7 | W4 | P7W4 | FY14 | FY14P07
25 | 2014-03-12 | 4 | WK28 | P7 | W4 | P7W4 | FY14 | FY14P07
26 | 2014-03-13 | 5 | WK28 | P7 | W4 | P7W4 | FY14 | FY14P07
27 | 2014-03-14 | 6 | WK28 | P7 | W4 | P7W4 | FY14 | FY14P07
28 | 2014-03-15 | 7 | WK28 | P7 | W4 | P7W4 | FY14 | FY14P07
1 | 2014-03-16 | 1 | WK29 | P8 | W1 | P8W1 | FY14 | FY14P08
2 | 2014-03-17 | 2 | WK29 | P8 | W1 | P8W1 | FY14 | FY14P08
3 | 2014-03-18 | 3 | WK29 | P8 | W1 | P8W1 | FY14 | FY14P08
4 | 2014-03-19 | 4 | WK29 | P8 | W1 | P8W1 | FY14 | FY14P08
5 | 2014-03-20 | 5 | WK29 | P8 | W1 | P8W1 | FY14 | FY14P08
6 | 2014-03-21 | 6 | WK29 | P8 | W1 | P8W1 | FY14 | FY14P08
7 | 2014-03-22 | 7 | WK29 | P8 | W1 | P8W1 | FY14 | FY14P08
8 | 2014-03-23 | 1 | WK30 | P8 | W2 | P8W2 | FY14 | FY14P08
9 | 2014-03-24 | 2 | WK30 | P8 | W2 | P8W2 | FY14 | FY14P08
10 | 2014-03-25 | 3 | WK30 | P8 | W2 | P8W2 | FY14 | FY14P08
11 | 2014-03-26 | 4 | WK30 | P8 | W2 | P8W2 | FY14 | FY14P08
12 | 2014-03-27 | 5 | WK30 | P8 | W2 | P8W2 | FY14 | FY14P08
13 | 2014-03-28 | 6 | WK30 | P8 | W2 | P8W2 | FY14 | FY14P08
14 | 2014-03-29 | 7 | WK30 | P8 | W2 | P8W2 | FY14 | FY14P08
15 | 2014-03-30 | 1 | WK31 | P8 | W3 | P8W3 | FY14 | FY14P08
16 | 2014-03-31 | 2 | WK31 | P8 | W3 | P8W3 | FY14 | FY14P08
17 | 2014-04-01 | 3 | WK31 | P8 | W3 | P8W3 | FY14 | FY14P08
18 | 2014-04-02 | 4 | WK31 | P8 | W3 | P8W3 | FY14 | FY14P08
19 | 2014-04-03 | 5 | WK31 | P8 | W3 | P8W3 | FY14 | FY14P08
20 | 2014-04-04 | 6 | WK31 | P8 | W3 | P8W3 | FY14 | FY14P08
21 | 2014-04-05 | 7 | WK31 | P8 | W3 | P8W3 | FY14 | FY14P08
22 | 2014-04-06 | 1 | WK32 | P8 | W4 | P8W4 | FY14 | FY14P08
23 | 2014-04-07 | 2 | WK32 | P8 | W4 | P8W4 | FY14 | FY14P08
24 | 2014-04-08 | 3 | WK32 | P8 | W4 | P8W4 | FY14 | FY14P08
25 | 2014-04-09 | 4 | WK32 | P8 | W4 | P8W4 | FY14 | FY14P08
26 | 2014-04-10 | 5 | WK32 | P8 | W4 | P8W4 | FY14 | FY14P08
27 | 2014-04-11 | 6 | WK32 | P8 | W4 | P8W4 | FY14 | FY14P08
28 | 2014-04-12 | 7 | WK32 | P8 | W4 | P8W4 | FY14 | FY14P08
1 | 2014-04-13 | 1 | WK33 | P9 | W1 | P9W1 | FY14 | FY14P09
2 | 2014-04-14 | 2 | WK33 | P9 | W1 | P9W1 | FY14 | FY14P09
3 | 2014-04-15 | 3 | WK33 | P9 | W1 | P9W1 | FY14 | FY14P09
4 | 2014-04-16 | 4 | WK33 | P9 | W1 | P9W1 | FY14 | FY14P09
5 | 2014-04-17 | 5 | WK33 | P9 | W1 | P9W1 | FY14 | FY14P09
6 | 2014-04-18 | 6 | WK33 | P9 | W1 | P9W1 | FY14 | FY14P09
7 | 2014-04-19 | 7 | WK33 | P9 | W1 | P9W1 | FY14 | FY14P09
8 | 2014-04-20 | 1 | WK34 | P9 | W2 | P9W2 | FY14 | FY14P09
9 | 2014-04-21 | 2 | WK34 | P9 | W2 | P9W2 | FY14 | FY14P09
10 | 2014-04-22 | 3 | WK34 | P9 | W2 | P9W2 | FY14 | FY14P09
11 | 2014-04-23 | 4 | WK34 | P9 | W2 | P9W2 | FY14 | FY14P09
12 | 2014-04-24 | 5 | WK34 | P9 | W2 | P9W2 | FY14 | FY14P09
13 | 2014-04-25 | 6 | WK34 | P9 | W2 | P9W2 | FY14 | FY14P09
14 | 2014-04-26 | 7 | WK34 | P9 | W2 | P9W2 | FY14 | FY14P09
15 | 2014-04-27 | 1 | WK35 | P9 | W3 | P9W3 | FY14 | FY14P09
16 | 2014-04-28 | 2 | WK35 | P9 | W3 | P9W3 | FY14 | FY14P09
17 | 2014-04-29 | 3 | WK35 | P9 | W3 | P9W3 | FY14 | FY14P09
18 | 2014-04-30 | 4 | WK35 | P9 | W3 | P9W3 | FY14 | FY14P09
19 | 2014-05-01 | 5 | WK35 | P9 | W3 | P9W3 | FY14 | FY14P09
20 | 2014-05-02 | 6 | WK35 | P9 | W3 | P9W3 | FY14 | FY14P09
21 | 2014-05-03 | 7 | WK35 | P9 | W3 | P9W3 | FY14 | FY14P09
22 | 2014-05-04 | 1 | WK36 | P9 | W4 | P9W4 | FY14 | FY14P09
23 | 2014-05-05 | 2 | WK36 | P9 | W4 | P9W4 | FY14 | FY14P09
24 | 2014-05-06 | 3 | WK36 | P9 | W4 | P9W4 | FY14 | FY14P09
25 | 2014-05-07 | 4 | WK36 | P9 | W4 | P9W4 | FY14 | FY14P09
26 | 2014-05-08 | 5 | WK36 | P9 | W4 | P9W4 | FY14 | FY14P09
27 | 2014-05-09 | 6 | WK36 | P9 | W4 | P9W4 | FY14 | FY14P09
28 | 2014-05-10 | 7 | WK36 | P9 | W4 | P9W4 | FY14 | FY14P09
1 | 2014-05-11 | 1 | WK37 | P10 | W1 | P10W1 | FY14 | FY14P10
2 | 2014-05-12 | 2 | WK37 | P10 | W1 | P10W1 | FY14 | FY14P10
3 | 2014-05-13 | 3 | WK37 | P10 | W1 | P10W1 | FY14 | FY14P10
4 | 2014-05-14 | 4 | WK37 | P10 | W1 | P10W1 | FY14 | FY14P10
5 | 2014-05-15 | 5 | WK37 | P10 | W1 | P10W1 | FY14 | FY14P10
6 | 2014-05-16 | 6 | WK37 | P10 | W1 | P10W1 | FY14 | FY14P10
7 | 2014-05-17 | 7 | WK37 | P10 | W1 | P10W1 | FY14 | FY14P10
8 | 2014-05-18 | 1 | WK38 | P10 | W2 | P10W2 | FY14 | FY14P10
9 | 2014-05-19 | 2 | WK38 | P10 | W2 | P10W2 | FY14 | FY14P10
10 | 2014-05-20 | 3 | WK38 | P10 | W2 | P10W2 | FY14 | FY14P10
11 | 2014-05-21 | 4 | WK38 | P10 | W2 | P10W2 | FY14 | FY14P10
12 | 2014-05-22 | 5 | WK38 | P10 | W2 | P10W2 | FY14 | FY14P10
13 | 2014-05-23 | 6 | WK38 | P10 | W2 | P10W2 | FY14 | FY14P10
14 | 2014-05-24 | 7 | WK38 | P10 | W2 | P10W2 | FY14 | FY14P10
15 | 2014-05-25 | 1 | WK39 | P10 | W3 | P10W3 | FY14 | FY14P10
16 | 2014-05-26 | 2 | WK39 | P10 | W3 | P10W3 | FY14 | FY14P10
17 | 2014-05-27 | 3 | WK39 | P10 | W3 | P10W3 | FY14 | FY14P10
18 | 2014-05-28 | 4 | WK39 | P10 | W3 | P10W3 | FY14 | FY14P10
19 | 2014-05-29 | 5 | WK39 | P10 | W3 | P10W3 | FY14 | FY14P10
20 | 2014-05-30 | 6 | WK39 | P10 | W3 | P10W3 | FY14 | FY14P10
21 | 2014-05-31 | 7 | WK39 | P10 | W3 | P10W3 | FY14 | FY14P10
22 | 2014-06-01 | 1 | WK40 | P10 | W4 | P10W4 | FY14 | FY14P10
23 | 2014-06-02 | 2 | WK40 | P10 | W4 | P10W4 | FY14 | FY14P10
24 | 2014-06-03 | 3 | WK40 | P10 | W4 | P10W4 | FY14 | FY14P10
25 | 2014-06-04 | 4 | WK40 | P10 | W4 | P10W4 | FY14 | FY14P10
26 | 2014-06-05 | 5 | WK40 | P10 | W4 | P10W4 | FY14 | FY14P10
27 | 2014-06-06 | 6 | WK40 | P10 | W4 | P10W4 | FY14 | FY14P10
28 | 2014-06-07 | 7 | WK40 | P10 | W4 | P10W4 | FY14 | FY14P10
1 | 2014-06-08 | 1 | WK41 | P11 | W1 | P11W1 | FY14 | FY14P11
2 | 2014-06-09 | 2 | WK41 | P11 | W1 | P11W1 | FY14 | FY14P11
3 | 2014-06-10 | 3 | WK41 | P11 | W1 | P11W1 | FY14 | FY14P11
4 | 2014-06-11 | 4 | WK41 | P11 | W1 | P11W1 | FY14 | FY14P11
5 | 2014-06-12 | 5 | WK41 | P11 | W1 | P11W1 | FY14 | FY14P11
6 | 2014-06-13 | 6 | WK41 | P11 | W1 | P11W1 | FY14 | FY14P11
7 | 2014-06-14 | 7 | WK41 | P11 | W1 | P11W1 | FY14 | FY14P11
8 | 2014-06-15 | 1 | WK42 | P11 | W2 | P11W2 | FY14 | FY14P11
9 | 2014-06-16 | 2 | WK42 | P11 | W2 | P11W2 | FY14 | FY14P11
10 | 2014-06-17 | 3 | WK42 | P11 | W2 | P11W2 | FY14 | FY14P11
11 | 2014-06-18 | 4 | WK42 | P11 | W2 | P11W2 | FY14 | FY14P11
12 | 2014-06-19 | 5 | WK42 | P11 | W2 | P11W2 | FY14 | FY14P11
13 | 2014-06-20 | 6 | WK42 | P11 | W2 | P11W2 | FY14 | FY14P11
14 | 2014-06-21 | 7 | WK42 | P11 | W2 | P11W2 | FY14 | FY14P11
15 | 2014-06-22 | 1 | WK43 | P11 | W3 | P11W3 | FY14 | FY14P11
16 | 2014-06-23 | 2 | WK43 | P11 | W3 | P11W3 | FY14 | FY14P11
17 | 2014-06-24 | 3 | WK43 | P11 | W3 | P11W3 | FY14 | FY14P11
18 | 2014-06-25 | 4 | WK43 | P11 | W3 | P11W3 | FY14 | FY14P11
19 | 2014-06-26 | 5 | WK43 | P11 | W3 | P11W3 | FY14 | FY14P11
20 | 2014-06-27 | 6 | WK43 | P11 | W3 | P11W3 | FY14 | FY14P11
21 | 2014-06-28 | 7 | WK43 | P11 | W3 | P11W3 | FY14 | FY14P11
22 | 2014-06-29 | 1 | WK44 | P11 | W4 | P11W4 | FY14 | FY14P11
23 | 2014-06-30 | 2 | WK44 | P11 | W4 | P11W4 | FY14 | FY14P11
24 | 2014-07-01 | 3 | WK44 | P11 | W4 | P11W4 | FY14 | FY14P11
25 | 2014-07-02 | 4 | WK44 | P11 | W4 | P11W4 | FY14 | FY14P11
26 | 2014-07-03 | 5 | WK44 | P11 | W4 | P11W4 | FY14 | FY14P11
27 | 2014-07-04 | 6 | WK44 | P11 | W4 | P11W4 | FY14 | FY14P11
28 | 2014-07-05 | 7 | WK44 | P11 | W4 | P11W4 | FY14 | FY14P11
1 | 2014-07-06 | 1 | WK45 | P12 | W1 | P12W1 | FY14 | FY14P12
2 | 2014-07-07 | 2 | WK45 | P12 | W1 | P12W1 | FY14 | FY14P12
3 | 2014-07-08 | 3 | WK45 | P12 | W1 | P12W1 | FY14 | FY14P12
4 | 2014-07-09 | 4 | WK45 | P12 | W1 | P12W1 | FY14 | FY14P12
5 | 2014-07-10 | 5 | WK45 | P12 | W1 | P12W1 | FY14 | FY14P12
6 | 2014-07-11 | 6 | WK45 | P12 | W1 | P12W1 | FY14 | FY14P12
7 | 2014-07-12 | 7 | WK45 | P12 | W1 | P12W1 | FY14 | FY14P12
8 | 2014-07-13 | 1 | WK46 | P12 | W2 | P12W2 | FY14 | FY14P12
9 | 2014-07-14 | 2 | WK46 | P12 | W2 | P12W2 | FY14 | FY14P12
10 | 2014-07-15 | 3 | WK46 | P12 | W2 | P12W2 | FY14 | FY14P12
11 | 2014-07-16 | 4 | WK46 | P12 | W2 | P12W2 | FY14 | FY14P12
12 | 2014-07-17 | 5 | WK46 | P12 | W2 | P12W2 | FY14 | FY14P12
13 | 2014-07-18 | 6 | WK46 | P12 | W2 | P12W2 | FY14 | FY14P12
14 | 2014-07-19 | 7 | WK46 | P12 | W2 | P12W2 | FY14 | FY14P12
15 | 2014-07-20 | 1 | WK47 | P12 | W3 | P12W3 | FY14 | FY14P12
16 | 2014-07-21 | 2 | WK47 | P12 | W3 | P12W3 | FY14 | FY14P12
17 | 2014-07-22 | 3 | WK47 | P12 | W3 | P12W3 | FY14 | FY14P12
18 | 2014-07-23 | 4 | WK47 | P12 | W3 | P12W3 | FY14 | FY14P12
19 | 2014-07-24 | 5 | WK47 | P12 | W3 | P12W3 | FY14 | FY14P12
20 | 2014-07-25 | 6 | WK47 | P12 | W3 | P12W3 | FY14 | FY14P12
21 | 2014-07-26 | 7 | WK47 | P12 | W3 | P12W3 | FY14 | FY14P12
22 | 2014-07-27 | 1 | WK48 | P12 | W4 | P12W4 | FY14 | FY14P12
23 | 2014-07-28 | 2 | WK48 | P12 | W4 | P12W4 | FY14 | FY14P12
24 | 2014-07-29 | 3 | WK48 | P12 | W4 | P12W4 | FY14 | FY14P12
25 | 2014-07-30 | 4 | WK48 | P12 | W4 | P12W4 | FY14 | FY14P12
26 | 2014-07-31 | 5 | WK48 | P12 | W4 | P12W4 | FY14 | FY14P12
27 | 2014-08-01 | 6 | WK48 | P12 | W4 | P12W4 | FY14 | FY14P12
28 | 2014-08-02 | 7 | WK48 | P12 | W4 | P12W4 | FY14 | FY14P12
1 | 2014-08-03 | 1 | WK49 | P13 | W1 | P13W1 | FY14 | FY14P13
2 | 2014-08-04 | 2 | WK49 | P13 | W1 | P13W1 | FY14 | FY14P13
3 | 2014-08-05 | 3 | WK49 | P13 | W1 | P13W1 | FY14 | FY14P13
4 | 2014-08-06 | 4 | WK49 | P13 | W1 | P13W1 | FY14 | FY14P13
5 | 2014-08-07 | 5 | WK49 | P13 | W1 | P13W1 | FY14 | FY14P13
6 | 2014-08-08 | 6 | WK49 | P13 | W1 | P13W1 | FY14 | FY14P13
7 | 2014-08-09 | 7 | WK49 | P13 | W1 | P13W1 | FY14 | FY14P13
8 | 2014-08-10 | 1 | WK50 | P13 | W2 | P13W2 | FY14 | FY14P13
9 | 2014-08-11 | 2 | WK50 | P13 | W2 | P13W2 | FY14 | FY14P13
10 | 2014-08-12 | 3 | WK50 | P13 | W2 | P13W2 | FY14 | FY14P13
11 | 2014-08-13 | 4 | WK50 | P13 | W2 | P13W2 | FY14 | FY14P13
12 | 2014-08-14 | 5 | WK50 | P13 | W2 | P13W2 | FY14 | FY14P13
13 | 2014-08-15 | 6 | WK50 | P13 | W2 | P13W2 | FY14 | FY14P13
14 | 2014-08-16 | 7 | WK50 | P13 | W2 | P13W2 | FY14 | FY14P13
15 | 2014-08-17 | 1 | WK51 | P13 | W3 | P13W3 | FY14 | FY14P13
16 | 2014-08-18 | 2 | WK51 | P13 | W3 | P13W3 | FY14 | FY14P13
17 | 2014-08-19 | 3 | WK51 | P13 | W3 | P13W3 | FY14 | FY14P13
18 | 2014-08-20 | 4 | WK51 | P13 | W3 | P13W3 | FY14 | FY14P13
19 | 2014-08-21 | 5 | WK51 | P13 | W3 | P13W3 | FY14 | FY14P13
20 | 2014-08-22 | 6 | WK51 | P13 | W3 | P13W3 | FY14 | FY14P13
21 | 2014-08-23 | 7 | WK51 | P13 | W3 | P13W3 | FY14 | FY14P13
22 | 2014-08-24 | 1 | WK52 | P13 | W4 | P13W4 | FY14 | FY14P13
23 | 2014-08-25 | 2 | WK52 | P13 | W4 | P13W4 | FY14 | FY14P13
24 | 2014-08-26 | 3 | WK52 | P13 | W4 | P13W4 | FY14 | FY14P13
25 | 2014-08-27 | 4 | WK52 | P13 | W4 | P13W4 | FY14 | FY14P13
26 | 2014-08-28 | 5 | WK52 | P13 | W4 | P13W4 | FY14 | FY14P13
27 | 2014-08-29 | 6 | WK52 | P13 | W4 | P13W4 | FY14 | FY14P13
28 | 2014-08-30 | 7 | WK52 | P13 | W4 | P13W4 | FY14 | FY14P13
1 | 2014-08-31 | 1 | WK1 | P1 | W1 | P1W1 | FY15 | FY15P01
2 | 2014-09-01 | 2 | WK1 | P1 | W1 | P1W1 | FY15 | FY15P01
3 | 2014-09-02 | 3 | WK1 | P1 | W1 | P1W1 | FY15 | FY15P01
4 | 2014-09-03 | 4 | WK1 | P1 | W1 | P1W1 | FY15 | FY15P01
5 | 2014-09-04 | 5 | WK1 | P1 | W1 | P1W1 | FY15 | FY15P01
6 | 2014-09-05 | 6 | WK1 | P1 | W1 | P1W1 | FY15 | FY15P01
7 | 2014-09-06 | 7 | WK1 | P1 | W1 | P1W1 | FY15 | FY15P01
8 | 2014-09-07 | 1 | WK2 | P1 | W2 | P1W2 | FY15 | FY15P01
9 | 2014-09-08 | 2 | WK2 | P1 | W2 | P1W2 | FY15 | FY15P01
10 | 2014-09-09 | 3 | WK2 | P1 | W2 | P1W2 | FY15 | FY15P01
11 | 2014-09-10 | 4 | WK2 | P1 | W2 | P1W2 | FY15 | FY15P01
12 | 2014-09-11 | 5 | WK2 | P1 | W2 | P1W2 | FY15 | FY15P01
13 | 2014-09-12 | 6 | WK2 | P1 | W2 | P1W2 | FY15 | FY15P01
14 | 2014-09-13 | 7 | WK2 | P1 | W2 | P1W2 | FY15 | FY15P01
15 | 2014-09-14 | 1 | WK3 | P1 | W3 | P1W3 | FY15 | FY15P01
16 | 2014-09-15 | 2 | WK3 | P1 | W3 | P1W3 | FY15 | FY15P01
17 | 2014-09-16 | 3 | WK3 | P1 | W3 | P1W3 | FY15 | FY15P01
18 | 2014-09-17 | 4 | WK3 | P1 | W3 | P1W3 | FY15 | FY15P01
19 | 2014-09-18 | 5 | WK3 | P1 | W3 | P1W3 | FY15 | FY15P01
20 | 2014-09-19 | 6 | WK3 | P1 | W3 | P1W3 | FY15 | FY15P01
21 | 2014-09-20 | 7 | WK3 | P1 | W3 | P1W3 | FY15 | FY15P01
22 | 2014-09-21 | 1 | WK4 | P1 | W4 | P1W4 | FY15 | FY15P01
23 | 2014-09-22 | 2 | WK4 | P1 | W4 | P1W4 | FY15 | FY15P01
24 | 2014-09-23 | 3 | WK4 | P1 | W4 | P1W4 | FY15 | FY15P01
25 | 2014-09-24 | 4 | WK4 | P1 | W4 | P1W4 | FY15 | FY15P01
26 | 2014-09-25 | 5 | WK4 | P1 | W4 | P1W4 | FY15 | FY15P01
27 | 2014-09-26 | 6 | WK4 | P1 | W4 | P1W4 | FY15 | FY15P01
28 | 2014-09-27 | 7 | WK4 | P1 | W4 | P1W4 | FY15 | FY15P01
1 | 2014-09-28 | 1 | WK5 | P2 | W1 | P2W1 | FY15 | FY15P02
2 | 2014-09-29 | 2 | WK5 | P2 | W1 | P2W1 | FY15 | FY15P02
3 | 2014-09-30 | 3 | WK5 | P2 | W1 | P2W1 | FY15 | FY15P02
4 | 2014-10-01 | 4 | WK5 | P2 | W1 | P2W1 | FY15 | FY15P02
5 | 2014-10-02 | 5 | WK5 | P2 | W1 | P2W1 | FY15 | FY15P02
6 | 2014-10-03 | 6 | WK5 | P2 | W1 | P2W1 | FY15 | FY15P02
7 | 2014-10-04 | 7 | WK5 | P2 | W1 | P2W1 | FY15 | FY15P02
8 | 2014-10-05 | 1 | WK6 | P2 | W2 | P2W2 | FY15 | FY15P02
9 | 2014-10-06 | 2 | WK6 | P2 | W2 | P2W2 | FY15 | FY15P02
10 | 2014-10-07 | 3 | WK6 | P2 | W2 | P2W2 | FY15 | FY15P02
11 | 2014-10-08 | 4 | WK6 | P2 | W2 | P2W2 | FY15 | FY15P02
12 | 2014-10-09 | 5 | WK6 | P2 | W2 | P2W2 | FY15 | FY15P02
13 | 2014-10-10 | 6 | WK6 | P2 | W2 | P2W2 | FY15 | FY15P02
14 | 2014-10-11 | 7 | WK6 | P2 | W2 | P2W2 | FY15 | FY15P02
15 | 2014-10-12 | 1 | WK7 | P2 | W3 | P2W3 | FY15 | FY15P02
16 | 2014-10-13 | 2 | WK7 | P2 | W3 | P2W3 | FY15 | FY15P02
17 | 2014-10-14 | 3 | WK7 | P2 | W3 | P2W3 | FY15 | FY15P02
18 | 2014-10-15 | 4 | WK7 | P2 | W3 | P2W3 | FY15 | FY15P02
19 | 2014-10-16 | 5 | WK7 | P2 | W3 | P2W3 | FY15 | FY15P02
20 | 2014-10-17 | 6 | WK7 | P2 | W3 | P2W3 | FY15 | FY15P02
21 | 2014-10-18 | 7 | WK7 | P2 | W3 | P2W3 | FY15 | FY15P02
22 | 2014-10-19 | 1 | WK8 | P2 | W4 | P2W4 | FY15 | FY15P02
23 | 2014-10-20 | 2 | WK8 | P2 | W4 | P2W4 | FY15 | FY15P02
24 | 2014-10-21 | 3 | WK8 | P2 | W4 | P2W4 | FY15 | FY15P02
25 | 2014-10-22 | 4 | WK8 | P2 | W4 | P2W4 | FY15 | FY15P02
26 | 2014-10-23 | 5 | WK8 | P2 | W4 | P2W4 | FY15 | FY15P02
27 | 2014-10-24 | 6 | WK8 | P2 | W4 | P2W4 | FY15 | FY15P02
28 | 2014-10-25 | 7 | WK8 | P2 | W4 | P2W4 | FY15 | FY15P02
1 | 2014-10-26 | 1 | WK9 | P3 | W1 | P3W1 | FY15 | FY15P03
2 | 2014-10-27 | 2 | WK9 | P3 | W1 | P3W1 | FY15 | FY15P03
3 | 2014-10-28 | 3 | WK9 | P3 | W1 | P3W1 | FY15 | FY15P03
4 | 2014-10-29 | 4 | WK9 | P3 | W1 | P3W1 | FY15 | FY15P03
5 | 2014-10-30 | 5 | WK9 | P3 | W1 | P3W1 | FY15 | FY15P03
6 | 2014-10-31 | 6 | WK9 | P3 | W1 | P3W1 | FY15 | FY15P03
7 | 2014-11-01 | 7 | WK9 | P3 | W1 | P3W1 | FY15 | FY15P03
8 | 2014-11-02 | 1 | WK10 | P3 | W2 | P3W2 | FY15 | FY15P03
9 | 2014-11-03 | 2 | WK10 | P3 | W2 | P3W2 | FY15 | FY15P03
10 | 2014-11-04 | 3 | WK10 | P3 | W2 | P3W2 | FY15 | FY15P03
11 | 2014-11-05 | 4 | WK10 | P3 | W2 | P3W2 | FY15 | FY15P03
12 | 2014-11-06 | 5 | WK10 | P3 | W2 | P3W2 | FY15 | FY15P03
13 | 2014-11-07 | 6 | WK10 | P3 | W2 | P3W2 | FY15 | FY15P03
14 | 2014-11-08 | 7 | WK10 | P3 | W2 | P3W2 | FY15 | FY15P03
15 | 2014-11-09 | 1 | WK11 | P3 | W3 | P3W3 | FY15 | FY15P03
16 | 2014-11-10 | 2 | WK11 | P3 | W3 | P3W3 | FY15 | FY15P03
17 | 2014-11-11 | 3 | WK11 | P3 | W3 | P3W3 | FY15 | FY15P03
18 | 2014-11-12 | 4 | WK11 | P3 | W3 | P3W3 | FY15 | FY15P03
19 | 2014-11-13 | 5 | WK11 | P3 | W3 | P3W3 | FY15 | FY15P03
20 | 2014-11-14 | 6 | WK11 | P3 | W3 | P3W3 | FY15 | FY15P03
21 | 2014-11-15 | 7 | WK11 | P3 | W3 | P3W3 | FY15 | FY15P03
22 | 2014-11-16 | 1 | WK12 | P3 | W4 | P3W4 | FY15 | FY15P03
23 | 2014-11-17 | 2 | WK12 | P3 | W4 | P3W4 | FY15 | FY15P03
24 | 2014-11-18 | 3 | WK12 | P3 | W4 | P3W4 | FY15 | FY15P03
25 | 2014-11-19 | 4 | WK12 | P3 | W4 | P3W4 | FY15 | FY15P03
26 | 2014-11-20 | 5 | WK12 | P3 | W4 | P3W4 | FY15 | FY15P03
27 | 2014-11-21 | 6 | WK12 | P3 | W4 | P3W4 | FY15 | FY15P03
28 | 2014-11-22 | 7 | WK12 | P3 | W4 | P3W4 | FY15 | FY15P03
1 | 2014-11-23 | 1 | WK13 | P4 | W1 | P4W1 | FY15 | FY15P04
2 | 2014-11-24 | 2 | WK13 | P4 | W1 | P4W1 | FY15 | FY15P04
3 | 2014-11-25 | 3 | WK13 | P4 | W1 | P4W1 | FY15 | FY15P04
4 | 2014-11-26 | 4 | WK13 | P4 | W1 | P4W1 | FY15 | FY15P04
5 | 2014-11-27 | 5 | WK13 | P4 | W1 | P4W1 | FY15 | FY15P04
6 | 2014-11-28 | 6 | WK13 | P4 | W1 | P4W1 | FY15 | FY15P04
7 | 2014-11-29 | 7 | WK13 | P4 | W1 | P4W1 | FY15 | FY15P04
8 | 2014-11-30 | 1 | WK14 | P4 | W2 | P4W2 | FY15 | FY15P04
9 | 2014-12-01 | 2 | WK14 | P4 | W2 | P4W2 | FY15 | FY15P04
10 | 2014-12-02 | 3 | WK14 | P4 | W2 | P4W2 | FY15 | FY15P04
11 | 2014-12-03 | 4 | WK14 | P4 | W2 | P4W2 | FY15 | FY15P04
12 | 2014-12-04 | 5 | WK14 | P4 | W2 | P4W2 | FY15 | FY15P04
13 | 2014-12-05 | 6 | WK14 | P4 | W2 | P4W2 | FY15 | FY15P04
14 | 2014-12-06 | 7 | WK14 | P4 | W2 | P4W2 | FY15 | FY15P04
15 | 2014-12-07 | 1 | WK15 | P4 | W3 | P4W3 | FY15 | FY15P04
16 | 2014-12-08 | 2 | WK15 | P4 | W3 | P4W3 | FY15 | FY15P04
17 | 2014-12-09 | 3 | WK15 | P4 | W3 | P4W3 | FY15 | FY15P04
18 | 2014-12-10 | 4 | WK15 | P4 | W3 | P4W3 | FY15 | FY15P04
19 | 2014-12-11 | 5 | WK15 | P4 | W3 | P4W3 | FY15 | FY15P04
20 | 2014-12-12 | 6 | WK15 | P4 | W3 | P4W3 | FY15 | FY15P04
21 | 2014-12-13 | 7 | WK15 | P4 | W3 | P4W3 | FY15 | FY15P04
22 | 2014-12-14 | 1 | WK16 | P4 | W4 | P4W4 | FY15 | FY15P04
23 | 2014-12-15 | 2 | WK16 | P4 | W4 | P4W4 | FY15 | FY15P04
24 | 2014-12-16 | 3 | WK16 | P4 | W4 | P4W4 | FY15 | FY15P04
25 | 2014-12-17 | 4 | WK16 | P4 | W4 | P4W4 | FY15 | FY15P04
26 | 2014-12-18 | 5 | WK16 | P4 | W4 | P4W4 | FY15 | FY15P04
27 | 2014-12-19 | 6 | WK16 | P4 | W4 | P4W4 | FY15 | FY15P04
28 | 2014-12-20 | 7 | WK16 | P4 | W4 | P4W4 | FY15 | FY15P04
1 | 2014-12-21 | 1 | WK17 | P5 | W1 | P5W1 | FY15 | FY15P05
2 | 2014-12-22 | 2 | WK17 | P5 | W1 | P5W1 | FY15 | FY15P05
3 | 2014-12-23 | 3 | WK17 | P5 | W1 | P5W1 | FY15 | FY15P05
4 | 2014-12-24 | 4 | WK17 | P5 | W1 | P5W1 | FY15 | FY15P05
5 | 2014-12-25 | 5 | WK17 | P5 | W1 | P5W1 | FY15 | FY15P05
6 | 2014-12-26 | 6 | WK17 | P5 | W1 | P5W1 | FY15 | FY15P05
7 | 2014-12-27 | 7 | WK17 | P5 | W1 | P5W1 | FY15 | FY15P05
8 | 2014-12-28 | 1 | WK18 | P5 | W2 | P5W2 | FY15 | FY15P05
9 | 2014-12-29 | 2 | WK18 | P5 | W2 | P5W2 | FY15 | FY15P05
10 | 2014-12-30 | 3 | WK18 | P5 | W2 | P5W2 | FY15 | FY15P05
11 | 2014-12-31 | 4 | WK18 | P5 | W2 | P5W2 | FY15 | FY15P05
12 | 2015-01-01 | 5 | WK18 | P5 | W2 | P5W2 | FY15 | FY15P05
13 | 2015-01-02 | 6 | WK18 | P5 | W2 | P5W2 | FY15 | FY15P05
14 | 2015-01-03 | 7 | WK18 | P5 | W2 | P5W2 | FY15 | FY15P05
15 | 2015-01-04 | 1 | WK19 | P5 | W3 | P5W3 | FY15 | FY15P05
16 | 2015-01-05 | 2 | WK19 | P5 | W3 | P5W3 | FY15 | FY15P05
17 | 2015-01-06 | 3 | WK19 | P5 | W3 | P5W3 | FY15 | FY15P05
18 | 2015-01-07 | 4 | WK19 | P5 | W3 | P5W3 | FY15 | FY15P05
19 | 2015-01-08 | 5 | WK19 | P5 | W3 | P5W3 | FY15 | FY15P05
20 | 2015-01-09 | 6 | WK19 | P5 | W3 | P5W3 | FY15 | FY15P05
21 | 2015-01-10 | 7 | WK19 | P5 | W3 | P5W3 | FY15 | FY15P05
22 | 2015-01-11 | 1 | WK20 | P5 | W4 | P5W4 | FY15 | FY15P05
23 | 2015-01-12 | 2 | WK20 | P5 | W4 | P5W4 | FY15 | FY15P05
24 | 2015-01-13 | 3 | WK20 | P5 | W4 | P5W4 | FY15 | FY15P05
25 | 2015-01-14 | 4 | WK20 | P5 | W4 | P5W4 | FY15 | FY15P05
26 | 2015-01-15 | 5 | WK20 | P5 | W4 | P5W4 | FY15 | FY15P05
27 | 2015-01-16 | 6 | WK20 | P5 | W4 | P5W4 | FY15 | FY15P05
28 | 2015-01-17 | 7 | WK20 | P5 | W4 | P5W4 | FY15 | FY15P05
1 | 2015-01-18 | 1 | WK21 | P6 | W1 | P6W1 | FY15 | FY15P06
2 | 2015-01-19 | 2 | WK21 | P6 | W1 | P6W1 | FY15 | FY15P06
3 | 2015-01-20 | 3 | WK21 | P6 | W1 | P6W1 | FY15 | FY15P06
4 | 2015-01-21 | 4 | WK21 | P6 | W1 | P6W1 | FY15 | FY15P06
5 | 2015-01-22 | 5 | WK21 | P6 | W1 | P6W1 | FY15 | FY15P06
6 | 2015-01-23 | 6 | WK21 | P6 | W1 | P6W1 | FY15 | FY15P06
7 | 2015-01-24 | 7 | WK21 | P6 | W1 | P6W1 | FY15 | FY15P06
8 | 2015-01-25 | 1 | WK22 | P6 | W2 | P6W2 | FY15 | FY15P06
9 | 2015-01-26 | 2 | WK22 | P6 | W2 | P6W2 | FY15 | FY15P06
10 | 2015-01-27 | 3 | WK22 | P6 | W2 | P6W2 | FY15 | FY15P06
11 | 2015-01-28 | 4 | WK22 | P6 | W2 | P6W2 | FY15 | FY15P06
12 | 2015-01-29 | 5 | WK22 | P6 | W2 | P6W2 | FY15 | FY15P06
13 | 2015-01-30 | 6 | WK22 | P6 | W2 | P6W2 | FY15 | FY15P06
14 | 2015-01-31 | 7 | WK22 | P6 | W2 | P6W2 | FY15 | FY15P06
15 | 2015-02-01 | 1 | WK23 | P6 | W3 | P6W3 | FY15 | FY15P06
16 | 2015-02-02 | 2 | WK23 | P6 | W3 | P6W3 | FY15 | FY15P06
17 | 2015-02-03 | 3 | WK23 | P6 | W3 | P6W3 | FY15 | FY15P06
18 | 2015-02-04 | 4 | WK23 | P6 | W3 | P6W3 | FY15 | FY15P06
19 | 2015-02-05 | 5 | WK23 | P6 | W3 | P6W3 | FY15 | FY15P06
20 | 2015-02-06 | 6 | WK23 | P6 | W3 | P6W3 | FY15 | FY15P06
21 | 2015-02-07 | 7 | WK23 | P6 | W3 | P6W3 | FY15 | FY15P06
22 | 2015-02-08 | 1 | WK24 | P6 | W4 | P6W4 | FY15 | FY15P06
23 | 2015-02-09 | 2 | WK24 | P6 | W4 | P6W4 | FY15 | FY15P06
24 | 2015-02-10 | 3 | WK24 | P6 | W4 | P6W4 | FY15 | FY15P06
25 | 2015-02-11 | 4 | WK24 | P6 | W4 | P6W4 | FY15 | FY15P06
26 | 2015-02-12 | 5 | WK24 | P6 | W4 | P6W4 | FY15 | FY15P06
27 | 2015-02-13 | 6 | WK24 | P6 | W4 | P6W4 | FY15 | FY15P06
28 | 2015-02-14 | 7 | WK24 | P6 | W4 | P6W4 | FY15 | FY15P06
1 | 2015-02-15 | 1 | WK25 | P7 | W1 | P7W1 | FY15 | FY15P07
2 | 2015-02-16 | 2 | WK25 | P7 | W1 | P7W1 | FY15 | FY15P07
3 | 2015-02-17 | 3 | WK25 | P7 | W1 | P7W1 | FY15 | FY15P07
4 | 2015-02-18 | 4 | WK25 | P7 | W1 | P7W1 | FY15 | FY15P07
5 | 2015-02-19 | 5 | WK25 | P7 | W1 | P7W1 | FY15 | FY15P07
6 | 2015-02-20 | 6 | WK25 | P7 | W1 | P7W1 | FY15 | FY15P07
7 | 2015-02-21 | 7 | WK25 | P7 | W1 | P7W1 | FY15 | FY15P07
8 | 2015-02-22 | 1 | WK26 | P7 | W2 | P7W2 | FY15 | FY15P07
9 | 2015-02-23 | 2 | WK26 | P7 | W2 | P7W2 | FY15 | FY15P07
10 | 2015-02-24 | 3 | WK26 | P7 | W2 | P7W2 | FY15 | FY15P07
11 | 2015-02-25 | 4 | WK26 | P7 | W2 | P7W2 | FY15 | FY15P07
12 | 2015-02-26 | 5 | WK26 | P7 | W2 | P7W2 | FY15 | FY15P07
13 | 2015-02-27 | 6 | WK26 | P7 | W2 | P7W2 | FY15 | FY15P07
14 | 2015-02-28 | 7 | WK26 | P7 | W2 | P7W2 | FY15 | FY15P07
15 | 2015-03-01 | 1 | WK27 | P7 | W3 | P7W3 | FY15 | FY15P07
16 | 2015-03-02 | 2 | WK27 | P7 | W3 | P7W3 | FY15 | FY15P07
17 | 2015-03-03 | 3 | WK27 | P7 | W3 | P7W3 | FY15 | FY15P07
18 | 2015-03-04 | 4 | WK27 | P7 | W3 | P7W3 | FY15 | FY15P07
19 | 2015-03-05 | 5 | WK27 | P7 | W3 | P7W3 | FY15 | FY15P07
20 | 2015-03-06 | 6 | WK27 | P7 | W3 | P7W3 | FY15 | FY15P07
21 | 2015-03-07 | 7 | WK27 | P7 | W3 | P7W3 | FY15 | FY15P07
22 | 2015-03-08 | 1 | WK28 | P7 | W4 | P7W4 | FY15 | FY15P07
23 | 2015-03-09 | 2 | WK28 | P7 | W4 | P7W4 | FY15 | FY15P07
24 | 2015-03-10 | 3 | WK28 | P7 | W4 | P7W4 | FY15 | FY15P07
25 | 2015-03-11 | 4 | WK28 | P7 | W4 | P7W4 | FY15 | FY15P07
26 | 2015-03-12 | 5 | WK28 | P7 | W4 | P7W4 | FY15 | FY15P07
27 | 2015-03-13 | 6 | WK28 | P7 | W4 | P7W4 | FY15 | FY15P07
28 | 2015-03-14 | 7 | WK28 | P7 | W4 | P7W4 | FY15 | FY15P07
1 | 2015-03-15 | 1 | WK29 | P8 | W1 | P8W1 | FY15 | FY15P08
2 | 2015-03-16 | 2 | WK29 | P8 | W1 | P8W1 | FY15 | FY15P08
3 | 2015-03-17 | 3 | WK29 | P8 | W1 | P8W1 | FY15 | FY15P08
4 | 2015-03-18 | 4 | WK29 | P8 | W1 | P8W1 | FY15 | FY15P08
5 | 2015-03-19 | 5 | WK29 | P8 | W1 | P8W1 | FY15 | FY15P08
6 | 2015-03-20 | 6 | WK29 | P8 | W1 | P8W1 | FY15 | FY15P08
7 | 2015-03-21 | 7 | WK29 | P8 | W1 | P8W1 | FY15 | FY15P08
8 | 2015-03-22 | 1 | WK30 | P8 | W2 | P8W2 | FY15 | FY15P08
9 | 2015-03-23 | 2 | WK30 | P8 | W2 | P8W2 | FY15 | FY15P08
10 | 2015-03-24 | 3 | WK30 | P8 | W2 | P8W2 | FY15 | FY15P08
11 | 2015-03-25 | 4 | WK30 | P8 | W2 | P8W2 | FY15 | FY15P08
12 | 2015-03-26 | 5 | WK30 | P8 | W2 | P8W2 | FY15 | FY15P08
13 | 2015-03-27 | 6 | WK30 | P8 | W2 | P8W2 | FY15 | FY15P08
14 | 2015-03-28 | 7 | WK30 | P8 | W2 | P8W2 | FY15 | FY15P08
15 | 2015-03-29 | 1 | WK31 | P8 | W3 | P8W3 | FY15 | FY15P08
16 | 2015-03-30 | 2 | WK31 | P8 | W3 | P8W3 | FY15 | FY15P08
17 | 2015-03-31 | 3 | WK31 | P8 | W3 | P8W3 | FY15 | FY15P08
18 | 2015-04-01 | 4 | WK31 | P8 | W3 | P8W3 | FY15 | FY15P08
19 | 2015-04-02 | 5 | WK31 | P8 | W3 | P8W3 | FY15 | FY15P08
20 | 2015-04-03 | 6 | WK31 | P8 | W3 | P8W3 | FY15 | FY15P08
21 | 2015-04-04 | 7 | WK31 | P8 | W3 | P8W3 | FY15 | FY15P08
22 | 2015-04-05 | 1 | WK32 | P8 | W4 | P8W4 | FY15 | FY15P08
23 | 2015-04-06 | 2 | WK32 | P8 | W4 | P8W4 | FY15 | FY15P08
24 | 2015-04-07 | 3 | WK32 | P8 | W4 | P8W4 | FY15 | FY15P08
25 | 2015-04-08 | 4 | WK32 | P8 | W4 | P8W4 | FY15 | FY15P08
26 | 2015-04-09 | 5 | WK32 | P8 | W4 | P8W4 | FY15 | FY15P08
27 | 2015-04-10 | 6 | WK32 | P8 | W4 | P8W4 | FY15 | FY15P08
28 | 2015-04-11 | 7 | WK32 | P8 | W4 | P8W4 | FY15 | FY15P08
1 | 2015-04-12 | 1 | WK33 | P9 | W1 | P9W1 | FY15 | FY15P09
2 | 2015-04-13 | 2 | WK33 | P9 | W1 | P9W1 | FY15 | FY15P09
3 | 2015-04-14 | 3 | WK33 | P9 | W1 | P9W1 | FY15 | FY15P09
4 | 2015-04-15 | 4 | WK33 | P9 | W1 | P9W1 | FY15 | FY15P09
5 | 2015-04-16 | 5 | WK33 | P9 | W1 | P9W1 | FY15 | FY15P09
6 | 2015-04-17 | 6 | WK33 | P9 | W1 | P9W1 | FY15 | FY15P09
7 | 2015-04-18 | 7 | WK33 | P9 | W1 | P9W1 | FY15 | FY15P09
8 | 2015-04-19 | 1 | WK34 | P9 | W2 | P9W2 | FY15 | FY15P09
9 | 2015-04-20 | 2 | WK34 | P9 | W2 | P9W2 | FY15 | FY15P09
10 | 2015-04-21 | 3 | WK34 | P9 | W2 | P9W2 | FY15 | FY15P09
11 | 2015-04-22 | 4 | WK34 | P9 | W2 | P9W2 | FY15 | FY15P09
12 | 2015-04-23 | 5 | WK34 | P9 | W2 | P9W2 | FY15 | FY15P09
13 | 2015-04-24 | 6 | WK34 | P9 | W2 | P9W2 | FY15 | FY15P09
14 | 2015-04-25 | 7 | WK34 | P9 | W2 | P9W2 | FY15 | FY15P09
15 | 2015-04-26 | 1 | WK35 | P9 | W3 | P9W3 | FY15 | FY15P09
16 | 2015-04-27 | 2 | WK35 | P9 | W3 | P9W3 | FY15 | FY15P09
17 | 2015-04-28 | 3 | WK35 | P9 | W3 | P9W3 | FY15 | FY15P09
18 | 2015-04-29 | 4 | WK35 | P9 | W3 | P9W3 | FY15 | FY15P09
19 | 2015-04-30 | 5 | WK35 | P9 | W3 | P9W3 | FY15 | FY15P09
20 | 2015-05-01 | 6 | WK35 | P9 | W3 | P9W3 | FY15 | FY15P09
21 | 2015-05-02 | 7 | WK35 | P9 | W3 | P9W3 | FY15 | FY15P09
22 | 2015-05-03 | 1 | WK36 | P9 | W4 | P9W4 | FY15 | FY15P09
23 | 2015-05-04 | 2 | WK36 | P9 | W4 | P9W4 | FY15 | FY15P09
24 | 2015-05-05 | 3 | WK36 | P9 | W4 | P9W4 | FY15 | FY15P09
25 | 2015-05-06 | 4 | WK36 | P9 | W4 | P9W4 | FY15 | FY15P09
26 | 2015-05-07 | 5 | WK36 | P9 | W4 | P9W4 | FY15 | FY15P09
27 | 2015-05-08 | 6 | WK36 | P9 | W4 | P9W4 | FY15 | FY15P09
28 | 2015-05-09 | 7 | WK36 | P9 | W4 | P9W4 | FY15 | FY15P09
1 | 2015-05-10 | 1 | WK37 | P10 | W1 | P10W1 | FY15 | FY15P10
2 | 2015-05-11 | 2 | WK37 | P10 | W1 | P10W1 | FY15 | FY15P10
3 | 2015-05-12 | 3 | WK37 | P10 | W1 | P10W1 | FY15 | FY15P10
4 | 2015-05-13 | 4 | WK37 | P10 | W1 | P10W1 | FY15 | FY15P10
5 | 2015-05-14 | 5 | WK37 | P10 | W1 | P10W1 | FY15 | FY15P10
6 | 2015-05-15 | 6 | WK37 | P10 | W1 | P10W1 | FY15 | FY15P10
7 | 2015-05-16 | 7 | WK37 | P10 | W1 | P10W1 | FY15 | FY15P10
8 | 2015-05-17 | 1 | WK38 | P10 | W2 | P10W2 | FY15 | FY15P10
9 | 2015-05-18 | 2 | WK38 | P10 | W2 | P10W2 | FY15 | FY15P10
10 | 2015-05-19 | 3 | WK38 | P10 | W2 | P10W2 | FY15 | FY15P10
11 | 2015-05-20 | 4 | WK38 | P10 | W2 | P10W2 | FY15 | FY15P10
12 | 2015-05-21 | 5 | WK38 | P10 | W2 | P10W2 | FY15 | FY15P10
13 | 2015-05-22 | 6 | WK38 | P10 | W2 | P10W2 | FY15 | FY15P10
14 | 2015-05-23 | 7 | WK38 | P10 | W2 | P10W2 | FY15 | FY15P10
15 | 2015-05-24 | 1 | WK39 | P10 | W3 | P10W3 | FY15 | FY15P10
16 | 2015-05-25 | 2 | WK39 | P10 | W3 | P10W3 | FY15 | FY15P10
17 | 2015-05-26 | 3 | WK39 | P10 | W3 | P10W3 | FY15 | FY15P10
18 | 2015-05-27 | 4 | WK39 | P10 | W3 | P10W3 | FY15 | FY15P10
19 | 2015-05-28 | 5 | WK39 | P10 | W3 | P10W3 | FY15 | FY15P10
20 | 2015-05-29 | 6 | WK39 | P10 | W3 | P10W3 | FY15 | FY15P10
21 | 2015-05-30 | 7 | WK39 | P10 | W3 | P10W3 | FY15 | FY15P10
22 | 2015-05-31 | 1 | WK40 | P10 | W4 | P10W4 | FY15 | FY15P10
23 | 2015-06-01 | 2 | WK40 | P10 | W4 | P10W4 | FY15 | FY15P10
24 | 2015-06-02 | 3 | WK40 | P10 | W4 | P10W4 | FY15 | FY15P10
25 | 2015-06-03 | 4 | WK40 | P10 | W4 | P10W4 | FY15 | FY15P10
26 | 2015-06-04 | 5 | WK40 | P10 | W4 | P10W4 | FY15 | FY15P10
27 | 2015-06-05 | 6 | WK40 | P10 | W4 | P10W4 | FY15 | FY15P10
28 | 2015-06-06 | 7 | WK40 | P10 | W4 | P10W4 | FY15 | FY15P10
1 | 2015-06-07 | 1 | WK41 | P11 | W1 | P11W1 | FY15 | FY15P11
2 | 2015-06-08 | 2 | WK41 | P11 | W1 | P11W1 | FY15 | FY15P11
3 | 2015-06-09 | 3 | WK41 | P11 | W1 | P11W1 | FY15 | FY15P11
4 | 2015-06-10 | 4 | WK41 | P11 | W1 | P11W1 | FY15 | FY15P11
5 | 2015-06-11 | 5 | WK41 | P11 | W1 | P11W1 | FY15 | FY15P11
6 | 2015-06-12 | 6 | WK41 | P11 | W1 | P11W1 | FY15 | FY15P11
7 | 2015-06-13 | 7 | WK41 | P11 | W1 | P11W1 | FY15 | FY15P11
8 | 2015-06-14 | 1 | WK42 | P11 | W2 | P11W2 | FY15 | FY15P11
9 | 2015-06-15 | 2 | WK42 | P11 | W2 | P11W2 | FY15 | FY15P11
10 | 2015-06-16 | 3 | WK42 | P11 | W2 | P11W2 | FY15 | FY15P11
11 | 2015-06-17 | 4 | WK42 | P11 | W2 | P11W2 | FY15 | FY15P11
12 | 2015-06-18 | 5 | WK42 | P11 | W2 | P11W2 | FY15 | FY15P11
13 | 2015-06-19 | 6 | WK42 | P11 | W2 | P11W2 | FY15 | FY15P11
14 | 2015-06-20 | 7 | WK42 | P11 | W2 | P11W2 | FY15 | FY15P11
15 | 2015-06-21 | 1 | WK43 | P11 | W3 | P11W3 | FY15 | FY15P11
16 | 2015-06-22 | 2 | WK43 | P11 | W3 | P11W3 | FY15 | FY15P11
17 | 2015-06-23 | 3 | WK43 | P11 | W3 | P11W3 | FY15 | FY15P11
18 | 2015-06-24 | 4 | WK43 | P11 | W3 | P11W3 | FY15 | FY15P11
19 | 2015-06-25 | 5 | WK43 | P11 | W3 | P11W3 | FY15 | FY15P11
20 | 2015-06-26 | 6 | WK43 | P11 | W3 | P11W3 | FY15 | FY15P11
21 | 2015-06-27 | 7 | WK43 | P11 | W3 | P11W3 | FY15 | FY15P11
22 | 2015-06-28 | 1 | WK44 | P11 | W4 | P11W4 | FY15 | FY15P11
23 | 2015-06-29 | 2 | WK44 | P11 | W4 | P11W4 | FY15 | FY15P11
24 | 2015-06-30 | 3 | WK44 | P11 | W4 | P11W4 | FY15 | FY15P11
25 | 2015-07-01 | 4 | WK44 | P11 | W4 | P11W4 | FY15 | FY15P11
26 | 2015-07-02 | 5 | WK44 | P11 | W4 | P11W4 | FY15 | FY15P11
27 | 2015-07-03 | 6 | WK44 | P11 | W4 | P11W4 | FY15 | FY15P11
28 | 2015-07-04 | 7 | WK44 | P11 | W4 | P11W4 | FY15 | FY15P11
1 | 2015-07-05 | 1 | WK45 | P12 | W1 | P12W1 | FY15 | FY15P12
2 | 2015-07-06 | 2 | WK45 | P12 | W1 | P12W1 | FY15 | FY15P12
3 | 2015-07-07 | 3 | WK45 | P12 | W1 | P12W1 | FY15 | FY15P12
4 | 2015-07-08 | 4 | WK45 | P12 | W1 | P12W1 | FY15 | FY15P12
5 | 2015-07-09 | 5 | WK45 | P12 | W1 | P12W1 | FY15 | FY15P12
6 | 2015-07-10 | 6 | WK45 | P12 | W1 | P12W1 | FY15 | FY15P12
7 | 2015-07-11 | 7 | WK45 | P12 | W1 | P12W1 | FY15 | FY15P12
8 | 2015-07-12 | 1 | WK46 | P12 | W2 | P12W2 | FY15 | FY15P12
9 | 2015-07-13 | 2 | WK46 | P12 | W2 | P12W2 | FY15 | FY15P12
10 | 2015-07-14 | 3 | WK46 | P12 | W2 | P12W2 | FY15 | FY15P12
11 | 2015-07-15 | 4 | WK46 | P12 | W2 | P12W2 | FY15 | FY15P12
12 | 2015-07-16 | 5 | WK46 | P12 | W2 | P12W2 | FY15 | FY15P12
13 | 2015-07-17 | 6 | WK46 | P12 | W2 | P12W2 | FY15 | FY15P12
14 | 2015-07-18 | 7 | WK46 | P12 | W2 | P12W2 | FY15 | FY15P12
15 | 2015-07-19 | 1 | WK47 | P12 | W3 | P12W3 | FY15 | FY15P12
16 | 2015-07-20 | 2 | WK47 | P12 | W3 | P12W3 | FY15 | FY15P12
17 | 2015-07-21 | 3 | WK47 | P12 | W3 | P12W3 | FY15 | FY15P12
18 | 2015-07-22 | 4 | WK47 | P12 | W3 | P12W3 | FY15 | FY15P12
19 | 2015-07-23 | 5 | WK47 | P12 | W3 | P12W3 | FY15 | FY15P12
20 | 2015-07-24 | 6 | WK47 | P12 | W3 | P12W3 | FY15 | FY15P12
21 | 2015-07-25 | 7 | WK47 | P12 | W3 | P12W3 | FY15 | FY15P12
22 | 2015-07-26 | 1 | WK48 | P12 | W4 | P12W4 | FY15 | FY15P12
23 | 2015-07-27 | 2 | WK48 | P12 | W4 | P12W4 | FY15 | FY15P12
24 | 2015-07-28 | 3 | WK48 | P12 | W4 | P12W4 | FY15 | FY15P12
25 | 2015-07-29 | 4 | WK48 | P12 | W4 | P12W4 | FY15 | FY15P12
26 | 2015-07-30 | 5 | WK48 | P12 | W4 | P12W4 | FY15 | FY15P12
27 | 2015-07-31 | 6 | WK48 | P12 | W4 | P12W4 | FY15 | FY15P12
28 | 2015-08-01 | 7 | WK48 | P12 | W4 | P12W4 | FY15 | FY15P12
1 | 2015-08-02 | 1 | WK49 | P13 | W1 | P13W1 | FY15 | FY15P13
2 | 2015-08-03 | 2 | WK49 | P13 | W1 | P13W1 | FY15 | FY15P13
3 | 2015-08-04 | 3 | WK49 | P13 | W1 | P13W1 | FY15 | FY15P13
4 | 2015-08-05 | 4 | WK49 | P13 | W1 | P13W1 | FY15 | FY15P13
5 | 2015-08-06 | 5 | WK49 | P13 | W1 | P13W1 | FY15 | FY15P13
6 | 2015-08-07 | 6 | WK49 | P13 | W1 | P13W1 | FY15 | FY15P13
7 | 2015-08-08 | 7 | WK49 | P13 | W1 | P13W1 | FY15 | FY15P13
8 | 2015-08-09 | 1 | WK50 | P13 | W2 | P13W2 | FY15 | FY15P13
9 | 2015-08-10 | 2 | WK50 | P13 | W2 | P13W2 | FY15 | FY15P13
10 | 2015-08-11 | 3 | WK50 | P13 | W2 | P13W2 | FY15 | FY15P13
11 | 2015-08-12 | 4 | WK50 | P13 | W2 | P13W2 | FY15 | FY15P13
12 | 2015-08-13 | 5 | WK50 | P13 | W2 | P13W2 | FY15 | FY15P13
13 | 2015-08-14 | 6 | WK50 | P13 | W2 | P13W2 | FY15 | FY15P13
14 | 2015-08-15 | 7 | WK50 | P13 | W2 | P13W2 | FY15 | FY15P13
15 | 2015-08-16 | 1 | WK51 | P13 | W3 | P13W3 | FY15 | FY15P13
16 | 2015-08-17 | 2 | WK51 | P13 | W3 | P13W3 | FY15 | FY15P13
17 | 2015-08-18 | 3 | WK51 | P13 | W3 | P13W3 | FY15 | FY15P13
18 | 2015-08-19 | 4 | WK51 | P13 | W3 | P13W3 | FY15 | FY15P13
19 | 2015-08-20 | 5 | WK51 | P13 | W3 | P13W3 | FY15 | FY15P13
20 | 2015-08-21 | 6 | WK51 | P13 | W3 | P13W3 | FY15 | FY15P13
21 | 2015-08-22 | 7 | WK51 | P13 | W3 | P13W3 | FY15 | FY15P13
22 | 2015-08-23 | 1 | WK52 | P13 | W4 | P13W4 | FY15 | FY15P13
23 | 2015-08-24 | 2 | WK52 | P13 | W4 | P13W4 | FY15 | FY15P13
24 | 2015-08-25 | 3 | WK52 | P13 | W4 | P13W4 | FY15 | FY15P13
25 | 2015-08-26 | 4 | WK52 | P13 | W4 | P13W4 | FY15 | FY15P13
26 | 2015-08-27 | 5 | WK52 | P13 | W4 | P13W4 | FY15 | FY15P13
27 | 2015-08-28 | 6 | WK52 | P13 | W4 | P13W4 | FY15 | FY15P13
28 | 2015-08-29 | 7 | WK52 | P13 | W4 | P13W4 | FY15 | FY15P13
1 | 2015-08-30 | 1 | WK1 | P1 | W1 | P1W1 | FY16 | FY16P01
2 | 2015-08-31 | 2 | WK1 | P1 | W1 | P1W1 | FY16 | FY16P01
3 | 2015-09-01 | 3 | WK1 | P1 | W1 | P1W1 | FY16 | FY16P01
4 | 2015-09-02 | 4 | WK1 | P1 | W1 | P1W1 | FY16 | FY16P01
5 | 2015-09-03 | 5 | WK1 | P1 | W1 | P1W1 | FY16 | FY16P01
6 | 2015-09-04 | 6 | WK1 | P1 | W1 | P1W1 | FY16 | FY16P01
7 | 2015-09-05 | 7 | WK1 | P1 | W1 | P1W1 | FY16 | FY16P01
8 | 2015-09-06 | 1 | WK2 | P1 | W2 | P1W2 | FY16 | FY16P01
9 | 2015-09-07 | 2 | WK2 | P1 | W2 | P1W2 | FY16 | FY16P01
10 | 2015-09-08 | 3 | WK2 | P1 | W2 | P1W2 | FY16 | FY16P01
11 | 2015-09-09 | 4 | WK2 | P1 | W2 | P1W2 | FY16 | FY16P01
12 | 2015-09-10 | 5 | WK2 | P1 | W2 | P1W2 | FY16 | FY16P01
13 | 2015-09-11 | 6 | WK2 | P1 | W2 | P1W2 | FY16 | FY16P01
14 | 2015-09-12 | 7 | WK2 | P1 | W2 | P1W2 | FY16 | FY16P01
15 | 2015-09-13 | 1 | WK3 | P1 | W3 | P1W3 | FY16 | FY16P01
16 | 2015-09-14 | 2 | WK3 | P1 | W3 | P1W3 | FY16 | FY16P01
17 | 2015-09-15 | 3 | WK3 | P1 | W3 | P1W3 | FY16 | FY16P01
18 | 2015-09-16 | 4 | WK3 | P1 | W3 | P1W3 | FY16 | FY16P01
19 | 2015-09-17 | 5 | WK3 | P1 | W3 | P1W3 | FY16 | FY16P01
20 | 2015-09-18 | 6 | WK3 | P1 | W3 | P1W3 | FY16 | FY16P01
21 | 2015-09-19 | 7 | WK3 | P1 | W3 | P1W3 | FY16 | FY16P01
22 | 2015-09-20 | 1 | WK4 | P1 | W4 | P1W4 | FY16 | FY16P01
23 | 2015-09-21 | 2 | WK4 | P1 | W4 | P1W4 | FY16 | FY16P01
24 | 2015-09-22 | 3 | WK4 | P1 | W4 | P1W4 | FY16 | FY16P01
25 | 2015-09-23 | 4 | WK4 | P1 | W4 | P1W4 | FY16 | FY16P01
26 | 2015-09-24 | 5 | WK4 | P1 | W4 | P1W4 | FY16 | FY16P01
27 | 2015-09-25 | 6 | WK4 | P1 | W4 | P1W4 | FY16 | FY16P01
28 | 2015-09-26 | 7 | WK4 | P1 | W4 | P1W4 | FY16 | FY16P01
1 | 2015-09-27 | 1 | WK5 | P2 | W1 | P2W1 | FY16 | FY16P02
2 | 2015-09-28 | 2 | WK5 | P2 | W1 | P2W1 | FY16 | FY16P02
3 | 2015-09-29 | 3 | WK5 | P2 | W1 | P2W1 | FY16 | FY16P02
4 | 2015-09-30 | 4 | WK5 | P2 | W1 | P2W1 | FY16 | FY16P02
5 | 2015-10-01 | 5 | WK5 | P2 | W1 | P2W1 | FY16 | FY16P02
6 | 2015-10-02 | 6 | WK5 | P2 | W1 | P2W1 | FY16 | FY16P02
7 | 2015-10-03 | 7 | WK5 | P2 | W1 | P2W1 | FY16 | FY16P02
8 | 2015-10-04 | 1 | WK6 | P2 | W2 | P2W2 | FY16 | FY16P02
9 | 2015-10-05 | 2 | WK6 | P2 | W2 | P2W2 | FY16 | FY16P02
10 | 2015-10-06 | 3 | WK6 | P2 | W2 | P2W2 | FY16 | FY16P02
11 | 2015-10-07 | 4 | WK6 | P2 | W2 | P2W2 | FY16 | FY16P02
12 | 2015-10-08 | 5 | WK6 | P2 | W2 | P2W2 | FY16 | FY16P02
13 | 2015-10-09 | 6 | WK6 | P2 | W2 | P2W2 | FY16 | FY16P02
14 | 2015-10-10 | 7 | WK6 | P2 | W2 | P2W2 | FY16 | FY16P02
15 | 2015-10-11 | 1 | WK7 | P2 | W3 | P2W3 | FY16 | FY16P02
16 | 2015-10-12 | 2 | WK7 | P2 | W3 | P2W3 | FY16 | FY16P02
17 | 2015-10-13 | 3 | WK7 | P2 | W3 | P2W3 | FY16 | FY16P02
18 | 2015-10-14 | 4 | WK7 | P2 | W3 | P2W3 | FY16 | FY16P02
19 | 2015-10-15 | 5 | WK7 | P2 | W3 | P2W3 | FY16 | FY16P02
20 | 2015-10-16 | 6 | WK7 | P2 | W3 | P2W3 | FY16 | FY16P02
21 | 2015-10-17 | 7 | WK7 | P2 | W3 | P2W3 | FY16 | FY16P02
22 | 2015-10-18 | 1 | WK8 | P2 | W4 | P2W4 | FY16 | FY16P02
23 | 2015-10-19 | 2 | WK8 | P2 | W4 | P2W4 | FY16 | FY16P02
24 | 2015-10-20 | 3 | WK8 | P2 | W4 | P2W4 | FY16 | FY16P02
25 | 2015-10-21 | 4 | WK8 | P2 | W4 | P2W4 | FY16 | FY16P02
26 | 2015-10-22 | 5 | WK8 | P2 | W4 | P2W4 | FY16 | FY16P02
27 | 2015-10-23 | 6 | WK8 | P2 | W4 | P2W4 | FY16 | FY16P02
28 | 2015-10-24 | 7 | WK8 | P2 | W4 | P2W4 | FY16 | FY16P02
1 | 2015-10-25 | 1 | WK9 | P3 | W1 | P3W1 | FY16 | FY16P03
2 | 2015-10-26 | 2 | WK9 | P3 | W1 | P3W1 | FY16 | FY16P03
3 | 2015-10-27 | 3 | WK9 | P3 | W1 | P3W1 | FY16 | FY16P03
4 | 2015-10-28 | 4 | WK9 | P3 | W1 | P3W1 | FY16 | FY16P03
5 | 2015-10-29 | 5 | WK9 | P3 | W1 | P3W1 | FY16 | FY16P03
6 | 2015-10-30 | 6 | WK9 | P3 | W1 | P3W1 | FY16 | FY16P03
7 | 2015-10-31 | 7 | WK9 | P3 | W1 | P3W1 | FY16 | FY16P03
8 | 2015-11-01 | 1 | WK10 | P3 | W2 | P3W2 | FY16 | FY16P03
9 | 2015-11-02 | 2 | WK10 | P3 | W2 | P3W2 | FY16 | FY16P03
10 | 2015-11-03 | 3 | WK10 | P3 | W2 | P3W2 | FY16 | FY16P03
11 | 2015-11-04 | 4 | WK10 | P3 | W2 | P3W2 | FY16 | FY16P03
12 | 2015-11-05 | 5 | WK10 | P3 | W2 | P3W2 | FY16 | FY16P03
13 | 2015-11-06 | 6 | WK10 | P3 | W2 | P3W2 | FY16 | FY16P03
14 | 2015-11-07 | 7 | WK10 | P3 | W2 | P3W2 | FY16 | FY16P03
15 | 2015-11-08 | 1 | WK11 | P3 | W3 | P3W3 | FY16 | FY16P03
16 | 2015-11-09 | 2 | WK11 | P3 | W3 | P3W3 | FY16 | FY16P03
17 | 2015-11-10 | 3 | WK11 | P3 | W3 | P3W3 | FY16 | FY16P03
18 | 2015-11-11 | 4 | WK11 | P3 | W3 | P3W3 | FY16 | FY16P03
19 | 2015-11-12 | 5 | WK11 | P3 | W3 | P3W3 | FY16 | FY16P03
20 | 2015-11-13 | 6 | WK11 | P3 | W3 | P3W3 | FY16 | FY16P03
21 | 2015-11-14 | 7 | WK11 | P3 | W3 | P3W3 | FY16 | FY16P03
22 | 2015-11-15 | 1 | WK12 | P3 | W4 | P3W4 | FY16 | FY16P03
23 | 2015-11-16 | 2 | WK12 | P3 | W4 | P3W4 | FY16 | FY16P03
24 | 2015-11-17 | 3 | WK12 | P3 | W4 | P3W4 | FY16 | FY16P03
25 | 2015-11-18 | 4 | WK12 | P3 | W4 | P3W4 | FY16 | FY16P03
26 | 2015-11-19 | 5 | WK12 | P3 | W4 | P3W4 | FY16 | FY16P03
27 | 2015-11-20 | 6 | WK12 | P3 | W4 | P3W4 | FY16 | FY16P03
28 | 2015-11-21 | 7 | WK12 | P3 | W4 | P3W4 | FY16 | FY16P03
1 | 2015-11-22 | 1 | WK13 | P4 | W1 | P4W1 | FY16 | FY16P04
2 | 2015-11-23 | 2 | WK13 | P4 | W1 | P4W1 | FY16 | FY16P04
3 | 2015-11-24 | 3 | WK13 | P4 | W1 | P4W1 | FY16 | FY16P04
4 | 2015-11-25 | 4 | WK13 | P4 | W1 | P4W1 | FY16 | FY16P04
5 | 2015-11-26 | 5 | WK13 | P4 | W1 | P4W1 | FY16 | FY16P04
6 | 2015-11-27 | 6 | WK13 | P4 | W1 | P4W1 | FY16 | FY16P04
7 | 2015-11-28 | 7 | WK13 | P4 | W1 | P4W1 | FY16 | FY16P04
8 | 2015-11-29 | 1 | WK14 | P4 | W2 | P4W2 | FY16 | FY16P04
9 | 2015-11-30 | 2 | WK14 | P4 | W2 | P4W2 | FY16 | FY16P04
10 | 2015-12-01 | 3 | WK14 | P4 | W2 | P4W2 | FY16 | FY16P04
11 | 2015-12-02 | 4 | WK14 | P4 | W2 | P4W2 | FY16 | FY16P04
12 | 2015-12-03 | 5 | WK14 | P4 | W2 | P4W2 | FY16 | FY16P04
13 | 2015-12-04 | 6 | WK14 | P4 | W2 | P4W2 | FY16 | FY16P04
14 | 2015-12-05 | 7 | WK14 | P4 | W2 | P4W2 | FY16 | FY16P04
15 | 2015-12-06 | 1 | WK15 | P4 | W3 | P4W3 | FY16 | FY16P04
16 | 2015-12-07 | 2 | WK15 | P4 | W3 | P4W3 | FY16 | FY16P04
17 | 2015-12-08 | 3 | WK15 | P4 | W3 | P4W3 | FY16 | FY16P04
18 | 2015-12-09 | 4 | WK15 | P4 | W3 | P4W3 | FY16 | FY16P04
19 | 2015-12-10 | 5 | WK15 | P4 | W3 | P4W3 | FY16 | FY16P04
20 | 2015-12-11 | 6 | WK15 | P4 | W3 | P4W3 | FY16 | FY16P04
21 | 2015-12-12 | 7 | WK15 | P4 | W3 | P4W3 | FY16 | FY16P04
22 | 2015-12-13 | 1 | WK16 | P4 | W4 | P4W4 | FY16 | FY16P04
23 | 2015-12-14 | 2 | WK16 | P4 | W4 | P4W4 | FY16 | FY16P04
24 | 2015-12-15 | 3 | WK16 | P4 | W4 | P4W4 | FY16 | FY16P04
25 | 2015-12-16 | 4 | WK16 | P4 | W4 | P4W4 | FY16 | FY16P04
26 | 2015-12-17 | 5 | WK16 | P4 | W4 | P4W4 | FY16 | FY16P04
27 | 2015-12-18 | 6 | WK16 | P4 | W4 | P4W4 | FY16 | FY16P04
28 | 2015-12-19 | 7 | WK16 | P4 | W4 | P4W4 | FY16 | FY16P04
1 | 2015-12-20 | 1 | WK17 | P5 | W1 | P5W1 | FY16 | FY16P05
2 | 2015-12-21 | 2 | WK17 | P5 | W1 | P5W1 | FY16 | FY16P05
3 | 2015-12-22 | 3 | WK17 | P5 | W1 | P5W1 | FY16 | FY16P05
4 | 2015-12-23 | 4 | WK17 | P5 | W1 | P5W1 | FY16 | FY16P05
5 | 2015-12-24 | 5 | WK17 | P5 | W1 | P5W1 | FY16 | FY16P05
6 | 2015-12-25 | 6 | WK17 | P5 | W1 | P5W1 | FY16 | FY16P05
7 | 2015-12-26 | 7 | WK17 | P5 | W1 | P5W1 | FY16 | FY16P05
8 | 2015-12-27 | 1 | WK18 | P5 | W2 | P5W2 | FY16 | FY16P05
9 | 2015-12-28 | 2 | WK18 | P5 | W2 | P5W2 | FY16 | FY16P05
10 | 2015-12-29 | 3 | WK18 | P5 | W2 | P5W2 | FY16 | FY16P05
11 | 2015-12-30 | 4 | WK18 | P5 | W2 | P5W2 | FY16 | FY16P05
12 | 2015-12-31 | 5 | WK18 | P5 | W2 | P5W2 | FY16 | FY16P05
13 | 2016-01-01 | 6 | WK18 | P5 | W2 | P5W2 | FY16 | FY16P05
14 | 2016-01-02 | 7 | WK18 | P5 | W2 | P5W2 | FY16 | FY16P05
15 | 2016-01-03 | 1 | WK19 | P5 | W3 | P5W3 | FY16 | FY16P05
16 | 2016-01-04 | 2 | WK19 | P5 | W3 | P5W3 | FY16 | FY16P05
17 | 2016-01-05 | 3 | WK19 | P5 | W3 | P5W3 | FY16 | FY16P05
18 | 2016-01-06 | 4 | WK19 | P5 | W3 | P5W3 | FY16 | FY16P05
19 | 2016-01-07 | 5 | WK19 | P5 | W3 | P5W3 | FY16 | FY16P05
20 | 2016-01-08 | 6 | WK19 | P5 | W3 | P5W3 | FY16 | FY16P05
21 | 2016-01-09 | 7 | WK19 | P5 | W3 | P5W3 | FY16 | FY16P05
22 | 2016-01-10 | 1 | WK20 | P5 | W4 | P5W4 | FY16 | FY16P05
23 | 2016-01-11 | 2 | WK20 | P5 | W4 | P5W4 | FY16 | FY16P05
24 | 2016-01-12 | 3 | WK20 | P5 | W4 | P5W4 | FY16 | FY16P05
25 | 2016-01-13 | 4 | WK20 | P5 | W4 | P5W4 | FY16 | FY16P05
26 | 2016-01-14 | 5 | WK20 | P5 | W4 | P5W4 | FY16 | FY16P05
27 | 2016-01-15 | 6 | WK20 | P5 | W4 | P5W4 | FY16 | FY16P05
28 | 2016-01-16 | 7 | WK20 | P5 | W4 | P5W4 | FY16 | FY16P05
1 | 2016-01-17 | 1 | WK21 | P6 | W1 | P6W1 | FY16 | FY16P06
2 | 2016-01-18 | 2 | WK21 | P6 | W1 | P6W1 | FY16 | FY16P06
3 | 2016-01-19 | 3 | WK21 | P6 | W1 | P6W1 | FY16 | FY16P06
4 | 2016-01-20 | 4 | WK21 | P6 | W1 | P6W1 | FY16 | FY16P06
5 | 2016-01-21 | 5 | WK21 | P6 | W1 | P6W1 | FY16 | FY16P06
6 | 2016-01-22 | 6 | WK21 | P6 | W1 | P6W1 | FY16 | FY16P06
7 | 2016-01-23 | 7 | WK21 | P6 | W1 | P6W1 | FY16 | FY16P06
8 | 2016-01-24 | 1 | WK22 | P6 | W2 | P6W2 | FY16 | FY16P06
9 | 2016-01-25 | 2 | WK22 | P6 | W2 | P6W2 | FY16 | FY16P06
10 | 2016-01-26 | 3 | WK22 | P6 | W2 | P6W2 | FY16 | FY16P06
11 | 2016-01-27 | 4 | WK22 | P6 | W2 | P6W2 | FY16 | FY16P06
12 | 2016-01-28 | 5 | WK22 | P6 | W2 | P6W2 | FY16 | FY16P06
13 | 2016-01-29 | 6 | WK22 | P6 | W2 | P6W2 | FY16 | FY16P06
14 | 2016-01-30 | 7 | WK22 | P6 | W2 | P6W2 | FY16 | FY16P06
15 | 2016-01-31 | 1 | WK23 | P6 | W3 | P6W3 | FY16 | FY16P06
16 | 2016-02-01 | 2 | WK23 | P6 | W3 | P6W3 | FY16 | FY16P06
17 | 2016-02-02 | 3 | WK23 | P6 | W3 | P6W3 | FY16 | FY16P06
18 | 2016-02-03 | 4 | WK23 | P6 | W3 | P6W3 | FY16 | FY16P06
19 | 2016-02-04 | 5 | WK23 | P6 | W3 | P6W3 | FY16 | FY16P06
20 | 2016-02-05 | 6 | WK23 | P6 | W3 | P6W3 | FY16 | FY16P06
21 | 2016-02-06 | 7 | WK23 | P6 | W3 | P6W3 | FY16 | FY16P06
22 | 2016-02-07 | 1 | WK24 | P6 | W4 | P6W4 | FY16 | FY16P06
23 | 2016-02-08 | 2 | WK24 | P6 | W4 | P6W4 | FY16 | FY16P06
24 | 2016-02-09 | 3 | WK24 | P6 | W4 | P6W4 | FY16 | FY16P06
25 | 2016-02-10 | 4 | WK24 | P6 | W4 | P6W4 | FY16 | FY16P06
26 | 2016-02-11 | 5 | WK24 | P6 | W4 | P6W4 | FY16 | FY16P06
27 | 2016-02-12 | 6 | WK24 | P6 | W4 | P6W4 | FY16 | FY16P06
28 | 2016-02-13 | 7 | WK24 | P6 | W4 | P6W4 | FY16 | FY16P06
1 | 2016-02-14 | 1 | WK25 | P7 | W1 | P7W1 | FY16 | FY16P07
2 | 2016-02-15 | 2 | WK25 | P7 | W1 | P7W1 | FY16 | FY16P07
3 | 2016-02-16 | 3 | WK25 | P7 | W1 | P7W1 | FY16 | FY16P07
4 | 2016-02-17 | 4 | WK25 | P7 | W1 | P7W1 | FY16 | FY16P07
5 | 2016-02-18 | 5 | WK25 | P7 | W1 | P7W1 | FY16 | FY16P07
6 | 2016-02-19 | 6 | WK25 | P7 | W1 | P7W1 | FY16 | FY16P07
7 | 2016-02-20 | 7 | WK25 | P7 | W1 | P7W1 | FY16 | FY16P07
8 | 2016-02-21 | 1 | WK26 | P7 | W2 | P7W2 | FY16 | FY16P07
9 | 2016-02-22 | 2 | WK26 | P7 | W2 | P7W2 | FY16 | FY16P07
10 | 2016-02-23 | 3 | WK26 | P7 | W2 | P7W2 | FY16 | FY16P07
11 | 2016-02-24 | 4 | WK26 | P7 | W2 | P7W2 | FY16 | FY16P07
12 | 2016-02-25 | 5 | WK26 | P7 | W2 | P7W2 | FY16 | FY16P07
13 | 2016-02-26 | 6 | WK26 | P7 | W2 | P7W2 | FY16 | FY16P07
14 | 2016-02-27 | 7 | WK26 | P7 | W2 | P7W2 | FY16 | FY16P07
15 | 2016-02-28 | 1 | WK27 | P7 | W3 | P7W3 | FY16 | FY16P07
16 | 2016-02-29 | 2 | WK27 | P7 | W3 | P7W3 | FY16 | FY16P07
17 | 2016-03-01 | 3 | WK27 | P7 | W3 | P7W3 | FY16 | FY16P07
18 | 2016-03-02 | 4 | WK27 | P7 | W3 | P7W3 | FY16 | FY16P07
19 | 2016-03-03 | 5 | WK27 | P7 | W3 | P7W3 | FY16 | FY16P07
20 | 2016-03-04 | 6 | WK27 | P7 | W3 | P7W3 | FY16 | FY16P07
21 | 2016-03-05 | 7 | WK27 | P7 | W3 | P7W3 | FY16 | FY16P07
22 | 2016-03-06 | 1 | WK28 | P7 | W4 | P7W4 | FY16 | FY16P07
23 | 2016-03-07 | 2 | WK28 | P7 | W4 | P7W4 | FY16 | FY16P07
24 | 2016-03-08 | 3 | WK28 | P7 | W4 | P7W4 | FY16 | FY16P07
25 | 2016-03-09 | 4 | WK28 | P7 | W4 | P7W4 | FY16 | FY16P07
26 | 2016-03-10 | 5 | WK28 | P7 | W4 | P7W4 | FY16 | FY16P07
27 | 2016-03-11 | 6 | WK28 | P7 | W4 | P7W4 | FY16 | FY16P07
28 | 2016-03-12 | 7 | WK28 | P7 | W4 | P7W4 | FY16 | FY16P07
1 | 2016-03-13 | 1 | WK29 | P8 | W1 | P8W1 | FY16 | FY16P08
2 | 2016-03-14 | 2 | WK29 | P8 | W1 | P8W1 | FY16 | FY16P08
3 | 2016-03-15 | 3 | WK29 | P8 | W1 | P8W1 | FY16 | FY16P08
4 | 2016-03-16 | 4 | WK29 | P8 | W1 | P8W1 | FY16 | FY16P08
5 | 2016-03-17 | 5 | WK29 | P8 | W1 | P8W1 | FY16 | FY16P08
6 | 2016-03-18 | 6 | WK29 | P8 | W1 | P8W1 | FY16 | FY16P08
7 | 2016-03-19 | 7 | WK29 | P8 | W1 | P8W1 | FY16 | FY16P08
8 | 2016-03-20 | 1 | WK30 | P8 | W2 | P8W2 | FY16 | FY16P08
9 | 2016-03-21 | 2 | WK30 | P8 | W2 | P8W2 | FY16 | FY16P08
10 | 2016-03-22 | 3 | WK30 | P8 | W2 | P8W2 | FY16 | FY16P08
11 | 2016-03-23 | 4 | WK30 | P8 | W2 | P8W2 | FY16 | FY16P08
12 | 2016-03-24 | 5 | WK30 | P8 | W2 | P8W2 | FY16 | FY16P08
13 | 2016-03-25 | 6 | WK30 | P8 | W2 | P8W2 | FY16 | FY16P08
14 | 2016-03-26 | 7 | WK30 | P8 | W2 | P8W2 | FY16 | FY16P08
15 | 2016-03-27 | 1 | WK31 | P8 | W3 | P8W3 | FY16 | FY16P08
16 | 2016-03-28 | 2 | WK31 | P8 | W3 | P8W3 | FY16 | FY16P08
17 | 2016-03-29 | 3 | WK31 | P8 | W3 | P8W3 | FY16 | FY16P08
18 | 2016-03-30 | 4 | WK31 | P8 | W3 | P8W3 | FY16 | FY16P08
19 | 2016-03-31 | 5 | WK31 | P8 | W3 | P8W3 | FY16 | FY16P08
20 | 2016-04-01 | 6 | WK31 | P8 | W3 | P8W3 | FY16 | FY16P08
21 | 2016-04-02 | 7 | WK31 | P8 | W3 | P8W3 | FY16 | FY16P08
22 | 2016-04-03 | 1 | WK32 | P8 | W4 | P8W4 | FY16 | FY16P08
23 | 2016-04-04 | 2 | WK32 | P8 | W4 | P8W4 | FY16 | FY16P08
24 | 2016-04-05 | 3 | WK32 | P8 | W4 | P8W4 | FY16 | FY16P08
25 | 2016-04-06 | 4 | WK32 | P8 | W4 | P8W4 | FY16 | FY16P08
26 | 2016-04-07 | 5 | WK32 | P8 | W4 | P8W4 | FY16 | FY16P08
27 | 2016-04-08 | 6 | WK32 | P8 | W4 | P8W4 | FY16 | FY16P08
28 | 2016-04-09 | 7 | WK32 | P8 | W4 | P8W4 | FY16 | FY16P08
1 | 2016-04-10 | 1 | WK33 | P9 | W1 | P9W1 | FY16 | FY16P09
2 | 2016-04-11 | 2 | WK33 | P9 | W1 | P9W1 | FY16 | FY16P09
3 | 2016-04-12 | 3 | WK33 | P9 | W1 | P9W1 | FY16 | FY16P09
4 | 2016-04-13 | 4 | WK33 | P9 | W1 | P9W1 | FY16 | FY16P09
5 | 2016-04-14 | 5 | WK33 | P9 | W1 | P9W1 | FY16 | FY16P09
6 | 2016-04-15 | 6 | WK33 | P9 | W1 | P9W1 | FY16 | FY16P09
7 | 2016-04-16 | 7 | WK33 | P9 | W1 | P9W1 | FY16 | FY16P09
8 | 2016-04-17 | 1 | WK34 | P9 | W2 | P9W2 | FY16 | FY16P09
9 | 2016-04-18 | 2 | WK34 | P9 | W2 | P9W2 | FY16 | FY16P09
10 | 2016-04-19 | 3 | WK34 | P9 | W2 | P9W2 | FY16 | FY16P09
11 | 2016-04-20 | 4 | WK34 | P9 | W2 | P9W2 | FY16 | FY16P09
12 | 2016-04-21 | 5 | WK34 | P9 | W2 | P9W2 | FY16 | FY16P09
13 | 2016-04-22 | 6 | WK34 | P9 | W2 | P9W2 | FY16 | FY16P09
14 | 2016-04-23 | 7 | WK34 | P9 | W2 | P9W2 | FY16 | FY16P09
15 | 2016-04-24 | 1 | WK35 | P9 | W3 | P9W3 | FY16 | FY16P09
16 | 2016-04-25 | 2 | WK35 | P9 | W3 | P9W3 | FY16 | FY16P09
17 | 2016-04-26 | 3 | WK35 | P9 | W3 | P9W3 | FY16 | FY16P09
18 | 2016-04-27 | 4 | WK35 | P9 | W3 | P9W3 | FY16 | FY16P09
19 | 2016-04-28 | 5 | WK35 | P9 | W3 | P9W3 | FY16 | FY16P09
20 | 2016-04-29 | 6 | WK35 | P9 | W3 | P9W3 | FY16 | FY16P09
21 | 2016-04-30 | 7 | WK35 | P9 | W3 | P9W3 | FY16 | FY16P09
22 | 2016-05-01 | 1 | WK36 | P9 | W4 | P9W4 | FY16 | FY16P09
23 | 2016-05-02 | 2 | WK36 | P9 | W4 | P9W4 | FY16 | FY16P09
24 | 2016-05-03 | 3 | WK36 | P9 | W4 | P9W4 | FY16 | FY16P09
25 | 2016-05-04 | 4 | WK36 | P9 | W4 | P9W4 | FY16 | FY16P09
26 | 2016-05-05 | 5 | WK36 | P9 | W4 | P9W4 | FY16 | FY16P09
27 | 2016-05-06 | 6 | WK36 | P9 | W4 | P9W4 | FY16 | FY16P09
28 | 2016-05-07 | 7 | WK36 | P9 | W4 | P9W4 | FY16 | FY16P09
1 | 2016-05-08 | 1 | WK37 | P10 | W1 | P10W1 | FY16 | FY16P10
2 | 2016-05-09 | 2 | WK37 | P10 | W1 | P10W1 | FY16 | FY16P10
3 | 2016-05-10 | 3 | WK37 | P10 | W1 | P10W1 | FY16 | FY16P10
4 | 2016-05-11 | 4 | WK37 | P10 | W1 | P10W1 | FY16 | FY16P10
5 | 2016-05-12 | 5 | WK37 | P10 | W1 | P10W1 | FY16 | FY16P10
6 | 2016-05-13 | 6 | WK37 | P10 | W1 | P10W1 | FY16 | FY16P10
7 | 2016-05-14 | 7 | WK37 | P10 | W1 | P10W1 | FY16 | FY16P10
8 | 2016-05-15 | 1 | WK38 | P10 | W2 | P10W2 | FY16 | FY16P10
9 | 2016-05-16 | 2 | WK38 | P10 | W2 | P10W2 | FY16 | FY16P10
10 | 2016-05-17 | 3 | WK38 | P10 | W2 | P10W2 | FY16 | FY16P10
11 | 2016-05-18 | 4 | WK38 | P10 | W2 | P10W2 | FY16 | FY16P10
12 | 2016-05-19 | 5 | WK38 | P10 | W2 | P10W2 | FY16 | FY16P10
13 | 2016-05-20 | 6 | WK38 | P10 | W2 | P10W2 | FY16 | FY16P10
14 | 2016-05-21 | 7 | WK38 | P10 | W2 | P10W2 | FY16 | FY16P10
15 | 2016-05-22 | 1 | WK39 | P10 | W3 | P10W3 | FY16 | FY16P10
16 | 2016-05-23 | 2 | WK39 | P10 | W3 | P10W3 | FY16 | FY16P10
17 | 2016-05-24 | 3 | WK39 | P10 | W3 | P10W3 | FY16 | FY16P10
18 | 2016-05-25 | 4 | WK39 | P10 | W3 | P10W3 | FY16 | FY16P10
19 | 2016-05-26 | 5 | WK39 | P10 | W3 | P10W3 | FY16 | FY16P10
20 | 2016-05-27 | 6 | WK39 | P10 | W3 | P10W3 | FY16 | FY16P10
21 | 2016-05-28 | 7 | WK39 | P10 | W3 | P10W3 | FY16 | FY16P10
22 | 2016-05-29 | 1 | WK40 | P10 | W4 | P10W4 | FY16 | FY16P10
23 | 2016-05-30 | 2 | WK40 | P10 | W4 | P10W4 | FY16 | FY16P10
24 | 2016-05-31 | 3 | WK40 | P10 | W4 | P10W4 | FY16 | FY16P10
25 | 2016-06-01 | 4 | WK40 | P10 | W4 | P10W4 | FY16 | FY16P10
26 | 2016-06-02 | 5 | WK40 | P10 | W4 | P10W4 | FY16 | FY16P10
27 | 2016-06-03 | 6 | WK40 | P10 | W4 | P10W4 | FY16 | FY16P10
28 | 2016-06-04 | 7 | WK40 | P10 | W4 | P10W4 | FY16 | FY16P10
1 | 2016-06-05 | 1 | WK41 | P11 | W1 | P11W1 | FY16 | FY16P11
2 | 2016-06-06 | 2 | WK41 | P11 | W1 | P11W1 | FY16 | FY16P11
3 | 2016-06-07 | 3 | WK41 | P11 | W1 | P11W1 | FY16 | FY16P11
4 | 2016-06-08 | 4 | WK41 | P11 | W1 | P11W1 | FY16 | FY16P11
5 | 2016-06-09 | 5 | WK41 | P11 | W1 | P11W1 | FY16 | FY16P11
6 | 2016-06-10 | 6 | WK41 | P11 | W1 | P11W1 | FY16 | FY16P11
7 | 2016-06-11 | 7 | WK41 | P11 | W1 | P11W1 | FY16 | FY16P11
8 | 2016-06-12 | 1 | WK42 | P11 | W2 | P11W2 | FY16 | FY16P11
9 | 2016-06-13 | 2 | WK42 | P11 | W2 | P11W2 | FY16 | FY16P11
10 | 2016-06-14 | 3 | WK42 | P11 | W2 | P11W2 | FY16 | FY16P11
11 | 2016-06-15 | 4 | WK42 | P11 | W2 | P11W2 | FY16 | FY16P11
12 | 2016-06-16 | 5 | WK42 | P11 | W2 | P11W2 | FY16 | FY16P11
13 | 2016-06-17 | 6 | WK42 | P11 | W2 | P11W2 | FY16 | FY16P11
14 | 2016-06-18 | 7 | WK42 | P11 | W2 | P11W2 | FY16 | FY16P11
15 | 2016-06-19 | 1 | WK43 | P11 | W3 | P11W3 | FY16 | FY16P11
16 | 2016-06-20 | 2 | WK43 | P11 | W3 | P11W3 | FY16 | FY16P11
17 | 2016-06-21 | 3 | WK43 | P11 | W3 | P11W3 | FY16 | FY16P11
18 | 2016-06-22 | 4 | WK43 | P11 | W3 | P11W3 | FY16 | FY16P11
19 | 2016-06-23 | 5 | WK43 | P11 | W3 | P11W3 | FY16 | FY16P11
20 | 2016-06-24 | 6 | WK43 | P11 | W3 | P11W3 | FY16 | FY16P11
21 | 2016-06-25 | 7 | WK43 | P11 | W3 | P11W3 | FY16 | FY16P11
22 | 2016-06-26 | 1 | WK44 | P11 | W4 | P11W4 | FY16 | FY16P11
23 | 2016-06-27 | 2 | WK44 | P11 | W4 | P11W4 | FY16 | FY16P11
24 | 2016-06-28 | 3 | WK44 | P11 | W4 | P11W4 | FY16 | FY16P11
25 | 2016-06-29 | 4 | WK44 | P11 | W4 | P11W4 | FY16 | FY16P11
26 | 2016-06-30 | 5 | WK44 | P11 | W4 | P11W4 | FY16 | FY16P11
27 | 2016-07-01 | 6 | WK44 | P11 | W4 | P11W4 | FY16 | FY16P11
28 | 2016-07-02 | 7 | WK44 | P11 | W4 | P11W4 | FY16 | FY16P11
1 | 2016-07-03 | 1 | WK45 | P12 | W1 | P12W1 | FY16 | FY16P12
2 | 2016-07-04 | 2 | WK45 | P12 | W1 | P12W1 | FY16 | FY16P12
3 | 2016-07-05 | 3 | WK45 | P12 | W1 | P12W1 | FY16 | FY16P12
4 | 2016-07-06 | 4 | WK45 | P12 | W1 | P12W1 | FY16 | FY16P12
5 | 2016-07-07 | 5 | WK45 | P12 | W1 | P12W1 | FY16 | FY16P12
6 | 2016-07-08 | 6 | WK45 | P12 | W1 | P12W1 | FY16 | FY16P12
7 | 2016-07-09 | 7 | WK45 | P12 | W1 | P12W1 | FY16 | FY16P12
8 | 2016-07-10 | 1 | WK46 | P12 | W2 | P12W2 | FY16 | FY16P12
9 | 2016-07-11 | 2 | WK46 | P12 | W2 | P12W2 | FY16 | FY16P12
10 | 2016-07-12 | 3 | WK46 | P12 | W2 | P12W2 | FY16 | FY16P12
11 | 2016-07-13 | 4 | WK46 | P12 | W2 | P12W2 | FY16 | FY16P12
12 | 2016-07-14 | 5 | WK46 | P12 | W2 | P12W2 | FY16 | FY16P12
13 | 2016-07-15 | 6 | WK46 | P12 | W2 | P12W2 | FY16 | FY16P12
14 | 2016-07-16 | 7 | WK46 | P12 | W2 | P12W2 | FY16 | FY16P12
15 | 2016-07-17 | 1 | WK47 | P12 | W3 | P12W3 | FY16 | FY16P12
16 | 2016-07-18 | 2 | WK47 | P12 | W3 | P12W3 | FY16 | FY16P12
17 | 2016-07-19 | 3 | WK47 | P12 | W3 | P12W3 | FY16 | FY16P12
18 | 2016-07-20 | 4 | WK47 | P12 | W3 | P12W3 | FY16 | FY16P12
19 | 2016-07-21 | 5 | WK47 | P12 | W3 | P12W3 | FY16 | FY16P12
20 | 2016-07-22 | 6 | WK47 | P12 | W3 | P12W3 | FY16 | FY16P12
21 | 2016-07-23 | 7 | WK47 | P12 | W3 | P12W3 | FY16 | FY16P12
22 | 2016-07-24 | 1 | WK48 | P12 | W4 | P12W4 | FY16 | FY16P12
23 | 2016-07-25 | 2 | WK48 | P12 | W4 | P12W4 | FY16 | FY16P12
24 | 2016-07-26 | 3 | WK48 | P12 | W4 | P12W4 | FY16 | FY16P12
25 | 2016-07-27 | 4 | WK48 | P12 | W4 | P12W4 | FY16 | FY16P12
26 | 2016-07-28 | 5 | WK48 | P12 | W4 | P12W4 | FY16 | FY16P12
27 | 2016-07-29 | 6 | WK48 | P12 | W4 | P12W4 | FY16 | FY16P12
28 | 2016-07-30 | 7 | WK48 | P12 | W4 | P12W4 | FY16 | FY16P12
1 | 2016-07-31 | 1 | WK49 | P13 | W1 | P13W1 | FY16 | FY16P13
2 | 2016-08-01 | 2 | WK49 | P13 | W1 | P13W1 | FY16 | FY16P13
3 | 2016-08-02 | 3 | WK49 | P13 | W1 | P13W1 | FY16 | FY16P13
4 | 2016-08-03 | 4 | WK49 | P13 | W1 | P13W1 | FY16 | FY16P13
5 | 2016-08-04 | 5 | WK49 | P13 | W1 | P13W1 | FY16 | FY16P13
6 | 2016-08-05 | 6 | WK49 | P13 | W1 | P13W1 | FY16 | FY16P13
7 | 2016-08-06 | 7 | WK49 | P13 | W1 | P13W1 | FY16 | FY16P13
8 | 2016-08-07 | 1 | WK50 | P13 | W2 | P13W2 | FY16 | FY16P13
9 | 2016-08-08 | 2 | WK50 | P13 | W2 | P13W2 | FY16 | FY16P13
10 | 2016-08-09 | 3 | WK50 | P13 | W2 | P13W2 | FY16 | FY16P13
11 | 2016-08-10 | 4 | WK50 | P13 | W2 | P13W2 | FY16 | FY16P13
12 | 2016-08-11 | 5 | WK50 | P13 | W2 | P13W2 | FY16 | FY16P13
13 | 2016-08-12 | 6 | WK50 | P13 | W2 | P13W2 | FY16 | FY16P13
14 | 2016-08-13 | 7 | WK50 | P13 | W2 | P13W2 | FY16 | FY16P13
15 | 2016-08-14 | 1 | WK51 | P13 | W3 | P13W3 | FY16 | FY16P13
16 | 2016-08-15 | 2 | WK51 | P13 | W3 | P13W3 | FY16 | FY16P13
17 | 2016-08-16 | 3 | WK51 | P13 | W3 | P13W3 | FY16 | FY16P13
18 | 2016-08-17 | 4 | WK51 | P13 | W3 | P13W3 | FY16 | FY16P13
19 | 2016-08-18 | 5 | WK51 | P13 | W3 | P13W3 | FY16 | FY16P13
20 | 2016-08-19 | 6 | WK51 | P13 | W3 | P13W3 | FY16 | FY16P13
21 | 2016-08-20 | 7 | WK51 | P13 | W3 | P13W3 | FY16 | FY16P13
22 | 2016-08-21 | 1 | WK52 | P13 | W4 | P13W4 | FY16 | FY16P13
23 | 2016-08-22 | 2 | WK52 | P13 | W4 | P13W4 | FY16 | FY16P13
24 | 2016-08-23 | 3 | WK52 | P13 | W4 | P13W4 | FY16 | FY16P13
25 | 2016-08-24 | 4 | WK52 | P13 | W4 | P13W4 | FY16 | FY16P13
26 | 2016-08-25 | 5 | WK52 | P13 | W4 | P13W4 | FY16 | FY16P13
27 | 2016-08-26 | 6 | WK52 | P13 | W4 | P13W4 | FY16 | FY16P13
28 | 2016-08-27 | 7 | WK52 | P13 | W4 | P13W4 | FY16 | FY16P13
1 | 2016-08-28 | 1 | WK 1 | P1 | W1 | P1W1 | FY17 | FY17P01
2 | 2016-08-29 | 2 | WK 1 | P1 | W1 | P1W1 | FY17 | FY17P01
3 | 2016-08-30 | 3 | WK 1 | P1 | W1 | P1W1 | FY17 | FY17P01
4 | 2016-08-31 | 4 | WK 1 | P1 | W1 | P1W1 | FY17 | FY17P01
5 | 2016-09-01 | 5 | WK 1 | P1 | W1 | P1W1 | FY17 | FY17P01
6 | 2016-09-02 | 6 | WK 1 | P1 | W1 | P1W1 | FY17 | FY17P01
7 | 2016-09-03 | 7 | WK 1 | P1 | W1 | P1W1 | FY17 | FY17P01
8 | 2016-09-04 | 1 | WK 2 | P1 | W2 | P1W2 | FY17 | FY17P01
9 | 2016-09-05 | 2 | WK 2 | P1 | W2 | P1W2 | FY17 | FY17P01
10 | 2016-09-06 | 3 | WK 2 | P1 | W2 | P1W2 | FY17 | FY17P01
11 | 2016-09-07 | 4 | WK 2 | P1 | W2 | P1W2 | FY17 | FY17P01
12 | 2016-09-08 | 5 | WK 2 | P1 | W2 | P1W2 | FY17 | FY17P01
13 | 2016-09-09 | 6 | WK 2 | P1 | W2 | P1W2 | FY17 | FY17P01
14 | 2016-09-10 | 7 | WK 2 | P1 | W2 | P1W2 | FY17 | FY17P01
15 | 2016-09-11 | 1 | WK 3 | P1 | W3 | P1W3 | FY17 | FY17P01
16 | 2016-09-12 | 2 | WK 3 | P1 | W3 | P1W3 | FY17 | FY17P01
17 | 2016-09-13 | 3 | WK 3 | P1 | W3 | P1W3 | FY17 | FY17P01
18 | 2016-09-14 | 4 | WK 3 | P1 | W3 | P1W3 | FY17 | FY17P01
19 | 2016-09-15 | 5 | WK 3 | P1 | W3 | P1W3 | FY17 | FY17P01
20 | 2016-09-16 | 6 | WK 3 | P1 | W3 | P1W3 | FY17 | FY17P01
21 | 2016-09-17 | 7 | WK 3 | P1 | W3 | P1W3 | FY17 | FY17P01
22 | 2016-09-18 | 1 | WK 4 | P1 | W4 | P1W4 | FY17 | FY17P01
23 | 2016-09-19 | 2 | WK 4 | P1 | W4 | P1W4 | FY17 | FY17P01
24 | 2016-09-20 | 3 | WK 4 | P1 | W4 | P1W4 | FY17 | FY17P01
25 | 2016-09-21 | 4 | WK 4 | P1 | W4 | P1W4 | FY17 | FY17P01
26 | 2016-09-22 | 5 | WK 4 | P1 | W4 | P1W4 | FY17 | FY17P01
27 | 2016-09-23 | 6 | WK 4 | P1 | W4 | P1W4 | FY17 | FY17P01
28 | 2016-09-24 | 7 | WK 4 | P1 | W4 | P1W4 | FY17 | FY17P01
1 | 2016-09-25 | 1 | WK 5 | P2 | W1 | P2W1 | FY17 | FY17P02
2 | 2016-09-26 | 2 | WK 5 | P2 | W1 | P2W1 | FY17 | FY17P02
3 | 2016-09-27 | 3 | WK 5 | P2 | W1 | P2W1 | FY17 | FY17P02
4 | 2016-09-28 | 4 | WK 5 | P2 | W1 | P2W1 | FY17 | FY17P02
5 | 2016-09-29 | 5 | WK 5 | P2 | W1 | P2W1 | FY17 | FY17P02
6 | 2016-09-30 | 6 | WK 5 | P2 | W1 | P2W1 | FY17 | FY17P02
7 | 2016-10-01 | 7 | WK 5 | P2 | W1 | P2W1 | FY17 | FY17P02
8 | 2016-10-02 | 1 | WK 6 | P2 | W2 | P2W2 | FY17 | FY17P02
9 | 2016-10-03 | 2 | WK 6 | P2 | W2 | P2W2 | FY17 | FY17P02
10 | 2016-10-04 | 3 | WK 6 | P2 | W2 | P2W2 | FY17 | FY17P02
11 | 2016-10-05 | 4 | WK 6 | P2 | W2 | P2W2 | FY17 | FY17P02
12 | 2016-10-06 | 5 | WK 6 | P2 | W2 | P2W2 | FY17 | FY17P02
13 | 2016-10-07 | 6 | WK 6 | P2 | W2 | P2W2 | FY17 | FY17P02
14 | 2016-10-08 | 7 | WK 6 | P2 | W2 | P2W2 | FY17 | FY17P02
15 | 2016-10-09 | 1 | WK 7 | P2 | W3 | P2W3 | FY17 | FY17P02
16 | 2016-10-10 | 2 | WK 7 | P2 | W3 | P2W3 | FY17 | FY17P02
17 | 2016-10-11 | 3 | WK 7 | P2 | W3 | P2W3 | FY17 | FY17P02
18 | 2016-10-12 | 4 | WK 7 | P2 | W3 | P2W3 | FY17 | FY17P02
19 | 2016-10-13 | 5 | WK 7 | P2 | W3 | P2W3 | FY17 | FY17P02
20 | 2016-10-14 | 6 | WK 7 | P2 | W3 | P2W3 | FY17 | FY17P02
21 | 2016-10-15 | 7 | WK 7 | P2 | W3 | P2W3 | FY17 | FY17P02
22 | 2016-10-16 | 1 | WK 8 | P2 | W4 | P2W4 | FY17 | FY17P02
23 | 2016-10-17 | 2 | WK 8 | P2 | W4 | P2W4 | FY17 | FY17P02
24 | 2016-10-18 | 3 | WK 8 | P2 | W4 | P2W4 | FY17 | FY17P02
25 | 2016-10-19 | 4 | WK 8 | P2 | W4 | P2W4 | FY17 | FY17P02
26 | 2016-10-20 | 5 | WK 8 | P2 | W4 | P2W4 | FY17 | FY17P02
27 | 2016-10-21 | 6 | WK 8 | P2 | W4 | P2W4 | FY17 | FY17P02
28 | 2016-10-22 | 7 | WK 8 | P2 | W4 | P2W4 | FY17 | FY17P02
1 | 2016-10-23 | 1 | WK 9 | P3 | W1 | P3W1 | FY17 | FY17P03
2 | 2016-10-24 | 2 | WK 9 | P3 | W1 | P3W1 | FY17 | FY17P03
3 | 2016-10-25 | 3 | WK 9 | P3 | W1 | P3W1 | FY17 | FY17P03
4 | 2016-10-26 | 4 | WK 9 | P3 | W1 | P3W1 | FY17 | FY17P03
5 | 2016-10-27 | 5 | WK 9 | P3 | W1 | P3W1 | FY17 | FY17P03
6 | 2016-10-28 | 6 | WK 9 | P3 | W1 | P3W1 | FY17 | FY17P03
7 | 2016-10-29 | 7 | WK 9 | P3 | W1 | P3W1 | FY17 | FY17P03
8 | 2016-10-30 | 1 | WK 10 | P3 | W2 | P3W2 | FY17 | FY17P03
9 | 2016-10-31 | 2 | WK 10 | P3 | W2 | P3W2 | FY17 | FY17P03
10 | 2016-11-01 | 3 | WK 10 | P3 | W2 | P3W2 | FY17 | FY17P03
11 | 2016-11-02 | 4 | WK 10 | P3 | W2 | P3W2 | FY17 | FY17P03
12 | 2016-11-03 | 5 | WK 10 | P3 | W2 | P3W2 | FY17 | FY17P03
13 | 2016-11-04 | 6 | WK 10 | P3 | W2 | P3W2 | FY17 | FY17P03
14 | 2016-11-05 | 7 | WK 10 | P3 | W2 | P3W2 | FY17 | FY17P03
15 | 2016-11-06 | 1 | WK 11 | P3 | W3 | P3W3 | FY17 | FY17P03
16 | 2016-11-07 | 2 | WK 11 | P3 | W3 | P3W3 | FY17 | FY17P03
17 | 2016-11-08 | 3 | WK 11 | P3 | W3 | P3W3 | FY17 | FY17P03
18 | 2016-11-09 | 4 | WK 11 | P3 | W3 | P3W3 | FY17 | FY17P03
19 | 2016-11-10 | 5 | WK 11 | P3 | W3 | P3W3 | FY17 | FY17P03
20 | 2016-11-11 | 6 | WK 11 | P3 | W3 | P3W3 | FY17 | FY17P03
21 | 2016-11-12 | 7 | WK 11 | P3 | W3 | P3W3 | FY17 | FY17P03
22 | 2016-11-13 | 1 | WK 12 | P3 | W4 | P3W4 | FY17 | FY17P03
23 | 2016-11-14 | 2 | WK 12 | P3 | W4 | P3W4 | FY17 | FY17P03
24 | 2016-11-15 | 3 | WK 12 | P3 | W4 | P3W4 | FY17 | FY17P03
25 | 2016-11-16 | 4 | WK 12 | P3 | W4 | P3W4 | FY17 | FY17P03
26 | 2016-11-17 | 5 | WK 12 | P3 | W4 | P3W4 | FY17 | FY17P03
27 | 2016-11-18 | 6 | WK 12 | P3 | W4 | P3W4 | FY17 | FY17P03
28 | 2016-11-19 | 7 | WK 12 | P3 | W4 | P3W4 | FY17 | FY17P03
1 | 2016-11-20 | 1 | WK 13 | P4 | W1 | P4W1 | FY17 | FY17P04
2 | 2016-11-21 | 2 | WK 13 | P4 | W1 | P4W1 | FY17 | FY17P04
3 | 2016-11-22 | 3 | WK 13 | P4 | W1 | P4W1 | FY17 | FY17P04
4 | 2016-11-23 | 4 | WK 13 | P4 | W1 | P4W1 | FY17 | FY17P04
5 | 2016-11-24 | 5 | WK 13 | P4 | W1 | P4W1 | FY17 | FY17P04
6 | 2016-11-25 | 6 | WK 13 | P4 | W1 | P4W1 | FY17 | FY17P04
7 | 2016-11-26 | 7 | WK 13 | P4 | W1 | P4W1 | FY17 | FY17P04
8 | 2016-11-27 | 1 | WK 14 | P4 | W2 | P4W2 | FY17 | FY17P04
9 | 2016-11-28 | 2 | WK 14 | P4 | W2 | P4W2 | FY17 | FY17P04
10 | 2016-11-29 | 3 | WK 14 | P4 | W2 | P4W2 | FY17 | FY17P04
11 | 2016-11-30 | 4 | WK 14 | P4 | W2 | P4W2 | FY17 | FY17P04
12 | 2016-12-01 | 5 | WK 14 | P4 | W2 | P4W2 | FY17 | FY17P04
13 | 2016-12-02 | 6 | WK 14 | P4 | W2 | P4W2 | FY17 | FY17P04
14 | 2016-12-03 | 7 | WK 14 | P4 | W2 | P4W2 | FY17 | FY17P04
15 | 2016-12-04 | 1 | WK 15 | P4 | W3 | P4W3 | FY17 | FY17P04
16 | 2016-12-05 | 2 | WK 15 | P4 | W3 | P4W3 | FY17 | FY17P04
17 | 2016-12-06 | 3 | WK 15 | P4 | W3 | P4W3 | FY17 | FY17P04
18 | 2016-12-07 | 4 | WK 15 | P4 | W3 | P4W3 | FY17 | FY17P04
19 | 2016-12-08 | 5 | WK 15 | P4 | W3 | P4W3 | FY17 | FY17P04
20 | 2016-12-09 | 6 | WK 15 | P4 | W3 | P4W3 | FY17 | FY17P04
21 | 2016-12-10 | 7 | WK 15 | P4 | W3 | P4W3 | FY17 | FY17P04
22 | 2016-12-11 | 1 | WK 16 | P4 | W4 | P4W4 | FY17 | FY17P04
23 | 2016-12-12 | 2 | WK 16 | P4 | W4 | P4W4 | FY17 | FY17P04
24 | 2016-12-13 | 3 | WK 16 | P4 | W4 | P4W4 | FY17 | FY17P04
25 | 2016-12-14 | 4 | WK 16 | P4 | W4 | P4W4 | FY17 | FY17P04
26 | 2016-12-15 | 5 | WK 16 | P4 | W4 | P4W4 | FY17 | FY17P04
27 | 2016-12-16 | 6 | WK 16 | P4 | W4 | P4W4 | FY17 | FY17P04
28 | 2016-12-17 | 7 | WK 16 | P4 | W4 | P4W4 | FY17 | FY17P04
1 | 2016-12-18 | 1 | WK 17 | P5 | W1 | P5W1 | FY17 | FY17P05
2 | 2016-12-19 | 2 | WK 17 | P5 | W1 | P5W1 | FY17 | FY17P05
3 | 2016-12-20 | 3 | WK 17 | P5 | W1 | P5W1 | FY17 | FY17P05
4 | 2016-12-21 | 4 | WK 17 | P5 | W1 | P5W1 | FY17 | FY17P05
5 | 2016-12-22 | 5 | WK 17 | P5 | W1 | P5W1 | FY17 | FY17P05
6 | 2016-12-23 | 6 | WK 17 | P5 | W1 | P5W1 | FY17 | FY17P05
7 | 2016-12-24 | 7 | WK 17 | P5 | W1 | P5W1 | FY17 | FY17P05
8 | 2016-12-25 | 1 | WK 18 | P5 | W2 | P5W2 | FY17 | FY17P05
9 | 2016-12-26 | 2 | WK 18 | P5 | W2 | P5W2 | FY17 | FY17P05
10 | 2016-12-27 | 3 | WK 18 | P5 | W2 | P5W2 | FY17 | FY17P05
11 | 2016-12-28 | 4 | WK 18 | P5 | W2 | P5W2 | FY17 | FY17P05
12 | 2016-12-29 | 5 | WK 18 | P5 | W2 | P5W2 | FY17 | FY17P05
13 | 2016-12-30 | 6 | WK 18 | P5 | W2 | P5W2 | FY17 | FY17P05
14 | 2016-12-31 | 7 | WK 18 | P5 | W2 | P5W2 | FY17 | FY17P05
15 | 2017-01-01 | 1 | WK 19 | P5 | W3 | P5W3 | FY17 | FY17P05
16 | 2017-01-02 | 2 | WK 19 | P5 | W3 | P5W3 | FY17 | FY17P05
17 | 2017-01-03 | 3 | WK 19 | P5 | W3 | P5W3 | FY17 | FY17P05
18 | 2017-01-04 | 4 | WK 19 | P5 | W3 | P5W3 | FY17 | FY17P05
19 | 2017-01-05 | 5 | WK 19 | P5 | W3 | P5W3 | FY17 | FY17P05
20 | 2017-01-06 | 6 | WK 19 | P5 | W3 | P5W3 | FY17 | FY17P05
21 | 2017-01-07 | 7 | WK 19 | P5 | W3 | P5W3 | FY17 | FY17P05
22 | 2017-01-08 | 1 | WK 20 | P5 | W4 | P5W4 | FY17 | FY17P05
23 | 2017-01-09 | 2 | WK 20 | P5 | W4 | P5W4 | FY17 | FY17P05
24 | 2017-01-10 | 3 | WK 20 | P5 | W4 | P5W4 | FY17 | FY17P05
25 | 2017-01-11 | 4 | WK 20 | P5 | W4 | P5W4 | FY17 | FY17P05
26 | 2017-01-12 | 5 | WK 20 | P5 | W4 | P5W4 | FY17 | FY17P05
27 | 2017-01-13 | 6 | WK 20 | P5 | W4 | P5W4 | FY17 | FY17P05
28 | 2017-01-14 | 7 | WK 20 | P5 | W4 | P5W4 | FY17 | FY17P05
1 | 2017-01-15 | 1 | WK 21 | P6 | W1 | P6W1 | FY17 | FY17P06
2 | 2017-01-16 | 2 | WK 21 | P6 | W1 | P6W1 | FY17 | FY17P06
3 | 2017-01-17 | 3 | WK 21 | P6 | W1 | P6W1 | FY17 | FY17P06
4 | 2017-01-18 | 4 | WK 21 | P6 | W1 | P6W1 | FY17 | FY17P06
5 | 2017-01-19 | 5 | WK 21 | P6 | W1 | P6W1 | FY17 | FY17P06
6 | 2017-01-20 | 6 | WK 21 | P6 | W1 | P6W1 | FY17 | FY17P06
7 | 2017-01-21 | 7 | WK 21 | P6 | W1 | P6W1 | FY17 | FY17P06
8 | 2017-01-22 | 1 | WK 22 | P6 | W2 | P6W2 | FY17 | FY17P06
9 | 2017-01-23 | 2 | WK 22 | P6 | W2 | P6W2 | FY17 | FY17P06
10 | 2017-01-24 | 3 | WK 22 | P6 | W2 | P6W2 | FY17 | FY17P06
11 | 2017-01-25 | 4 | WK 22 | P6 | W2 | P6W2 | FY17 | FY17P06
12 | 2017-01-26 | 5 | WK 22 | P6 | W2 | P6W2 | FY17 | FY17P06
13 | 2017-01-27 | 6 | WK 22 | P6 | W2 | P6W2 | FY17 | FY17P06
14 | 2017-01-28 | 7 | WK 22 | P6 | W2 | P6W2 | FY17 | FY17P06
15 | 2017-01-29 | 1 | WK 23 | P6 | W3 | P6W3 | FY17 | FY17P06
16 | 2017-01-30 | 2 | WK 23 | P6 | W3 | P6W3 | FY17 | FY17P06
17 | 2017-01-31 | 3 | WK 23 | P6 | W3 | P6W3 | FY17 | FY17P06
18 | 2017-02-01 | 4 | WK 23 | P6 | W3 | P6W3 | FY17 | FY17P06
19 | 2017-02-02 | 5 | WK 23 | P6 | W3 | P6W3 | FY17 | FY17P06
20 | 2017-02-03 | 6 | WK 23 | P6 | W3 | P6W3 | FY17 | FY17P06
21 | 2017-02-04 | 7 | WK 23 | P6 | W3 | P6W3 | FY17 | FY17P06
22 | 2017-02-05 | 1 | WK 24 | P6 | W4 | P6W4 | FY17 | FY17P06
23 | 2017-02-06 | 2 | WK 24 | P6 | W4 | P6W4 | FY17 | FY17P06
24 | 2017-02-07 | 3 | WK 24 | P6 | W4 | P6W4 | FY17 | FY17P06
25 | 2017-02-08 | 4 | WK 24 | P6 | W4 | P6W4 | FY17 | FY17P06
26 | 2017-02-09 | 5 | WK 24 | P6 | W4 | P6W4 | FY17 | FY17P06
27 | 2017-02-10 | 6 | WK 24 | P6 | W4 | P6W4 | FY17 | FY17P06
28 | 2017-02-11 | 7 | WK 24 | P6 | W4 | P6W4 | FY17 | FY17P06
1 | 2017-02-12 | 1 | WK 25 | P7 | W1 | P7W1 | FY17 | FY17P07
2 | 2017-02-13 | 2 | WK 25 | P7 | W1 | P7W1 | FY17 | FY17P07
3 | 2017-02-14 | 3 | WK 25 | P7 | W1 | P7W1 | FY17 | FY17P07
4 | 2017-02-15 | 4 | WK 25 | P7 | W1 | P7W1 | FY17 | FY17P07
5 | 2017-02-16 | 5 | WK 25 | P7 | W1 | P7W1 | FY17 | FY17P07
6 | 2017-02-17 | 6 | WK 25 | P7 | W1 | P7W1 | FY17 | FY17P07
7 | 2017-02-18 | 7 | WK 25 | P7 | W1 | P7W1 | FY17 | FY17P07
8 | 2017-02-19 | 1 | WK 26 | P7 | W2 | P7W2 | FY17 | FY17P07
9 | 2017-02-20 | 2 | WK 26 | P7 | W2 | P7W2 | FY17 | FY17P07
10 | 2017-02-21 | 3 | WK 26 | P7 | W2 | P7W2 | FY17 | FY17P07
11 | 2017-02-22 | 4 | WK 26 | P7 | W2 | P7W2 | FY17 | FY17P07
12 | 2017-02-23 | 5 | WK 26 | P7 | W2 | P7W2 | FY17 | FY17P07
13 | 2017-02-24 | 6 | WK 26 | P7 | W2 | P7W2 | FY17 | FY17P07
14 | 2017-02-25 | 7 | WK 26 | P7 | W2 | P7W2 | FY17 | FY17P07
15 | 2017-02-26 | 1 | WK 27 | P7 | W3 | P7W3 | FY17 | FY17P07
16 | 2017-02-27 | 2 | WK 27 | P7 | W3 | P7W3 | FY17 | FY17P07
17 | 2017-02-28 | 3 | WK 27 | P7 | W3 | P7W3 | FY17 | FY17P07
18 | 2017-03-01 | 4 | WK 27 | P7 | W3 | P7W3 | FY17 | FY17P07
19 | 2017-03-02 | 5 | WK 27 | P7 | W3 | P7W3 | FY17 | FY17P07
20 | 2017-03-03 | 6 | WK 27 | P7 | W3 | P7W3 | FY17 | FY17P07
21 | 2017-03-04 | 7 | WK 27 | P7 | W3 | P7W3 | FY17 | FY17P07
22 | 2017-03-05 | 1 | WK 28 | P7 | W4 | P7W4 | FY17 | FY17P07
23 | 2017-03-06 | 2 | WK 28 | P7 | W4 | P7W4 | FY17 | FY17P07
24 | 2017-03-07 | 3 | WK 28 | P7 | W4 | P7W4 | FY17 | FY17P07
25 | 2017-03-08 | 4 | WK 28 | P7 | W4 | P7W4 | FY17 | FY17P07
26 | 2017-03-09 | 5 | WK 28 | P7 | W4 | P7W4 | FY17 | FY17P07
27 | 2017-03-10 | 6 | WK 28 | P7 | W4 | P7W4 | FY17 | FY17P07
28 | 2017-03-11 | 7 | WK 28 | P7 | W4 | P7W4 | FY17 | FY17P07
1 | 2017-03-12 | 1 | WK 29 | P8 | W1 | P8W1 | FY17 | FY17P08
2 | 2017-03-13 | 2 | WK 29 | P8 | W1 | P8W1 | FY17 | FY17P08
3 | 2017-03-14 | 3 | WK 29 | P8 | W1 | P8W1 | FY17 | FY17P08
4 | 2017-03-15 | 4 | WK 29 | P8 | W1 | P8W1 | FY17 | FY17P08
5 | 2017-03-16 | 5 | WK 29 | P8 | W1 | P8W1 | FY17 | FY17P08
6 | 2017-03-17 | 6 | WK 29 | P8 | W1 | P8W1 | FY17 | FY17P08
7 | 2017-03-18 | 7 | WK 29 | P8 | W1 | P8W1 | FY17 | FY17P08
8 | 2017-03-19 | 1 | WK 30 | P8 | W2 | P8W2 | FY17 | FY17P08
9 | 2017-03-20 | 2 | WK 30 | P8 | W2 | P8W2 | FY17 | FY17P08
10 | 2017-03-21 | 3 | WK 30 | P8 | W2 | P8W2 | FY17 | FY17P08
11 | 2017-03-22 | 4 | WK 30 | P8 | W2 | P8W2 | FY17 | FY17P08
12 | 2017-03-23 | 5 | WK 30 | P8 | W2 | P8W2 | FY17 | FY17P08
13 | 2017-03-24 | 6 | WK 30 | P8 | W2 | P8W2 | FY17 | FY17P08
14 | 2017-03-25 | 7 | WK 30 | P8 | W2 | P8W2 | FY17 | FY17P08
15 | 2017-03-26 | 1 | WK 31 | P8 | W3 | P8W3 | FY17 | FY17P08
16 | 2017-03-27 | 2 | WK 31 | P8 | W3 | P8W3 | FY17 | FY17P08
17 | 2017-03-28 | 3 | WK 31 | P8 | W3 | P8W3 | FY17 | FY17P08
18 | 2017-03-29 | 4 | WK 31 | P8 | W3 | P8W3 | FY17 | FY17P08
19 | 2017-03-30 | 5 | WK 31 | P8 | W3 | P8W3 | FY17 | FY17P08
20 | 2017-03-31 | 6 | WK 31 | P8 | W3 | P8W3 | FY17 | FY17P08
21 | 2017-04-01 | 7 | WK 31 | P8 | W3 | P8W3 | FY17 | FY17P08
22 | 2017-04-02 | 1 | WK 32 | P8 | W4 | P8W4 | FY17 | FY17P08
23 | 2017-04-03 | 2 | WK 32 | P8 | W4 | P8W4 | FY17 | FY17P08
24 | 2017-04-04 | 3 | WK 32 | P8 | W4 | P8W4 | FY17 | FY17P08
25 | 2017-04-05 | 4 | WK 32 | P8 | W4 | P8W4 | FY17 | FY17P08
26 | 2017-04-06 | 5 | WK 32 | P8 | W4 | P8W4 | FY17 | FY17P08
27 | 2017-04-07 | 6 | WK 32 | P8 | W4 | P8W4 | FY17 | FY17P08
28 | 2017-04-08 | 7 | WK 32 | P8 | W4 | P8W4 | FY17 | FY17P08
1 | 2017-04-09 | 1 | WK 33 | P9 | W1 | P9W1 | FY17 | FY17P09
2 | 2017-04-10 | 2 | WK 33 | P9 | W1 | P9W1 | FY17 | FY17P09
3 | 2017-04-11 | 3 | WK 33 | P9 | W1 | P9W1 | FY17 | FY17P09
4 | 2017-04-12 | 4 | WK 33 | P9 | W1 | P9W1 | FY17 | FY17P09
5 | 2017-04-13 | 5 | WK 33 | P9 | W1 | P9W1 | FY17 | FY17P09
6 | 2017-04-14 | 6 | WK 33 | P9 | W1 | P9W1 | FY17 | FY17P09
7 | 2017-04-15 | 7 | WK 33 | P9 | W1 | P9W1 | FY17 | FY17P09
8 | 2017-04-16 | 1 | WK 34 | P9 | W2 | P9W2 | FY17 | FY17P09
9 | 2017-04-17 | 2 | WK 34 | P9 | W2 | P9W2 | FY17 | FY17P09
10 | 2017-04-18 | 3 | WK 34 | P9 | W2 | P9W2 | FY17 | FY17P09
11 | 2017-04-19 | 4 | WK 34 | P9 | W2 | P9W2 | FY17 | FY17P09
12 | 2017-04-20 | 5 | WK 34 | P9 | W2 | P9W2 | FY17 | FY17P09
13 | 2017-04-21 | 6 | WK 34 | P9 | W2 | P9W2 | FY17 | FY17P09
14 | 2017-04-22 | 7 | WK 34 | P9 | W2 | P9W2 | FY17 | FY17P09
15 | 2017-04-23 | 1 | WK 35 | P9 | W3 | P9W3 | FY17 | FY17P09
16 | 2017-04-24 | 2 | WK 35 | P9 | W3 | P9W3 | FY17 | FY17P09
17 | 2017-04-25 | 3 | WK 35 | P9 | W3 | P9W3 | FY17 | FY17P09
18 | 2017-04-26 | 4 | WK 35 | P9 | W3 | P9W3 | FY17 | FY17P09
19 | 2017-04-27 | 5 | WK 35 | P9 | W3 | P9W3 | FY17 | FY17P09
20 | 2017-04-28 | 6 | WK 35 | P9 | W3 | P9W3 | FY17 | FY17P09
21 | 2017-04-29 | 7 | WK 35 | P9 | W3 | P9W3 | FY17 | FY17P09
22 | 2017-04-30 | 1 | WK 36 | P9 | W4 | P9W4 | FY17 | FY17P09
23 | 2017-05-01 | 2 | WK 36 | P9 | W4 | P9W4 | FY17 | FY17P09
24 | 2017-05-02 | 3 | WK 36 | P9 | W4 | P9W4 | FY17 | FY17P09
25 | 2017-05-03 | 4 | WK 36 | P9 | W4 | P9W4 | FY17 | FY17P09
26 | 2017-05-04 | 5 | WK 36 | P9 | W4 | P9W4 | FY17 | FY17P09
27 | 2017-05-05 | 6 | WK 36 | P9 | W4 | P9W4 | FY17 | FY17P09
28 | 2017-05-06 | 7 | WK 36 | P9 | W4 | P9W4 | FY17 | FY17P09
1 | 2017-05-07 | 1 | WK 37 | P10 | W1 | P10W1 | FY17 | FY17P10
2 | 2017-05-08 | 2 | WK 37 | P10 | W1 | P10W1 | FY17 | FY17P10
3 | 2017-05-09 | 3 | WK 37 | P10 | W1 | P10W1 | FY17 | FY17P10
4 | 2017-05-10 | 4 | WK 37 | P10 | W1 | P10W1 | FY17 | FY17P10
5 | 2017-05-11 | 5 | WK 37 | P10 | W1 | P10W1 | FY17 | FY17P10
6 | 2017-05-12 | 6 | WK 37 | P10 | W1 | P10W1 | FY17 | FY17P10
7 | 2017-05-13 | 7 | WK 37 | P10 | W1 | P10W1 | FY17 | FY17P10
8 | 2017-05-14 | 1 | WK 38 | P10 | W2 | P10W2 | FY17 | FY17P10
9 | 2017-05-15 | 2 | WK 38 | P10 | W2 | P10W2 | FY17 | FY17P10
10 | 2017-05-16 | 3 | WK 38 | P10 | W2 | P10W2 | FY17 | FY17P10
11 | 2017-05-17 | 4 | WK 38 | P10 | W2 | P10W2 | FY17 | FY17P10
12 | 2017-05-18 | 5 | WK 38 | P10 | W2 | P10W2 | FY17 | FY17P10
13 | 2017-05-19 | 6 | WK 38 | P10 | W2 | P10W2 | FY17 | FY17P10
14 | 2017-05-20 | 7 | WK 38 | P10 | W2 | P10W2 | FY17 | FY17P10
15 | 2017-05-21 | 1 | WK 39 | P10 | W3 | P10W3 | FY17 | FY17P10
16 | 2017-05-22 | 2 | WK 39 | P10 | W3 | P10W3 | FY17 | FY17P10
17 | 2017-05-23 | 3 | WK 39 | P10 | W3 | P10W3 | FY17 | FY17P10
18 | 2017-05-24 | 4 | WK 39 | P10 | W3 | P10W3 | FY17 | FY17P10
19 | 2017-05-25 | 5 | WK 39 | P10 | W3 | P10W3 | FY17 | FY17P10
20 | 2017-05-26 | 6 | WK 39 | P10 | W3 | P10W3 | FY17 | FY17P10
21 | 2017-05-27 | 7 | WK 39 | P10 | W3 | P10W3 | FY17 | FY17P10
22 | 2017-05-28 | 1 | WK 40 | P10 | W4 | P10W4 | FY17 | FY17P10
23 | 2017-05-29 | 2 | WK 40 | P10 | W4 | P10W4 | FY17 | FY17P10
24 | 2017-05-30 | 3 | WK 40 | P10 | W4 | P10W4 | FY17 | FY17P10
25 | 2017-05-31 | 4 | WK 40 | P10 | W4 | P10W4 | FY17 | FY17P10
26 | 2017-06-01 | 5 | WK 40 | P10 | W4 | P10W4 | FY17 | FY17P10
27 | 2017-06-02 | 6 | WK 40 | P10 | W4 | P10W4 | FY17 | FY17P10
28 | 2017-06-03 | 7 | WK 40 | P10 | W4 | P10W4 | FY17 | FY17P10
1 | 2017-06-04 | 1 | WK 41 | P11 | W1 | P11W1 | FY17 | FY17P11
2 | 2017-06-05 | 2 | WK 41 | P11 | W1 | P11W1 | FY17 | FY17P11
3 | 2017-06-06 | 3 | WK 41 | P11 | W1 | P11W1 | FY17 | FY17P11
4 | 2017-06-07 | 4 | WK 41 | P11 | W1 | P11W1 | FY17 | FY17P11
5 | 2017-06-08 | 5 | WK 41 | P11 | W1 | P11W1 | FY17 | FY17P11
6 | 2017-06-09 | 6 | WK 41 | P11 | W1 | P11W1 | FY17 | FY17P11
7 | 2017-06-10 | 7 | WK 41 | P11 | W1 | P11W1 | FY17 | FY17P11
8 | 2017-06-11 | 1 | WK 42 | P11 | W2 | P11W2 | FY17 | FY17P11
9 | 2017-06-12 | 2 | WK 42 | P11 | W2 | P11W2 | FY17 | FY17P11
10 | 2017-06-13 | 3 | WK 42 | P11 | W2 | P11W2 | FY17 | FY17P11
11 | 2017-06-14 | 4 | WK 42 | P11 | W2 | P11W2 | FY17 | FY17P11
12 | 2017-06-15 | 5 | WK 42 | P11 | W2 | P11W2 | FY17 | FY17P11
13 | 2017-06-16 | 6 | WK 42 | P11 | W2 | P11W2 | FY17 | FY17P11
14 | 2017-06-17 | 7 | WK 42 | P11 | W2 | P11W2 | FY17 | FY17P11
15 | 2017-06-18 | 1 | WK 43 | P11 | W3 | P11W3 | FY17 | FY17P11
16 | 2017-06-19 | 2 | WK 43 | P11 | W3 | P11W3 | FY17 | FY17P11
17 | 2017-06-20 | 3 | WK 43 | P11 | W3 | P11W3 | FY17 | FY17P11
18 | 2017-06-21 | 4 | WK 43 | P11 | W3 | P11W3 | FY17 | FY17P11
19 | 2017-06-22 | 5 | WK 43 | P11 | W3 | P11W3 | FY17 | FY17P11
20 | 2017-06-23 | 6 | WK 43 | P11 | W3 | P11W3 | FY17 | FY17P11
21 | 2017-06-24 | 7 | WK 43 | P11 | W3 | P11W3 | FY17 | FY17P11
22 | 2017-06-25 | 1 | WK 44 | P11 | W4 | P11W4 | FY17 | FY17P11
23 | 2017-06-26 | 2 | WK 44 | P11 | W4 | P11W4 | FY17 | FY17P11
24 | 2017-06-27 | 3 | WK 44 | P11 | W4 | P11W4 | FY17 | FY17P11
25 | 2017-06-28 | 4 | WK 44 | P11 | W4 | P11W4 | FY17 | FY17P11
26 | 2017-06-29 | 5 | WK 44 | P11 | W4 | P11W4 | FY17 | FY17P11
27 | 2017-06-30 | 6 | WK 44 | P11 | W4 | P11W4 | FY17 | FY17P11
28 | 2017-07-01 | 7 | WK 44 | P11 | W4 | P11W4 | FY17 | FY17P11
1 | 2017-07-02 | 1 | WK 45 | P12 | W1 | P12W1 | FY17 | FY17P12
2 | 2017-07-03 | 2 | WK 45 | P12 | W1 | P12W1 | FY17 | FY17P12
3 | 2017-07-04 | 3 | WK 45 | P12 | W1 | P12W1 | FY17 | FY17P12
4 | 2017-07-05 | 4 | WK 45 | P12 | W1 | P12W1 | FY17 | FY17P12
5 | 2017-07-06 | 5 | WK 45 | P12 | W1 | P12W1 | FY17 | FY17P12
6 | 2017-07-07 | 6 | WK 45 | P12 | W1 | P12W1 | FY17 | FY17P12
7 | 2017-07-08 | 7 | WK 45 | P12 | W1 | P12W1 | FY17 | FY17P12
8 | 2017-07-09 | 1 | WK 46 | P12 | W2 | P12W2 | FY17 | FY17P12
9 | 2017-07-10 | 2 | WK 46 | P12 | W2 | P12W2 | FY17 | FY17P12
10 | 2017-07-11 | 3 | WK 46 | P12 | W2 | P12W2 | FY17 | FY17P12
11 | 2017-07-12 | 4 | WK 46 | P12 | W2 | P12W2 | FY17 | FY17P12
12 | 2017-07-13 | 5 | WK 46 | P12 | W2 | P12W2 | FY17 | FY17P12
13 | 2017-07-14 | 6 | WK 46 | P12 | W2 | P12W2 | FY17 | FY17P12
14 | 2017-07-15 | 7 | WK 46 | P12 | W2 | P12W2 | FY17 | FY17P12
15 | 2017-07-16 | 1 | WK 47 | P12 | W3 | P12W3 | FY17 | FY17P12
16 | 2017-07-17 | 2 | WK 47 | P12 | W3 | P12W3 | FY17 | FY17P12
17 | 2017-07-18 | 3 | WK 47 | P12 | W3 | P12W3 | FY17 | FY17P12
18 | 2017-07-19 | 4 | WK 47 | P12 | W3 | P12W3 | FY17 | FY17P12
19 | 2017-07-20 | 5 | WK 47 | P12 | W3 | P12W3 | FY17 | FY17P12
20 | 2017-07-21 | 6 | WK 47 | P12 | W3 | P12W3 | FY17 | FY17P12
21 | 2017-07-22 | 7 | WK 47 | P12 | W3 | P12W3 | FY17 | FY17P12
22 | 2017-07-23 | 1 | WK 48 | P12 | W4 | P12W4 | FY17 | FY17P12
23 | 2017-07-24 | 2 | WK 48 | P12 | W4 | P12W4 | FY17 | FY17P12
24 | 2017-07-25 | 3 | WK 48 | P12 | W4 | P12W4 | FY17 | FY17P12
25 | 2017-07-26 | 4 | WK 48 | P12 | W4 | P12W4 | FY17 | FY17P12
26 | 2017-07-27 | 5 | WK 48 | P12 | W4 | P12W4 | FY17 | FY17P12
27 | 2017-07-28 | 6 | WK 48 | P12 | W4 | P12W4 | FY17 | FY17P12
28 | 2017-07-29 | 7 | WK 48 | P12 | W4 | P12W4 | FY17 | FY17P12
1 | 2017-07-30 | 1 | WK 49 | P13 | W1 | P13W1 | FY17 | FY17P13
2 | 2017-07-31 | 2 | WK 49 | P13 | W1 | P13W1 | FY17 | FY17P13
3 | 2017-08-01 | 3 | WK 49 | P13 | W1 | P13W1 | FY17 | FY17P13
4 | 2017-08-02 | 4 | WK 49 | P13 | W1 | P13W1 | FY17 | FY17P13
5 | 2017-08-03 | 5 | WK 49 | P13 | W1 | P13W1 | FY17 | FY17P13
6 | 2017-08-04 | 6 | WK 49 | P13 | W1 | P13W1 | FY17 | FY17P13
7 | 2017-08-05 | 7 | WK 49 | P13 | W1 | P13W1 | FY17 | FY17P13
8 | 2017-08-06 | 1 | WK 50 | P13 | W2 | P13W2 | FY17 | FY17P13
9 | 2017-08-07 | 2 | WK 50 | P13 | W2 | P13W2 | FY17 | FY17P13
10 | 2017-08-08 | 3 | WK 50 | P13 | W2 | P13W2 | FY17 | FY17P13
11 | 2017-08-09 | 4 | WK 50 | P13 | W2 | P13W2 | FY17 | FY17P13
12 | 2017-08-10 | 5 | WK 50 | P13 | W2 | P13W2 | FY17 | FY17P13
13 | 2017-08-11 | 6 | WK 50 | P13 | W2 | P13W2 | FY17 | FY17P13
14 | 2017-08-12 | 7 | WK 50 | P13 | W2 | P13W2 | FY17 | FY17P13
15 | 2017-08-13 | 1 | WK 51 | P13 | W3 | P13W3 | FY17 | FY17P13
16 | 2017-08-14 | 2 | WK 51 | P13 | W3 | P13W3 | FY17 | FY17P13
17 | 2017-08-15 | 3 | WK 51 | P13 | W3 | P13W3 | FY17 | FY17P13
18 | 2017-08-16 | 4 | WK 51 | P13 | W3 | P13W3 | FY17 | FY17P13
19 | 2017-08-17 | 5 | WK 51 | P13 | W3 | P13W3 | FY17 | FY17P13
20 | 2017-08-18 | 6 | WK 51 | P13 | W3 | P13W3 | FY17 | FY17P13
21 | 2017-08-19 | 7 | WK 51 | P13 | W3 | P13W3 | FY17 | FY17P13
22 | 2017-08-20 | 1 | WK 52 | P13 | W4 | P13W4 | FY17 | FY17P13
23 | 2017-08-21 | 2 | WK 52 | P13 | W4 | P13W4 | FY17 | FY17P13
24 | 2017-08-22 | 3 | WK 52 | P13 | W4 | P13W4 | FY17 | FY17P13
25 | 2017-08-23 | 4 | WK 52 | P13 | W4 | P13W4 | FY17 | FY17P13
26 | 2017-08-24 | 5 | WK 52 | P13 | W4 | P13W4 | FY17 | FY17P13
27 | 2017-08-25 | 6 | WK 52 | P13 | W4 | P13W4 | FY17 | FY17P13
28 | 2017-08-26 | 7 | WK 52 | P13 | W4 | P13W4 | FY17 | FY17P13
1 | 2017-08-27 | 1 | WK 1 | P1 | W1 | P1W1 | FY18 | FY18P01
2 | 2017-08-28 | 2 | WK 1 | P1 | W1 | P1W1 | FY18 | FY18P01
3 | 2017-08-29 | 3 | WK 1 | P1 | W1 | P1W1 | FY18 | FY18P01
4 | 2017-08-30 | 4 | WK 1 | P1 | W1 | P1W1 | FY18 | FY18P01
5 | 2017-08-31 | 5 | WK 1 | P1 | W1 | P1W1 | FY18 | FY18P01
6 | 2017-09-01 | 6 | WK 1 | P1 | W1 | P1W1 | FY18 | FY18P01
7 | 2017-09-02 | 7 | WK 1 | P1 | W1 | P1W1 | FY18 | FY18P01
8 | 2017-09-03 | 1 | WK 2 | P1 | W2 | P1W2 | FY18 | FY18P01
9 | 2017-09-04 | 2 | WK 2 | P1 | W2 | P1W2 | FY18 | FY18P01
10 | 2017-09-05 | 3 | WK 2 | P1 | W2 | P1W2 | FY18 | FY18P01
11 | 2017-09-06 | 4 | WK 2 | P1 | W2 | P1W2 | FY18 | FY18P01
12 | 2017-09-07 | 5 | WK 2 | P1 | W2 | P1W2 | FY18 | FY18P01
13 | 2017-09-08 | 6 | WK 2 | P1 | W2 | P1W2 | FY18 | FY18P01
14 | 2017-09-09 | 7 | WK 2 | P1 | W2 | P1W2 | FY18 | FY18P01
15 | 2017-09-10 | 1 | WK 3 | P1 | W3 | P1W3 | FY18 | FY18P01
16 | 2017-09-11 | 2 | WK 3 | P1 | W3 | P1W3 | FY18 | FY18P01
17 | 2017-09-12 | 3 | WK 3 | P1 | W3 | P1W3 | FY18 | FY18P01
18 | 2017-09-13 | 4 | WK 3 | P1 | W3 | P1W3 | FY18 | FY18P01
19 | 2017-09-14 | 5 | WK 3 | P1 | W3 | P1W3 | FY18 | FY18P01
20 | 2017-09-15 | 6 | WK 3 | P1 | W3 | P1W3 | FY18 | FY18P01
21 | 2017-09-16 | 7 | WK 3 | P1 | W3 | P1W3 | FY18 | FY18P01
22 | 2017-09-17 | 1 | WK 4 | P1 | W4 | P1W4 | FY18 | FY18P01
23 | 2017-09-18 | 2 | WK 4 | P1 | W4 | P1W4 | FY18 | FY18P01
24 | 2017-09-19 | 3 | WK 4 | P1 | W4 | P1W4 | FY18 | FY18P01
25 | 2017-09-20 | 4 | WK 4 | P1 | W4 | P1W4 | FY18 | FY18P01
26 | 2017-09-21 | 5 | WK 4 | P1 | W4 | P1W4 | FY18 | FY18P01
27 | 2017-09-22 | 6 | WK 4 | P1 | W4 | P1W4 | FY18 | FY18P01
28 | 2017-09-23 | 7 | WK 4 | P1 | W4 | P1W4 | FY18 | FY18P01
1 | 2017-09-24 | 1 | WK 5 | P2 | W1 | P2W1 | FY18 | FY18P02
2 | 2017-09-25 | 2 | WK 5 | P2 | W1 | P2W1 | FY18 | FY18P02
3 | 2017-09-26 | 3 | WK 5 | P2 | W1 | P2W1 | FY18 | FY18P02
4 | 2017-09-27 | 4 | WK 5 | P2 | W1 | P2W1 | FY18 | FY18P02
5 | 2017-09-28 | 5 | WK 5 | P2 | W1 | P2W1 | FY18 | FY18P02
6 | 2017-09-29 | 6 | WK 5 | P2 | W1 | P2W1 | FY18 | FY18P02
7 | 2017-09-30 | 7 | WK 5 | P2 | W1 | P2W1 | FY18 | FY18P02
8 | 2017-10-01 | 1 | WK 6 | P2 | W2 | P2W2 | FY18 | FY18P02
9 | 2017-10-02 | 2 | WK 6 | P2 | W2 | P2W2 | FY18 | FY18P02
10 | 2017-10-03 | 3 | WK 6 | P2 | W2 | P2W2 | FY18 | FY18P02
11 | 2017-10-04 | 4 | WK 6 | P2 | W2 | P2W2 | FY18 | FY18P02
12 | 2017-10-05 | 5 | WK 6 | P2 | W2 | P2W2 | FY18 | FY18P02
13 | 2017-10-06 | 6 | WK 6 | P2 | W2 | P2W2 | FY18 | FY18P02
14 | 2017-10-07 | 7 | WK 6 | P2 | W2 | P2W2 | FY18 | FY18P02
15 | 2017-10-08 | 1 | WK 7 | P2 | W3 | P2W3 | FY18 | FY18P02
16 | 2017-10-09 | 2 | WK 7 | P2 | W3 | P2W3 | FY18 | FY18P02
17 | 2017-10-10 | 3 | WK 7 | P2 | W3 | P2W3 | FY18 | FY18P02
18 | 2017-10-11 | 4 | WK 7 | P2 | W3 | P2W3 | FY18 | FY18P02
19 | 2017-10-12 | 5 | WK 7 | P2 | W3 | P2W3 | FY18 | FY18P02
20 | 2017-10-13 | 6 | WK 7 | P2 | W3 | P2W3 | FY18 | FY18P02
21 | 2017-10-14 | 7 | WK 7 | P2 | W3 | P2W3 | FY18 | FY18P02
22 | 2017-10-15 | 1 | WK 8 | P2 | W4 | P2W4 | FY18 | FY18P02
23 | 2017-10-16 | 2 | WK 8 | P2 | W4 | P2W4 | FY18 | FY18P02
24 | 2017-10-17 | 3 | WK 8 | P2 | W4 | P2W4 | FY18 | FY18P02
25 | 2017-10-18 | 4 | WK 8 | P2 | W4 | P2W4 | FY18 | FY18P02
26 | 2017-10-19 | 5 | WK 8 | P2 | W4 | P2W4 | FY18 | FY18P02
27 | 2017-10-20 | 6 | WK 8 | P2 | W4 | P2W4 | FY18 | FY18P02
28 | 2017-10-21 | 7 | WK 8 | P2 | W4 | P2W4 | FY18 | FY18P02
1 | 2017-10-22 | 1 | WK 9 | P3 | W1 | P3W1 | FY18 | FY18P03
2 | 2017-10-23 | 2 | WK 9 | P3 | W1 | P3W1 | FY18 | FY18P03
3 | 2017-10-24 | 3 | WK 9 | P3 | W1 | P3W1 | FY18 | FY18P03
4 | 2017-10-25 | 4 | WK 9 | P3 | W1 | P3W1 | FY18 | FY18P03
5 | 2017-10-26 | 5 | WK 9 | P3 | W1 | P3W1 | FY18 | FY18P03
6 | 2017-10-27 | 6 | WK 9 | P3 | W1 | P3W1 | FY18 | FY18P03
7 | 2017-10-28 | 7 | WK 9 | P3 | W1 | P3W1 | FY18 | FY18P03
8 | 2017-10-29 | 1 | WK 10 | P3 | W2 | P3W2 | FY18 | FY18P03
9 | 2017-10-30 | 2 | WK 10 | P3 | W2 | P3W2 | FY18 | FY18P03
10 | 2017-10-31 | 3 | WK 10 | P3 | W2 | P3W2 | FY18 | FY18P03
11 | 2017-11-01 | 4 | WK 10 | P3 | W2 | P3W2 | FY18 | FY18P03
12 | 2017-11-02 | 5 | WK 10 | P3 | W2 | P3W2 | FY18 | FY18P03
13 | 2017-11-03 | 6 | WK 10 | P3 | W2 | P3W2 | FY18 | FY18P03
14 | 2017-11-04 | 7 | WK 10 | P3 | W2 | P3W2 | FY18 | FY18P03
15 | 2017-11-05 | 1 | WK 11 | P3 | W3 | P3W3 | FY18 | FY18P03
16 | 2017-11-06 | 2 | WK 11 | P3 | W3 | P3W3 | FY18 | FY18P03
17 | 2017-11-07 | 3 | WK 11 | P3 | W3 | P3W3 | FY18 | FY18P03
18 | 2017-11-08 | 4 | WK 11 | P3 | W3 | P3W3 | FY18 | FY18P03
19 | 2017-11-09 | 5 | WK 11 | P3 | W3 | P3W3 | FY18 | FY18P03
20 | 2017-11-10 | 6 | WK 11 | P3 | W3 | P3W3 | FY18 | FY18P03
21 | 2017-11-11 | 7 | WK 11 | P3 | W3 | P3W3 | FY18 | FY18P03
22 | 2017-11-12 | 1 | WK 12 | P3 | W4 | P3W4 | FY18 | FY18P03
23 | 2017-11-13 | 2 | WK 12 | P3 | W4 | P3W4 | FY18 | FY18P03
24 | 2017-11-14 | 3 | WK 12 | P3 | W4 | P3W4 | FY18 | FY18P03
25 | 2017-11-15 | 4 | WK 12 | P3 | W4 | P3W4 | FY18 | FY18P03
26 | 2017-11-16 | 5 | WK 12 | P3 | W4 | P3W4 | FY18 | FY18P03
27 | 2017-11-17 | 6 | WK 12 | P3 | W4 | P3W4 | FY18 | FY18P03
28 | 2017-11-18 | 7 | WK 12 | P3 | W4 | P3W4 | FY18 | FY18P03
1 | 2017-11-19 | 1 | WK 13 | P4 | W1 | P4W1 | FY18 | FY18P04
2 | 2017-11-20 | 2 | WK 13 | P4 | W1 | P4W1 | FY18 | FY18P04
3 | 2017-11-21 | 3 | WK 13 | P4 | W1 | P4W1 | FY18 | FY18P04
4 | 2017-11-22 | 4 | WK 13 | P4 | W1 | P4W1 | FY18 | FY18P04
5 | 2017-11-23 | 5 | WK 13 | P4 | W1 | P4W1 | FY18 | FY18P04
6 | 2017-11-24 | 6 | WK 13 | P4 | W1 | P4W1 | FY18 | FY18P04
7 | 2017-11-25 | 7 | WK 13 | P4 | W1 | P4W1 | FY18 | FY18P04
8 | 2017-11-26 | 1 | WK 14 | P4 | W2 | P4W2 | FY18 | FY18P04
9 | 2017-11-27 | 2 | WK 14 | P4 | W2 | P4W2 | FY18 | FY18P04
10 | 2017-11-28 | 3 | WK 14 | P4 | W2 | P4W2 | FY18 | FY18P04
11 | 2017-11-29 | 4 | WK 14 | P4 | W2 | P4W2 | FY18 | FY18P04
12 | 2017-11-30 | 5 | WK 14 | P4 | W2 | P4W2 | FY18 | FY18P04
13 | 2017-12-01 | 6 | WK 14 | P4 | W2 | P4W2 | FY18 | FY18P04
14 | 2017-12-02 | 7 | WK 14 | P4 | W2 | P4W2 | FY18 | FY18P04
15 | 2017-12-03 | 1 | WK 15 | P4 | W3 | P4W3 | FY18 | FY18P04
16 | 2017-12-04 | 2 | WK 15 | P4 | W3 | P4W3 | FY18 | FY18P04
17 | 2017-12-05 | 3 | WK 15 | P4 | W3 | P4W3 | FY18 | FY18P04
18 | 2017-12-06 | 4 | WK 15 | P4 | W3 | P4W3 | FY18 | FY18P04
19 | 2017-12-07 | 5 | WK 15 | P4 | W3 | P4W3 | FY18 | FY18P04
20 | 2017-12-08 | 6 | WK 15 | P4 | W3 | P4W3 | FY18 | FY18P04
21 | 2017-12-09 | 7 | WK 15 | P4 | W3 | P4W3 | FY18 | FY18P04
22 | 2017-12-10 | 1 | WK 16 | P4 | W4 | P4W4 | FY18 | FY18P04
23 | 2017-12-11 | 2 | WK 16 | P4 | W4 | P4W4 | FY18 | FY18P04
24 | 2017-12-12 | 3 | WK 16 | P4 | W4 | P4W4 | FY18 | FY18P04
25 | 2017-12-13 | 4 | WK 16 | P4 | W4 | P4W4 | FY18 | FY18P04
26 | 2017-12-14 | 5 | WK 16 | P4 | W4 | P4W4 | FY18 | FY18P04
27 | 2017-12-15 | 6 | WK 16 | P4 | W4 | P4W4 | FY18 | FY18P04
28 | 2017-12-16 | 7 | WK 16 | P4 | W4 | P4W4 | FY18 | FY18P04
1 | 2017-12-17 | 1 | WK 17 | P5 | W1 | P5W1 | FY18 | FY18P05
2 | 2017-12-18 | 2 | WK 17 | P5 | W1 | P5W1 | FY18 | FY18P05
3 | 2017-12-19 | 3 | WK 17 | P5 | W1 | P5W1 | FY18 | FY18P05
4 | 2017-12-20 | 4 | WK 17 | P5 | W1 | P5W1 | FY18 | FY18P05
5 | 2017-12-21 | 5 | WK 17 | P5 | W1 | P5W1 | FY18 | FY18P05
6 | 2017-12-22 | 6 | WK 17 | P5 | W1 | P5W1 | FY18 | FY18P05
7 | 2017-12-23 | 7 | WK 17 | P5 | W1 | P5W1 | FY18 | FY18P05
8 | 2017-12-24 | 1 | WK 18 | P5 | W2 | P5W2 | FY18 | FY18P05
9 | 2017-12-25 | 2 | WK 18 | P5 | W2 | P5W2 | FY18 | FY18P05
10 | 2017-12-26 | 3 | WK 18 | P5 | W2 | P5W2 | FY18 | FY18P05
11 | 2017-12-27 | 4 | WK 18 | P5 | W2 | P5W2 | FY18 | FY18P05
12 | 2017-12-28 | 5 | WK 18 | P5 | W2 | P5W2 | FY18 | FY18P05
13 | 2017-12-29 | 6 | WK 18 | P5 | W2 | P5W2 | FY18 | FY18P05
14 | 2017-12-30 | 7 | WK 18 | P5 | W2 | P5W2 | FY18 | FY18P05
15 | 2017-12-31 | 1 | WK 19 | P5 | W3 | P5W3 | FY18 | FY18P05
16 | 2018-01-01 | 2 | WK 19 | P5 | W3 | P5W3 | FY18 | FY18P05
17 | 2018-01-02 | 3 | WK 19 | P5 | W3 | P5W3 | FY18 | FY18P05
18 | 2018-01-03 | 4 | WK 19 | P5 | W3 | P5W3 | FY18 | FY18P05
19 | 2018-01-04 | 5 | WK 19 | P5 | W3 | P5W3 | FY18 | FY18P05
20 | 2018-01-05 | 6 | WK 19 | P5 | W3 | P5W3 | FY18 | FY18P05
21 | 2018-01-06 | 7 | WK 19 | P5 | W3 | P5W3 | FY18 | FY18P05
22 | 2018-01-07 | 1 | WK 20 | P5 | W4 | P5W4 | FY18 | FY18P05
23 | 2018-01-08 | 2 | WK 20 | P5 | W4 | P5W4 | FY18 | FY18P05
24 | 2018-01-09 | 3 | WK 20 | P5 | W4 | P5W4 | FY18 | FY18P05
25 | 2018-01-10 | 4 | WK 20 | P5 | W4 | P5W4 | FY18 | FY18P05
26 | 2018-01-11 | 5 | WK 20 | P5 | W4 | P5W4 | FY18 | FY18P05
27 | 2018-01-12 | 6 | WK 20 | P5 | W4 | P5W4 | FY18 | FY18P05
28 | 2018-01-13 | 7 | WK 20 | P5 | W4 | P5W4 | FY18 | FY18P05
1 | 2018-01-14 | 1 | WK 21 | P6 | W1 | P6W1 | FY18 | FY18P06
2 | 2018-01-15 | 2 | WK 21 | P6 | W1 | P6W1 | FY18 | FY18P06
3 | 2018-01-16 | 3 | WK 21 | P6 | W1 | P6W1 | FY18 | FY18P06
4 | 2018-01-17 | 4 | WK 21 | P6 | W1 | P6W1 | FY18 | FY18P06
5 | 2018-01-18 | 5 | WK 21 | P6 | W1 | P6W1 | FY18 | FY18P06
6 | 2018-01-19 | 6 | WK 21 | P6 | W1 | P6W1 | FY18 | FY18P06
7 | 2018-01-20 | 7 | WK 21 | P6 | W1 | P6W1 | FY18 | FY18P06
8 | 2018-01-21 | 1 | WK 22 | P6 | W2 | P6W2 | FY18 | FY18P06
9 | 2018-01-22 | 2 | WK 22 | P6 | W2 | P6W2 | FY18 | FY18P06
10 | 2018-01-23 | 3 | WK 22 | P6 | W2 | P6W2 | FY18 | FY18P06
11 | 2018-01-24 | 4 | WK 22 | P6 | W2 | P6W2 | FY18 | FY18P06
12 | 2018-01-25 | 5 | WK 22 | P6 | W2 | P6W2 | FY18 | FY18P06
13 | 2018-01-26 | 6 | WK 22 | P6 | W2 | P6W2 | FY18 | FY18P06
14 | 2018-01-27 | 7 | WK 22 | P6 | W2 | P6W2 | FY18 | FY18P06
15 | 2018-01-28 | 1 | WK 23 | P6 | W3 | P6W3 | FY18 | FY18P06
16 | 2018-01-29 | 2 | WK 23 | P6 | W3 | P6W3 | FY18 | FY18P06
17 | 2018-01-30 | 3 | WK 23 | P6 | W3 | P6W3 | FY18 | FY18P06
18 | 2018-01-31 | 4 | WK 23 | P6 | W3 | P6W3 | FY18 | FY18P06
19 | 2018-02-01 | 5 | WK 23 | P6 | W3 | P6W3 | FY18 | FY18P06
20 | 2018-02-02 | 6 | WK 23 | P6 | W3 | P6W3 | FY18 | FY18P06
21 | 2018-02-03 | 7 | WK 23 | P6 | W3 | P6W3 | FY18 | FY18P06
22 | 2018-02-04 | 1 | WK 24 | P6 | W4 | P6W4 | FY18 | FY18P06
23 | 2018-02-05 | 2 | WK 24 | P6 | W4 | P6W4 | FY18 | FY18P06
24 | 2018-02-06 | 3 | WK 24 | P6 | W4 | P6W4 | FY18 | FY18P06
25 | 2018-02-07 | 4 | WK 24 | P6 | W4 | P6W4 | FY18 | FY18P06
26 | 2018-02-08 | 5 | WK 24 | P6 | W4 | P6W4 | FY18 | FY18P06
27 | 2018-02-09 | 6 | WK 24 | P6 | W4 | P6W4 | FY18 | FY18P06
28 | 2018-02-10 | 7 | WK 24 | P6 | W4 | P6W4 | FY18 | FY18P06
1 | 2018-02-11 | 1 | WK 25 | P7 | W1 | P7W1 | FY18 | FY18P07
2 | 2018-02-12 | 2 | WK 25 | P7 | W1 | P7W1 | FY18 | FY18P07
3 | 2018-02-13 | 3 | WK 25 | P7 | W1 | P7W1 | FY18 | FY18P07
4 | 2018-02-14 | 4 | WK 25 | P7 | W1 | P7W1 | FY18 | FY18P07
5 | 2018-02-15 | 5 | WK 25 | P7 | W1 | P7W1 | FY18 | FY18P07
6 | 2018-02-16 | 6 | WK 25 | P7 | W1 | P7W1 | FY18 | FY18P07
7 | 2018-02-17 | 7 | WK 25 | P7 | W1 | P7W1 | FY18 | FY18P07
8 | 2018-02-18 | 1 | WK 26 | P7 | W2 | P7W2 | FY18 | FY18P07
9 | 2018-02-19 | 2 | WK 26 | P7 | W2 | P7W2 | FY18 | FY18P07
10 | 2018-02-20 | 3 | WK 26 | P7 | W2 | P7W2 | FY18 | FY18P07
11 | 2018-02-21 | 4 | WK 26 | P7 | W2 | P7W2 | FY18 | FY18P07
12 | 2018-02-22 | 5 | WK 26 | P7 | W2 | P7W2 | FY18 | FY18P07
13 | 2018-02-23 | 6 | WK 26 | P7 | W2 | P7W2 | FY18 | FY18P07
14 | 2018-02-24 | 7 | WK 26 | P7 | W2 | P7W2 | FY18 | FY18P07
15 | 2018-02-25 | 1 | WK 27 | P7 | W3 | P7W3 | FY18 | FY18P07
16 | 2018-02-26 | 2 | WK 27 | P7 | W3 | P7W3 | FY18 | FY18P07
17 | 2018-02-27 | 3 | WK 27 | P7 | W3 | P7W3 | FY18 | FY18P07
18 | 2018-02-28 | 4 | WK 27 | P7 | W3 | P7W3 | FY18 | FY18P07
19 | 2018-03-01 | 5 | WK 27 | P7 | W3 | P7W3 | FY18 | FY18P07
20 | 2018-03-02 | 6 | WK 27 | P7 | W3 | P7W3 | FY18 | FY18P07
21 | 2018-03-03 | 7 | WK 27 | P7 | W3 | P7W3 | FY18 | FY18P07
22 | 2018-03-04 | 1 | WK 28 | P7 | W4 | P7W4 | FY18 | FY18P07
23 | 2018-03-05 | 2 | WK 28 | P7 | W4 | P7W4 | FY18 | FY18P07
24 | 2018-03-06 | 3 | WK 28 | P7 | W4 | P7W4 | FY18 | FY18P07
25 | 2018-03-07 | 4 | WK 28 | P7 | W4 | P7W4 | FY18 | FY18P07
26 | 2018-03-08 | 5 | WK 28 | P7 | W4 | P7W4 | FY18 | FY18P07
27 | 2018-03-09 | 6 | WK 28 | P7 | W4 | P7W4 | FY18 | FY18P07
28 | 2018-03-10 | 7 | WK 28 | P7 | W4 | P7W4 | FY18 | FY18P07
1 | 2018-03-11 | 1 | WK 29 | P8 | W1 | P8W1 | FY18 | FY18P08
2 | 2018-03-12 | 2 | WK 29 | P8 | W1 | P8W1 | FY18 | FY18P08
3 | 2018-03-13 | 3 | WK 29 | P8 | W1 | P8W1 | FY18 | FY18P08
4 | 2018-03-14 | 4 | WK 29 | P8 | W1 | P8W1 | FY18 | FY18P08
5 | 2018-03-15 | 5 | WK 29 | P8 | W1 | P8W1 | FY18 | FY18P08
6 | 2018-03-16 | 6 | WK 29 | P8 | W1 | P8W1 | FY18 | FY18P08
7 | 2018-03-17 | 7 | WK 29 | P8 | W1 | P8W1 | FY18 | FY18P08
8 | 2018-03-18 | 1 | WK 30 | P8 | W2 | P8W2 | FY18 | FY18P08
9 | 2018-03-19 | 2 | WK 30 | P8 | W2 | P8W2 | FY18 | FY18P08
10 | 2018-03-20 | 3 | WK 30 | P8 | W2 | P8W2 | FY18 | FY18P08
11 | 2018-03-21 | 4 | WK 30 | P8 | W2 | P8W2 | FY18 | FY18P08
12 | 2018-03-22 | 5 | WK 30 | P8 | W2 | P8W2 | FY18 | FY18P08
13 | 2018-03-23 | 6 | WK 30 | P8 | W2 | P8W2 | FY18 | FY18P08
14 | 2018-03-24 | 7 | WK 30 | P8 | W2 | P8W2 | FY18 | FY18P08
15 | 2018-03-25 | 1 | WK 31 | P8 | W3 | P8W3 | FY18 | FY18P08
16 | 2018-03-26 | 2 | WK 31 | P8 | W3 | P8W3 | FY18 | FY18P08
17 | 2018-03-27 | 3 | WK 31 | P8 | W3 | P8W3 | FY18 | FY18P08
18 | 2018-03-28 | 4 | WK 31 | P8 | W3 | P8W3 | FY18 | FY18P08
19 | 2018-03-29 | 5 | WK 31 | P8 | W3 | P8W3 | FY18 | FY18P08
20 | 2018-03-30 | 6 | WK 31 | P8 | W3 | P8W3 | FY18 | FY18P08
21 | 2018-03-31 | 7 | WK 31 | P8 | W3 | P8W3 | FY18 | FY18P08
22 | 2018-04-01 | 1 | WK 32 | P8 | W4 | P8W4 | FY18 | FY18P08
23 | 2018-04-02 | 2 | WK 32 | P8 | W4 | P8W4 | FY18 | FY18P08
24 | 2018-04-03 | 3 | WK 32 | P8 | W4 | P8W4 | FY18 | FY18P08
25 | 2018-04-04 | 4 | WK 32 | P8 | W4 | P8W4 | FY18 | FY18P08
26 | 2018-04-05 | 5 | WK 32 | P8 | W4 | P8W4 | FY18 | FY18P08
27 | 2018-04-06 | 6 | WK 32 | P8 | W4 | P8W4 | FY18 | FY18P08
28 | 2018-04-07 | 7 | WK 32 | P8 | W4 | P8W4 | FY18 | FY18P08
1 | 2018-04-08 | 1 | WK 33 | P9 | W1 | P9W1 | FY18 | FY18P09
2 | 2018-04-09 | 2 | WK 33 | P9 | W1 | P9W1 | FY18 | FY18P09
3 | 2018-04-10 | 3 | WK 33 | P9 | W1 | P9W1 | FY18 | FY18P09
4 | 2018-04-11 | 4 | WK 33 | P9 | W1 | P9W1 | FY18 | FY18P09
5 | 2018-04-12 | 5 | WK 33 | P9 | W1 | P9W1 | FY18 | FY18P09
6 | 2018-04-13 | 6 | WK 33 | P9 | W1 | P9W1 | FY18 | FY18P09
7 | 2018-04-14 | 7 | WK 33 | P9 | W1 | P9W1 | FY18 | FY18P09
8 | 2018-04-15 | 1 | WK 34 | P9 | W2 | P9W2 | FY18 | FY18P09
9 | 2018-04-16 | 2 | WK 34 | P9 | W2 | P9W2 | FY18 | FY18P09
10 | 2018-04-17 | 3 | WK 34 | P9 | W2 | P9W2 | FY18 | FY18P09
11 | 2018-04-18 | 4 | WK 34 | P9 | W2 | P9W2 | FY18 | FY18P09
12 | 2018-04-19 | 5 | WK 34 | P9 | W2 | P9W2 | FY18 | FY18P09
13 | 2018-04-20 | 6 | WK 34 | P9 | W2 | P9W2 | FY18 | FY18P09
14 | 2018-04-21 | 7 | WK 34 | P9 | W2 | P9W2 | FY18 | FY18P09
15 | 2018-04-22 | 1 | WK 35 | P9 | W3 | P9W3 | FY18 | FY18P09
16 | 2018-04-23 | 2 | WK 35 | P9 | W3 | P9W3 | FY18 | FY18P09
17 | 2018-04-24 | 3 | WK 35 | P9 | W3 | P9W3 | FY18 | FY18P09
18 | 2018-04-25 | 4 | WK 35 | P9 | W3 | P9W3 | FY18 | FY18P09
19 | 2018-04-26 | 5 | WK 35 | P9 | W3 | P9W3 | FY18 | FY18P09
20 | 2018-04-27 | 6 | WK 35 | P9 | W3 | P9W3 | FY18 | FY18P09
21 | 2018-04-28 | 7 | WK 35 | P9 | W3 | P9W3 | FY18 | FY18P09
22 | 2018-04-29 | 1 | WK 36 | P9 | W4 | P9W4 | FY18 | FY18P09
23 | 2018-04-30 | 2 | WK 36 | P9 | W4 | P9W4 | FY18 | FY18P09
24 | 2018-05-01 | 3 | WK 36 | P9 | W4 | P9W4 | FY18 | FY18P09
25 | 2018-05-02 | 4 | WK 36 | P9 | W4 | P9W4 | FY18 | FY18P09
26 | 2018-05-03 | 5 | WK 36 | P9 | W4 | P9W4 | FY18 | FY18P09
27 | 2018-05-04 | 6 | WK 36 | P9 | W4 | P9W4 | FY18 | FY18P09
28 | 2018-05-05 | 7 | WK 36 | P9 | W4 | P9W4 | FY18 | FY18P09
1 | 2018-05-06 | 1 | WK 37 | P10 | W1 | P10W1 | FY18 | FY18P10
2 | 2018-05-07 | 2 | WK 37 | P10 | W1 | P10W1 | FY18 | FY18P10
3 | 2018-05-08 | 3 | WK 37 | P10 | W1 | P10W1 | FY18 | FY18P10
4 | 2018-05-09 | 4 | WK 37 | P10 | W1 | P10W1 | FY18 | FY18P10
5 | 2018-05-10 | 5 | WK 37 | P10 | W1 | P10W1 | FY18 | FY18P10
6 | 2018-05-11 | 6 | WK 37 | P10 | W1 | P10W1 | FY18 | FY18P10
7 | 2018-05-12 | 7 | WK 37 | P10 | W1 | P10W1 | FY18 | FY18P10
8 | 2018-05-13 | 1 | WK 38 | P10 | W2 | P10W2 | FY18 | FY18P10
9 | 2018-05-14 | 2 | WK 38 | P10 | W2 | P10W2 | FY18 | FY18P10
10 | 2018-05-15 | 3 | WK 38 | P10 | W2 | P10W2 | FY18 | FY18P10
11 | 2018-05-16 | 4 | WK 38 | P10 | W2 | P10W2 | FY18 | FY18P10
12 | 2018-05-17 | 5 | WK 38 | P10 | W2 | P10W2 | FY18 | FY18P10
13 | 2018-05-18 | 6 | WK 38 | P10 | W2 | P10W2 | FY18 | FY18P10
14 | 2018-05-19 | 7 | WK 38 | P10 | W2 | P10W2 | FY18 | FY18P10
15 | 2018-05-20 | 1 | WK 39 | P10 | W3 | P10W3 | FY18 | FY18P10
16 | 2018-05-21 | 2 | WK 39 | P10 | W3 | P10W3 | FY18 | FY18P10
17 | 2018-05-22 | 3 | WK 39 | P10 | W3 | P10W3 | FY18 | FY18P10
18 | 2018-05-23 | 4 | WK 39 | P10 | W3 | P10W3 | FY18 | FY18P10
19 | 2018-05-24 | 5 | WK 39 | P10 | W3 | P10W3 | FY18 | FY18P10
20 | 2018-05-25 | 6 | WK 39 | P10 | W3 | P10W3 | FY18 | FY18P10
21 | 2018-05-26 | 7 | WK 39 | P10 | W3 | P10W3 | FY18 | FY18P10
22 | 2018-05-27 | 1 | WK 40 | P10 | W4 | P10W4 | FY18 | FY18P10
23 | 2018-05-28 | 2 | WK 40 | P10 | W4 | P10W4 | FY18 | FY18P10
24 | 2018-05-29 | 3 | WK 40 | P10 | W4 | P10W4 | FY18 | FY18P10
25 | 2018-05-30 | 4 | WK 40 | P10 | W4 | P10W4 | FY18 | FY18P10
26 | 2018-05-31 | 5 | WK 40 | P10 | W4 | P10W4 | FY18 | FY18P10
27 | 2018-06-01 | 6 | WK 40 | P10 | W4 | P10W4 | FY18 | FY18P10
28 | 2018-06-02 | 7 | WK 40 | P10 | W4 | P10W4 | FY18 | FY18P10
1 | 2018-06-03 | 1 | WK 41 | P11 | W1 | P11W1 | FY18 | FY18P11
2 | 2018-06-04 | 2 | WK 41 | P11 | W1 | P11W1 | FY18 | FY18P11
3 | 2018-06-05 | 3 | WK 41 | P11 | W1 | P11W1 | FY18 | FY18P11
4 | 2018-06-06 | 4 | WK 41 | P11 | W1 | P11W1 | FY18 | FY18P11
5 | 2018-06-07 | 5 | WK 41 | P11 | W1 | P11W1 | FY18 | FY18P11
6 | 2018-06-08 | 6 | WK 41 | P11 | W1 | P11W1 | FY18 | FY18P11
7 | 2018-06-09 | 7 | WK 41 | P11 | W1 | P11W1 | FY18 | FY18P11
8 | 2018-06-10 | 1 | WK 42 | P11 | W2 | P11W2 | FY18 | FY18P11
9 | 2018-06-11 | 2 | WK 42 | P11 | W2 | P11W2 | FY18 | FY18P11
10 | 2018-06-12 | 3 | WK 42 | P11 | W2 | P11W2 | FY18 | FY18P11
11 | 2018-06-13 | 4 | WK 42 | P11 | W2 | P11W2 | FY18 | FY18P11
12 | 2018-06-14 | 5 | WK 42 | P11 | W2 | P11W2 | FY18 | FY18P11
13 | 2018-06-15 | 6 | WK 42 | P11 | W2 | P11W2 | FY18 | FY18P11
14 | 2018-06-16 | 7 | WK 42 | P11 | W2 | P11W2 | FY18 | FY18P11
15 | 2018-06-17 | 1 | WK 43 | P11 | W3 | P11W3 | FY18 | FY18P11
16 | 2018-06-18 | 2 | WK 43 | P11 | W3 | P11W3 | FY18 | FY18P11
17 | 2018-06-19 | 3 | WK 43 | P11 | W3 | P11W3 | FY18 | FY18P11
18 | 2018-06-20 | 4 | WK 43 | P11 | W3 | P11W3 | FY18 | FY18P11
19 | 2018-06-21 | 5 | WK 43 | P11 | W3 | P11W3 | FY18 | FY18P11
20 | 2018-06-22 | 6 | WK 43 | P11 | W3 | P11W3 | FY18 | FY18P11
21 | 2018-06-23 | 7 | WK 43 | P11 | W3 | P11W3 | FY18 | FY18P11
22 | 2018-06-24 | 1 | WK 44 | P11 | W4 | P11W4 | FY18 | FY18P11
23 | 2018-06-25 | 2 | WK 44 | P11 | W4 | P11W4 | FY18 | FY18P11
24 | 2018-06-26 | 3 | WK 44 | P11 | W4 | P11W4 | FY18 | FY18P11
25 | 2018-06-27 | 4 | WK 44 | P11 | W4 | P11W4 | FY18 | FY18P11
26 | 2018-06-28 | 5 | WK 44 | P11 | W4 | P11W4 | FY18 | FY18P11
27 | 2018-06-29 | 6 | WK 44 | P11 | W4 | P11W4 | FY18 | FY18P11
28 | 2018-06-30 | 7 | WK 44 | P11 | W4 | P11W4 | FY18 | FY18P11
1 | 2018-07-01 | 1 | WK 45 | P12 | W1 | P12W1 | FY18 | FY18P12
2 | 2018-07-02 | 2 | WK 45 | P12 | W1 | P12W1 | FY18 | FY18P12
3 | 2018-07-03 | 3 | WK 45 | P12 | W1 | P12W1 | FY18 | FY18P12
4 | 2018-07-04 | 4 | WK 45 | P12 | W1 | P12W1 | FY18 | FY18P12
5 | 2018-07-05 | 5 | WK 45 | P12 | W1 | P12W1 | FY18 | FY18P12
6 | 2018-07-06 | 6 | WK 45 | P12 | W1 | P12W1 | FY18 | FY18P12
7 | 2018-07-07 | 7 | WK 45 | P12 | W1 | P12W1 | FY18 | FY18P12
8 | 2018-07-08 | 1 | WK 46 | P12 | W2 | P12W2 | FY18 | FY18P12
9 | 2018-07-09 | 2 | WK 46 | P12 | W2 | P12W2 | FY18 | FY18P12
10 | 2018-07-10 | 3 | WK 46 | P12 | W2 | P12W2 | FY18 | FY18P12
11 | 2018-07-11 | 4 | WK 46 | P12 | W2 | P12W2 | FY18 | FY18P12
12 | 2018-07-12 | 5 | WK 46 | P12 | W2 | P12W2 | FY18 | FY18P12
13 | 2018-07-13 | 6 | WK 46 | P12 | W2 | P12W2 | FY18 | FY18P12
14 | 2018-07-14 | 7 | WK 46 | P12 | W2 | P12W2 | FY18 | FY18P12
15 | 2018-07-15 | 1 | WK 47 | P12 | W3 | P12W3 | FY18 | FY18P12
16 | 2018-07-16 | 2 | WK 47 | P12 | W3 | P12W3 | FY18 | FY18P12
17 | 2018-07-17 | 3 | WK 47 | P12 | W3 | P12W3 | FY18 | FY18P12
18 | 2018-07-18 | 4 | WK 47 | P12 | W3 | P12W3 | FY18 | FY18P12
19 | 2018-07-19 | 5 | WK 47 | P12 | W3 | P12W3 | FY18 | FY18P12
20 | 2018-07-20 | 6 | WK 47 | P12 | W3 | P12W3 | FY18 | FY18P12
21 | 2018-07-21 | 7 | WK 47 | P12 | W3 | P12W3 | FY18 | FY18P12
22 | 2018-07-22 | 1 | WK 48 | P12 | W4 | P12W4 | FY18 | FY18P12
23 | 2018-07-23 | 2 | WK 48 | P12 | W4 | P12W4 | FY18 | FY18P12
24 | 2018-07-24 | 3 | WK 48 | P12 | W4 | P12W4 | FY18 | FY18P12
25 | 2018-07-25 | 4 | WK 48 | P12 | W4 | P12W4 | FY18 | FY18P12
26 | 2018-07-26 | 5 | WK 48 | P12 | W4 | P12W4 | FY18 | FY18P12
27 | 2018-07-27 | 6 | WK 48 | P12 | W4 | P12W4 | FY18 | FY18P12
28 | 2018-07-28 | 7 | WK 48 | P12 | W4 | P12W4 | FY18 | FY18P12
1 | 2018-07-29 | 1 | WK 49 | P13 | W1 | P13W1 | FY18 | FY18P13
2 | 2018-07-30 | 2 | WK 49 | P13 | W1 | P13W1 | FY18 | FY18P13
3 | 2018-07-31 | 3 | WK 49 | P13 | W1 | P13W1 | FY18 | FY18P13
4 | 2018-08-01 | 4 | WK 49 | P13 | W1 | P13W1 | FY18 | FY18P13
5 | 2018-08-02 | 5 | WK 49 | P13 | W1 | P13W1 | FY18 | FY18P13
6 | 2018-08-03 | 6 | WK 49 | P13 | W1 | P13W1 | FY18 | FY18P13
7 | 2018-08-04 | 7 | WK 49 | P13 | W1 | P13W1 | FY18 | FY18P13
8 | 2018-08-05 | 1 | WK 50 | P13 | W2 | P13W2 | FY18 | FY18P13
9 | 2018-08-06 | 2 | WK 50 | P13 | W2 | P13W2 | FY18 | FY18P13
10 | 2018-08-07 | 3 | WK 50 | P13 | W2 | P13W2 | FY18 | FY18P13
11 | 2018-08-08 | 4 | WK 50 | P13 | W2 | P13W2 | FY18 | FY18P13
12 | 2018-08-09 | 5 | WK 50 | P13 | W2 | P13W2 | FY18 | FY18P13
13 | 2018-08-10 | 6 | WK 50 | P13 | W2 | P13W2 | FY18 | FY18P13
14 | 2018-08-11 | 7 | WK 50 | P13 | W2 | P13W2 | FY18 | FY18P13
15 | 2018-08-12 | 1 | WK 51 | P13 | W3 | P13W3 | FY18 | FY18P13
16 | 2018-08-13 | 2 | WK 51 | P13 | W3 | P13W3 | FY18 | FY18P13
17 | 2018-08-14 | 3 | WK 51 | P13 | W3 | P13W3 | FY18 | FY18P13
18 | 2018-08-15 | 4 | WK 51 | P13 | W3 | P13W3 | FY18 | FY18P13
19 | 2018-08-16 | 5 | WK 51 | P13 | W3 | P13W3 | FY18 | FY18P13
20 | 2018-08-17 | 6 | WK 51 | P13 | W3 | P13W3 | FY18 | FY18P13
21 | 2018-08-18 | 7 | WK 51 | P13 | W3 | P13W3 | FY18 | FY18P13
22 | 2018-08-19 | 1 | WK 52 | P13 | W4 | P13W4 | FY18 | FY18P13
23 | 2018-08-20 | 2 | WK 52 | P13 | W4 | P13W4 | FY18 | FY18P13
24 | 2018-08-21 | 3 | WK 52 | P13 | W4 | P13W4 | FY18 | FY18P13
25 | 2018-08-22 | 4 | WK 52 | P13 | W4 | P13W4 | FY18 | FY18P13
26 | 2018-08-23 | 5 | WK 52 | P13 | W4 | P13W4 | FY18 | FY18P13
27 | 2018-08-24 | 6 | WK 52 | P13 | W4 | P13W4 | FY18 | FY18P13
28 | 2018-08-25 | 7 | WK 52 | P13 | W4 | P13W4 | FY18 | FY18P13
1 | 2018-08-26 | 1 | WK 1 | P1 | W1 | P1W1 | FY19 | FY19P1
2 | 2018-08-27 | 2 | WK 1 | P1 | W1 | P1W1 | FY19 | FY19P1
3 | 2018-08-28 | 3 | WK 1 | P1 | W1 | P1W1 | FY19 | FY19P1
4 | 2018-08-29 | 4 | WK 1 | P1 | W1 | P1W1 | FY19 | FY19P1
5 | 2018-08-30 | 5 | WK 1 | P1 | W1 | P1W1 | FY19 | FY19P1
6 | 2018-08-31 | 6 | WK 1 | P1 | W1 | P1W1 | FY19 | FY19P1
7 | 2018-09-01 | 7 | WK 1 | P1 | W1 | P1W1 | FY19 | FY19P1
8 | 2018-09-02 | 1 | WK 2 | P1 | W2 | P1W2 | FY19 | FY19P1
9 | 2018-09-03 | 2 | WK 2 | P1 | W2 | P1W2 | FY19 | FY19P1
10 | 2018-09-04 | 3 | WK 2 | P1 | W2 | P1W2 | FY19 | FY19P1
11 | 2018-09-05 | 4 | WK 2 | P1 | W2 | P1W2 | FY19 | FY19P1
12 | 2018-09-06 | 5 | WK 2 | P1 | W2 | P1W2 | FY19 | FY19P1
13 | 2018-09-07 | 6 | WK 2 | P1 | W2 | P1W2 | FY19 | FY19P1
14 | 2018-09-08 | 7 | WK 2 | P1 | W2 | P1W2 | FY19 | FY19P1
15 | 2018-09-09 | 1 | WK 3 | P1 | W3 | P1W3 | FY19 | FY19P1
16 | 2018-09-10 | 2 | WK 3 | P1 | W3 | P1W3 | FY19 | FY19P1
17 | 2018-09-11 | 3 | WK 3 | P1 | W3 | P1W3 | FY19 | FY19P1
18 | 2018-09-12 | 4 | WK 3 | P1 | W3 | P1W3 | FY19 | FY19P1
19 | 2018-09-13 | 5 | WK 3 | P1 | W3 | P1W3 | FY19 | FY19P1
20 | 2018-09-14 | 6 | WK 3 | P1 | W3 | P1W3 | FY19 | FY19P1
21 | 2018-09-15 | 7 | WK 3 | P1 | W3 | P1W3 | FY19 | FY19P1
22 | 2018-09-16 | 1 | WK 4 | P1 | W4 | P1W4 | FY19 | FY19P1
23 | 2018-09-17 | 2 | WK 4 | P1 | W4 | P1W4 | FY19 | FY19P1
24 | 2018-09-18 | 3 | WK 4 | P1 | W4 | P1W4 | FY19 | FY19P1
25 | 2018-09-19 | 4 | WK 4 | P1 | W4 | P1W4 | FY19 | FY19P1
26 | 2018-09-20 | 5 | WK 4 | P1 | W4 | P1W4 | FY19 | FY19P1
27 | 2018-09-21 | 6 | WK 4 | P1 | W4 | P1W4 | FY19 | FY19P1
28 | 2018-09-22 | 7 | WK 4 | P1 | W4 | P1W4 | FY19 | FY19P1
1 | 2018-09-23 | 1 | WK 5 | P2 | W1 | P2W1 | FY19 | FY19P2
2 | 2018-09-24 | 2 | WK 5 | P2 | W1 | P2W1 | FY19 | FY19P2
3 | 2018-09-25 | 3 | WK 5 | P2 | W1 | P2W1 | FY19 | FY19P2
4 | 2018-09-26 | 4 | WK 5 | P2 | W1 | P2W1 | FY19 | FY19P2
5 | 2018-09-27 | 5 | WK 5 | P2 | W1 | P2W1 | FY19 | FY19P2
6 | 2018-09-28 | 6 | WK 5 | P2 | W1 | P2W1 | FY19 | FY19P2
7 | 2018-09-29 | 7 | WK 5 | P2 | W1 | P2W1 | FY19 | FY19P2
8 | 2018-09-30 | 1 | WK 6 | P2 | W2 | P2W2 | FY19 | FY19P2
9 | 2018-10-01 | 2 | WK 6 | P2 | W2 | P2W2 | FY19 | FY19P2
10 | 2018-10-02 | 3 | WK 6 | P2 | W2 | P2W2 | FY19 | FY19P2
11 | 2018-10-03 | 4 | WK 6 | P2 | W2 | P2W2 | FY19 | FY19P2
12 | 2018-10-04 | 5 | WK 6 | P2 | W2 | P2W2 | FY19 | FY19P2
13 | 2018-10-05 | 6 | WK 6 | P2 | W2 | P2W2 | FY19 | FY19P2
14 | 2018-10-06 | 7 | WK 6 | P2 | W2 | P2W2 | FY19 | FY19P2
15 | 2018-10-07 | 1 | WK 7 | P2 | W3 | P2W3 | FY19 | FY19P2
16 | 2018-10-08 | 2 | WK 7 | P2 | W3 | P2W3 | FY19 | FY19P2
17 | 2018-10-09 | 3 | WK 7 | P2 | W3 | P2W3 | FY19 | FY19P2
18 | 2018-10-10 | 4 | WK 7 | P2 | W3 | P2W3 | FY19 | FY19P2
19 | 2018-10-11 | 5 | WK 7 | P2 | W3 | P2W3 | FY19 | FY19P2
20 | 2018-10-12 | 6 | WK 7 | P2 | W3 | P2W3 | FY19 | FY19P2
21 | 2018-10-13 | 7 | WK 7 | P2 | W3 | P2W3 | FY19 | FY19P2
22 | 2018-10-14 | 1 | WK 8 | P2 | W4 | P2W4 | FY19 | FY19P2
23 | 2018-10-15 | 2 | WK 8 | P2 | W4 | P2W4 | FY19 | FY19P2
24 | 2018-10-16 | 3 | WK 8 | P2 | W4 | P2W4 | FY19 | FY19P2
25 | 2018-10-17 | 4 | WK 8 | P2 | W4 | P2W4 | FY19 | FY19P2
26 | 2018-10-18 | 5 | WK 8 | P2 | W4 | P2W4 | FY19 | FY19P2
27 | 2018-10-19 | 6 | WK 8 | P2 | W4 | P2W4 | FY19 | FY19P2
28 | 2018-10-20 | 7 | WK 8 | P2 | W4 | P2W4 | FY19 | FY19P2
1 | 2018-10-21 | 1 | WK 9 | P3 | W1 | P3W1 | FY19 | FY19P3
2 | 2018-10-22 | 2 | WK 9 | P3 | W1 | P3W1 | FY19 | FY19P3
3 | 2018-10-23 | 3 | WK 9 | P3 | W1 | P3W1 | FY19 | FY19P3
4 | 2018-10-24 | 4 | WK 9 | P3 | W1 | P3W1 | FY19 | FY19P3
5 | 2018-10-25 | 5 | WK 9 | P3 | W1 | P3W1 | FY19 | FY19P3
6 | 2018-10-26 | 6 | WK 9 | P3 | W1 | P3W1 | FY19 | FY19P3
7 | 2018-10-27 | 7 | WK 9 | P3 | W1 | P3W1 | FY19 | FY19P3
8 | 2018-10-28 | 1 | WK 10 | P3 | W2 | P3W2 | FY19 | FY19P3
9 | 2018-10-29 | 2 | WK 10 | P3 | W2 | P3W2 | FY19 | FY19P3
10 | 2018-10-30 | 3 | WK 10 | P3 | W2 | P3W2 | FY19 | FY19P3
11 | 2018-10-31 | 4 | WK 10 | P3 | W2 | P3W2 | FY19 | FY19P3
12 | 2018-11-01 | 5 | WK 10 | P3 | W2 | P3W2 | FY19 | FY19P3
13 | 2018-11-02 | 6 | WK 10 | P3 | W2 | P3W2 | FY19 | FY19P3
14 | 2018-11-03 | 7 | WK 10 | P3 | W2 | P3W2 | FY19 | FY19P3
15 | 2018-11-04 | 1 | WK 11 | P3 | W3 | P3W3 | FY19 | FY19P3
16 | 2018-11-05 | 2 | WK 11 | P3 | W3 | P3W3 | FY19 | FY19P3
17 | 2018-11-06 | 3 | WK 11 | P3 | W3 | P3W3 | FY19 | FY19P3
18 | 2018-11-07 | 4 | WK 11 | P3 | W3 | P3W3 | FY19 | FY19P3
19 | 2018-11-08 | 5 | WK 11 | P3 | W3 | P3W3 | FY19 | FY19P3
20 | 2018-11-09 | 6 | WK 11 | P3 | W3 | P3W3 | FY19 | FY19P3
21 | 2018-11-10 | 7 | WK 11 | P3 | W3 | P3W3 | FY19 | FY19P3
22 | 2018-11-11 | 1 | WK 12 | P3 | W4 | P3W4 | FY19 | FY19P3
23 | 2018-11-12 | 2 | WK 12 | P3 | W4 | P3W4 | FY19 | FY19P3
24 | 2018-11-13 | 3 | WK 12 | P3 | W4 | P3W4 | FY19 | FY19P3
25 | 2018-11-14 | 4 | WK 12 | P3 | W4 | P3W4 | FY19 | FY19P3
26 | 2018-11-15 | 5 | WK 12 | P3 | W4 | P3W4 | FY19 | FY19P3
27 | 2018-11-16 | 6 | WK 12 | P3 | W4 | P3W4 | FY19 | FY19P3
28 | 2018-11-17 | 7 | WK 12 | P3 | W4 | P3W4 | FY19 | FY19P3
1 | 2018-11-18 | 1 | WK 13 | P4 | W1 | P4W1 | FY19 | FY19P4
2 | 2018-11-19 | 2 | WK 13 | P4 | W1 | P4W1 | FY19 | FY19P4
3 | 2018-11-20 | 3 | WK 13 | P4 | W1 | P4W1 | FY19 | FY19P4
4 | 2018-11-21 | 4 | WK 13 | P4 | W1 | P4W1 | FY19 | FY19P4
5 | 2018-11-22 | 5 | WK 13 | P4 | W1 | P4W1 | FY19 | FY19P4
6 | 2018-11-23 | 6 | WK 13 | P4 | W1 | P4W1 | FY19 | FY19P4
7 | 2018-11-24 | 7 | WK 13 | P4 | W1 | P4W1 | FY19 | FY19P4
8 | 2018-11-25 | 1 | WK 14 | P4 | W2 | P4W2 | FY19 | FY19P4
9 | 2018-11-26 | 2 | WK 14 | P4 | W2 | P4W2 | FY19 | FY19P4
10 | 2018-11-27 | 3 | WK 14 | P4 | W2 | P4W2 | FY19 | FY19P4
11 | 2018-11-28 | 4 | WK 14 | P4 | W2 | P4W2 | FY19 | FY19P4
12 | 2018-11-29 | 5 | WK 14 | P4 | W2 | P4W2 | FY19 | FY19P4
13 | 2018-11-30 | 6 | WK 14 | P4 | W2 | P4W2 | FY19 | FY19P4
14 | 2018-12-01 | 7 | WK 14 | P4 | W2 | P4W2 | FY19 | FY19P4
15 | 2018-12-02 | 1 | WK 15 | P4 | W3 | P4W3 | FY19 | FY19P4
16 | 2018-12-03 | 2 | WK 15 | P4 | W3 | P4W3 | FY19 | FY19P4
17 | 2018-12-04 | 3 | WK 15 | P4 | W3 | P4W3 | FY19 | FY19P4
18 | 2018-12-05 | 4 | WK 15 | P4 | W3 | P4W3 | FY19 | FY19P4
19 | 2018-12-06 | 5 | WK 15 | P4 | W3 | P4W3 | FY19 | FY19P4
20 | 2018-12-07 | 6 | WK 15 | P4 | W3 | P4W3 | FY19 | FY19P4
21 | 2018-12-08 | 7 | WK 15 | P4 | W3 | P4W3 | FY19 | FY19P4
22 | 2018-12-09 | 1 | WK 16 | P4 | W4 | P4W4 | FY19 | FY19P4
23 | 2018-12-10 | 2 | WK 16 | P4 | W4 | P4W4 | FY19 | FY19P4
24 | 2018-12-11 | 3 | WK 16 | P4 | W4 | P4W4 | FY19 | FY19P4
25 | 2018-12-12 | 4 | WK 16 | P4 | W4 | P4W4 | FY19 | FY19P4
26 | 2018-12-13 | 5 | WK 16 | P4 | W4 | P4W4 | FY19 | FY19P4
27 | 2018-12-14 | 6 | WK 16 | P4 | W4 | P4W4 | FY19 | FY19P4
28 | 2018-12-15 | 7 | WK 16 | P4 | W4 | P4W4 | FY19 | FY19P4
1 | 2018-12-16 | 1 | WK 17 | P5 | W1 | P5W1 | FY19 | FY19P5
2 | 2018-12-17 | 2 | WK 17 | P5 | W1 | P5W1 | FY19 | FY19P5
3 | 2018-12-18 | 3 | WK 17 | P5 | W1 | P5W1 | FY19 | FY19P5
4 | 2018-12-19 | 4 | WK 17 | P5 | W1 | P5W1 | FY19 | FY19P5
5 | 2018-12-20 | 5 | WK 17 | P5 | W1 | P5W1 | FY19 | FY19P5
6 | 2018-12-21 | 6 | WK 17 | P5 | W1 | P5W1 | FY19 | FY19P5
7 | 2018-12-22 | 7 | WK 17 | P5 | W1 | P5W1 | FY19 | FY19P5
8 | 2018-12-23 | 1 | WK 18 | P5 | W2 | P5W2 | FY19 | FY19P5
9 | 2018-12-24 | 2 | WK 18 | P5 | W2 | P5W2 | FY19 | FY19P5
10 | 2018-12-25 | 3 | WK 18 | P5 | W2 | P5W2 | FY19 | FY19P5
11 | 2018-12-26 | 4 | WK 18 | P5 | W2 | P5W2 | FY19 | FY19P5
12 | 2018-12-27 | 5 | WK 18 | P5 | W2 | P5W2 | FY19 | FY19P5
13 | 2018-12-28 | 6 | WK 18 | P5 | W2 | P5W2 | FY19 | FY19P5
14 | 2018-12-29 | 7 | WK 18 | P5 | W2 | P5W2 | FY19 | FY19P5
15 | 2018-12-30 | 1 | WK 19 | P5 | W3 | P5W3 | FY19 | FY19P5
16 | 2018-12-31 | 2 | WK 19 | P5 | W3 | P5W3 | FY19 | FY19P5
17 | 2019-01-01 | 3 | WK 19 | P5 | W3 | P5W3 | FY19 | FY19P5
18 | 2019-01-02 | 4 | WK 19 | P5 | W3 | P5W3 | FY19 | FY19P5
19 | 2019-01-03 | 5 | WK 19 | P5 | W3 | P5W3 | FY19 | FY19P5
20 | 2019-01-04 | 6 | WK 19 | P5 | W3 | P5W3 | FY19 | FY19P5
21 | 2019-01-05 | 7 | WK 19 | P5 | W3 | P5W3 | FY19 | FY19P5
22 | 2019-01-06 | 1 | WK 20 | P5 | W4 | P5W4 | FY19 | FY19P5
23 | 2019-01-07 | 2 | WK 20 | P5 | W4 | P5W4 | FY19 | FY19P5
24 | 2019-01-08 | 3 | WK 20 | P5 | W4 | P5W4 | FY19 | FY19P5
25 | 2019-01-09 | 4 | WK 20 | P5 | W4 | P5W4 | FY19 | FY19P5
26 | 2019-01-10 | 5 | WK 20 | P5 | W4 | P5W4 | FY19 | FY19P5
27 | 2019-01-11 | 6 | WK 20 | P5 | W4 | P5W4 | FY19 | FY19P5
28 | 2019-01-12 | 7 | WK 20 | P5 | W4 | P5W4 | FY19 | FY19P5
1 | 2019-01-13 | 1 | WK 21 | P6 | W1 | P6W1 | FY19 | FY19P6
2 | 2019-01-14 | 2 | WK 21 | P6 | W1 | P6W1 | FY19 | FY19P6
3 | 2019-01-15 | 3 | WK 21 | P6 | W1 | P6W1 | FY19 | FY19P6
4 | 2019-01-16 | 4 | WK 21 | P6 | W1 | P6W1 | FY19 | FY19P6
5 | 2019-01-17 | 5 | WK 21 | P6 | W1 | P6W1 | FY19 | FY19P6
6 | 2019-01-18 | 6 | WK 21 | P6 | W1 | P6W1 | FY19 | FY19P6
7 | 2019-01-19 | 7 | WK 21 | P6 | W1 | P6W1 | FY19 | FY19P6
8 | 2019-01-20 | 1 | WK 22 | P6 | W2 | P6W2 | FY19 | FY19P6
9 | 2019-01-21 | 2 | WK 22 | P6 | W2 | P6W2 | FY19 | FY19P6
10 | 2019-01-22 | 3 | WK 22 | P6 | W2 | P6W2 | FY19 | FY19P6
11 | 2019-01-23 | 4 | WK 22 | P6 | W2 | P6W2 | FY19 | FY19P6
12 | 2019-01-24 | 5 | WK 22 | P6 | W2 | P6W2 | FY19 | FY19P6
13 | 2019-01-25 | 6 | WK 22 | P6 | W2 | P6W2 | FY19 | FY19P6
14 | 2019-01-26 | 7 | WK 22 | P6 | W2 | P6W2 | FY19 | FY19P6
15 | 2019-01-27 | 1 | WK 23 | P6 | W3 | P6W3 | FY19 | FY19P6
16 | 2019-01-28 | 2 | WK 23 | P6 | W3 | P6W3 | FY19 | FY19P6
17 | 2019-01-29 | 3 | WK 23 | P6 | W3 | P6W3 | FY19 | FY19P6
18 | 2019-01-30 | 4 | WK 23 | P6 | W3 | P6W3 | FY19 | FY19P6
19 | 2019-01-31 | 5 | WK 23 | P6 | W3 | P6W3 | FY19 | FY19P6
20 | 2019-02-01 | 6 | WK 23 | P6 | W3 | P6W3 | FY19 | FY19P6
21 | 2019-02-02 | 7 | WK 23 | P6 | W3 | P6W3 | FY19 | FY19P6
22 | 2019-02-03 | 1 | WK 24 | P6 | W4 | P6W4 | FY19 | FY19P6
23 | 2019-02-04 | 2 | WK 24 | P6 | W4 | P6W4 | FY19 | FY19P6
24 | 2019-02-05 | 3 | WK 24 | P6 | W4 | P6W4 | FY19 | FY19P6
25 | 2019-02-06 | 4 | WK 24 | P6 | W4 | P6W4 | FY19 | FY19P6
26 | 2019-02-07 | 5 | WK 24 | P6 | W4 | P6W4 | FY19 | FY19P6
27 | 2019-02-08 | 6 | WK 24 | P6 | W4 | P6W4 | FY19 | FY19P6
28 | 2019-02-09 | 7 | WK 24 | P6 | W4 | P6W4 | FY19 | FY19P6
1 | 2019-02-10 | 1 | WK 25 | P7 | W1 | P7W1 | FY19 | FY19P7
2 | 2019-02-11 | 2 | WK 25 | P7 | W1 | P7W1 | FY19 | FY19P7
3 | 2019-02-12 | 3 | WK 25 | P7 | W1 | P7W1 | FY19 | FY19P7
4 | 2019-02-13 | 4 | WK 25 | P7 | W1 | P7W1 | FY19 | FY19P7
5 | 2019-02-14 | 5 | WK 25 | P7 | W1 | P7W1 | FY19 | FY19P7
6 | 2019-02-15 | 6 | WK 25 | P7 | W1 | P7W1 | FY19 | FY19P7
7 | 2019-02-16 | 7 | WK 25 | P7 | W1 | P7W1 | FY19 | FY19P7
8 | 2019-02-17 | 1 | WK 26 | P7 | W2 | P7W2 | FY19 | FY19P7
9 | 2019-02-18 | 2 | WK 26 | P7 | W2 | P7W2 | FY19 | FY19P7
10 | 2019-02-19 | 3 | WK 26 | P7 | W2 | P7W2 | FY19 | FY19P7
11 | 2019-02-20 | 4 | WK 26 | P7 | W2 | P7W2 | FY19 | FY19P7
12 | 2019-02-21 | 5 | WK 26 | P7 | W2 | P7W2 | FY19 | FY19P7
13 | 2019-02-22 | 6 | WK 26 | P7 | W2 | P7W2 | FY19 | FY19P7
14 | 2019-02-23 | 7 | WK 26 | P7 | W2 | P7W2 | FY19 | FY19P7
15 | 2019-02-24 | 1 | WK 27 | P7 | W3 | P7W3 | FY19 | FY19P7
16 | 2019-02-25 | 2 | WK 27 | P7 | W3 | P7W3 | FY19 | FY19P7
17 | 2019-02-26 | 3 | WK 27 | P7 | W3 | P7W3 | FY19 | FY19P7
18 | 2019-02-27 | 4 | WK 27 | P7 | W3 | P7W3 | FY19 | FY19P7
19 | 2019-02-28 | 5 | WK 27 | P7 | W3 | P7W3 | FY19 | FY19P7
20 | 2019-03-01 | 6 | WK 27 | P7 | W3 | P7W3 | FY19 | FY19P7
21 | 2019-03-02 | 7 | WK 27 | P7 | W3 | P7W3 | FY19 | FY19P7
22 | 2019-03-03 | 1 | WK 28 | P7 | W4 | P7W4 | FY19 | FY19P7
23 | 2019-03-04 | 2 | WK 28 | P7 | W4 | P7W4 | FY19 | FY19P7
24 | 2019-03-05 | 3 | WK 28 | P7 | W4 | P7W4 | FY19 | FY19P7
25 | 2019-03-06 | 4 | WK 28 | P7 | W4 | P7W4 | FY19 | FY19P7
26 | 2019-03-07 | 5 | WK 28 | P7 | W4 | P7W4 | FY19 | FY19P7
27 | 2019-03-08 | 6 | WK 28 | P7 | W4 | P7W4 | FY19 | FY19P7
28 | 2019-03-09 | 7 | WK 28 | P7 | W4 | P7W4 | FY19 | FY19P7
1 | 2019-03-10 | 1 | WK 29 | P8 | W1 | P8W1 | FY19 | FY19P8
2 | 2019-03-11 | 2 | WK 29 | P8 | W1 | P8W1 | FY19 | FY19P8
3 | 2019-03-12 | 3 | WK 29 | P8 | W1 | P8W1 | FY19 | FY19P8
4 | 2019-03-13 | 4 | WK 29 | P8 | W1 | P8W1 | FY19 | FY19P8
5 | 2019-03-14 | 5 | WK 29 | P8 | W1 | P8W1 | FY19 | FY19P8
6 | 2019-03-15 | 6 | WK 29 | P8 | W1 | P8W1 | FY19 | FY19P8
7 | 2019-03-16 | 7 | WK 29 | P8 | W1 | P8W1 | FY19 | FY19P8
8 | 2019-03-17 | 1 | WK 30 | P8 | W2 | P8W2 | FY19 | FY19P8
9 | 2019-03-18 | 2 | WK 30 | P8 | W2 | P8W2 | FY19 | FY19P8
10 | 2019-03-19 | 3 | WK 30 | P8 | W2 | P8W2 | FY19 | FY19P8
11 | 2019-03-20 | 4 | WK 30 | P8 | W2 | P8W2 | FY19 | FY19P8
12 | 2019-03-21 | 5 | WK 30 | P8 | W2 | P8W2 | FY19 | FY19P8
13 | 2019-03-22 | 6 | WK 30 | P8 | W2 | P8W2 | FY19 | FY19P8
14 | 2019-03-23 | 7 | WK 30 | P8 | W2 | P8W2 | FY19 | FY19P8
15 | 2019-03-24 | 1 | WK 31 | P8 | W3 | P8W3 | FY19 | FY19P8
16 | 2019-03-25 | 2 | WK 31 | P8 | W3 | P8W3 | FY19 | FY19P8
17 | 2019-03-26 | 3 | WK 31 | P8 | W3 | P8W3 | FY19 | FY19P8
18 | 2019-03-27 | 4 | WK 31 | P8 | W3 | P8W3 | FY19 | FY19P8
19 | 2019-03-28 | 5 | WK 31 | P8 | W3 | P8W3 | FY19 | FY19P8
20 | 2019-03-29 | 6 | WK 31 | P8 | W3 | P8W3 | FY19 | FY19P8
21 | 2019-03-30 | 7 | WK 31 | P8 | W3 | P8W3 | FY19 | FY19P8
22 | 2019-03-31 | 1 | WK 32 | P8 | W4 | P8W4 | FY19 | FY19P8
23 | 2019-04-01 | 2 | WK 32 | P8 | W4 | P8W4 | FY19 | FY19P8
24 | 2019-04-02 | 3 | WK 32 | P8 | W4 | P8W4 | FY19 | FY19P8
25 | 2019-04-03 | 4 | WK 32 | P8 | W4 | P8W4 | FY19 | FY19P8
26 | 2019-04-04 | 5 | WK 32 | P8 | W4 | P8W4 | FY19 | FY19P8
27 | 2019-04-05 | 6 | WK 32 | P8 | W4 | P8W4 | FY19 | FY19P8
28 | 2019-04-06 | 7 | WK 32 | P8 | W4 | P8W4 | FY19 | FY19P8
1 | 2019-04-07 | 1 | WK 33 | P9 | W1 | P9W1 | FY19 | FY19P9
2 | 2019-04-08 | 2 | WK 33 | P9 | W1 | P9W1 | FY19 | FY19P9
3 | 2019-04-09 | 3 | WK 33 | P9 | W1 | P9W1 | FY19 | FY19P9
4 | 2019-04-10 | 4 | WK 33 | P9 | W1 | P9W1 | FY19 | FY19P9
5 | 2019-04-11 | 5 | WK 33 | P9 | W1 | P9W1 | FY19 | FY19P9
6 | 2019-04-12 | 6 | WK 33 | P9 | W1 | P9W1 | FY19 | FY19P9
7 | 2019-04-13 | 7 | WK 33 | P9 | W1 | P9W1 | FY19 | FY19P9
8 | 2019-04-14 | 1 | WK 34 | P9 | W2 | P9W2 | FY19 | FY19P9
9 | 2019-04-15 | 2 | WK 34 | P9 | W2 | P9W2 | FY19 | FY19P9
10 | 2019-04-16 | 3 | WK 34 | P9 | W2 | P9W2 | FY19 | FY19P9
11 | 2019-04-17 | 4 | WK 34 | P9 | W2 | P9W2 | FY19 | FY19P9
12 | 2019-04-18 | 5 | WK 34 | P9 | W2 | P9W2 | FY19 | FY19P9
13 | 2019-04-19 | 6 | WK 34 | P9 | W2 | P9W2 | FY19 | FY19P9
14 | 2019-04-20 | 7 | WK 34 | P9 | W2 | P9W2 | FY19 | FY19P9
15 | 2019-04-21 | 1 | WK 35 | P9 | W3 | P9W3 | FY19 | FY19P9
16 | 2019-04-22 | 2 | WK 35 | P9 | W3 | P9W3 | FY19 | FY19P9
17 | 2019-04-23 | 3 | WK 35 | P9 | W3 | P9W3 | FY19 | FY19P9
18 | 2019-04-24 | 4 | WK 35 | P9 | W3 | P9W3 | FY19 | FY19P9
19 | 2019-04-25 | 5 | WK 35 | P9 | W3 | P9W3 | FY19 | FY19P9
20 | 2019-04-26 | 6 | WK 35 | P9 | W3 | P9W3 | FY19 | FY19P9
21 | 2019-04-27 | 7 | WK 35 | P9 | W3 | P9W3 | FY19 | FY19P9
22 | 2019-04-28 | 1 | WK 36 | P9 | W4 | P9W4 | FY19 | FY19P9
23 | 2019-04-29 | 2 | WK 36 | P9 | W4 | P9W4 | FY19 | FY19P9
24 | 2019-04-30 | 3 | WK 36 | P9 | W4 | P9W4 | FY19 | FY19P9
25 | 2019-05-01 | 4 | WK 36 | P9 | W4 | P9W4 | FY19 | FY19P9
26 | 2019-05-02 | 5 | WK 36 | P9 | W4 | P9W4 | FY19 | FY19P9
27 | 2019-05-03 | 6 | WK 36 | P9 | W4 | P9W4 | FY19 | FY19P9
28 | 2019-05-04 | 7 | WK 36 | P9 | W4 | P9W4 | FY19 | FY19P9
1 | 2019-05-05 | 1 | WK 37 | P10 | W1 | P10W1 | FY19 | FY19P10
2 | 2019-05-06 | 2 | WK 37 | P10 | W1 | P10W1 | FY19 | FY19P10
3 | 2019-05-07 | 3 | WK 37 | P10 | W1 | P10W1 | FY19 | FY19P10
4 | 2019-05-08 | 4 | WK 37 | P10 | W1 | P10W1 | FY19 | FY19P10
5 | 2019-05-09 | 5 | WK 37 | P10 | W1 | P10W1 | FY19 | FY19P10
6 | 2019-05-10 | 6 | WK 37 | P10 | W1 | P10W1 | FY19 | FY19P10
7 | 2019-05-11 | 7 | WK 37 | P10 | W1 | P10W1 | FY19 | FY19P10
8 | 2019-05-12 | 1 | WK 38 | P10 | W2 | P10W2 | FY19 | FY19P10
9 | 2019-05-13 | 2 | WK 38 | P10 | W2 | P10W2 | FY19 | FY19P10
10 | 2019-05-14 | 3 | WK 38 | P10 | W2 | P10W2 | FY19 | FY19P10
11 | 2019-05-15 | 4 | WK 38 | P10 | W2 | P10W2 | FY19 | FY19P10
12 | 2019-05-16 | 5 | WK 38 | P10 | W2 | P10W2 | FY19 | FY19P10
13 | 2019-05-17 | 6 | WK 38 | P10 | W2 | P10W2 | FY19 | FY19P10
14 | 2019-05-18 | 7 | WK 38 | P10 | W2 | P10W2 | FY19 | FY19P10
15 | 2019-05-19 | 1 | WK 39 | P10 | W3 | P10W3 | FY19 | FY19P10
16 | 2019-05-20 | 2 | WK 39 | P10 | W3 | P10W3 | FY19 | FY19P10
17 | 2019-05-21 | 3 | WK 39 | P10 | W3 | P10W3 | FY19 | FY19P10
18 | 2019-05-22 | 4 | WK 39 | P10 | W3 | P10W3 | FY19 | FY19P10
19 | 2019-05-23 | 5 | WK 39 | P10 | W3 | P10W3 | FY19 | FY19P10
20 | 2019-05-24 | 6 | WK 39 | P10 | W3 | P10W3 | FY19 | FY19P10
21 | 2019-05-25 | 7 | WK 39 | P10 | W3 | P10W3 | FY19 | FY19P10
22 | 2019-05-26 | 1 | WK 40 | P10 | W4 | P10W4 | FY19 | FY19P10
23 | 2019-05-27 | 2 | WK 40 | P10 | W4 | P10W4 | FY19 | FY19P10
24 | 2019-05-28 | 3 | WK 40 | P10 | W4 | P10W4 | FY19 | FY19P10
25 | 2019-05-29 | 4 | WK 40 | P10 | W4 | P10W4 | FY19 | FY19P10
26 | 2019-05-30 | 5 | WK 40 | P10 | W4 | P10W4 | FY19 | FY19P10
27 | 2019-05-31 | 6 | WK 40 | P10 | W4 | P10W4 | FY19 | FY19P10
28 | 2019-06-01 | 7 | WK 40 | P10 | W4 | P10W4 | FY19 | FY19P10
1 | 2019-06-02 | 1 | WK 41 | P11 | W1 | P11W1 | FY19 | FY19P11
2 | 2019-06-03 | 2 | WK 41 | P11 | W1 | P11W1 | FY19 | FY19P11
3 | 2019-06-04 | 3 | WK 41 | P11 | W1 | P11W1 | FY19 | FY19P11
4 | 2019-06-05 | 4 | WK 41 | P11 | W1 | P11W1 | FY19 | FY19P11
5 | 2019-06-06 | 5 | WK 41 | P11 | W1 | P11W1 | FY19 | FY19P11
6 | 2019-06-07 | 6 | WK 41 | P11 | W1 | P11W1 | FY19 | FY19P11
7 | 2019-06-08 | 7 | WK 41 | P11 | W1 | P11W1 | FY19 | FY19P11
8 | 2019-06-09 | 1 | WK 42 | P11 | W2 | P11W2 | FY19 | FY19P11
9 | 2019-06-10 | 2 | WK 42 | P11 | W2 | P11W2 | FY19 | FY19P11
10 | 2019-06-11 | 3 | WK 42 | P11 | W2 | P11W2 | FY19 | FY19P11
11 | 2019-06-12 | 4 | WK 42 | P11 | W2 | P11W2 | FY19 | FY19P11
12 | 2019-06-13 | 5 | WK 42 | P11 | W2 | P11W2 | FY19 | FY19P11
13 | 2019-06-14 | 6 | WK 42 | P11 | W2 | P11W2 | FY19 | FY19P11
14 | 2019-06-15 | 7 | WK 42 | P11 | W2 | P11W2 | FY19 | FY19P11
15 | 2019-06-16 | 1 | WK 43 | P11 | W3 | P11W3 | FY19 | FY19P11
16 | 2019-06-17 | 2 | WK 43 | P11 | W3 | P11W3 | FY19 | FY19P11
17 | 2019-06-18 | 3 | WK 43 | P11 | W3 | P11W3 | FY19 | FY19P11
18 | 2019-06-19 | 4 | WK 43 | P11 | W3 | P11W3 | FY19 | FY19P11
19 | 2019-06-20 | 5 | WK 43 | P11 | W3 | P11W3 | FY19 | FY19P11
20 | 2019-06-21 | 6 | WK 43 | P11 | W3 | P11W3 | FY19 | FY19P11
21 | 2019-06-22 | 7 | WK 43 | P11 | W3 | P11W3 | FY19 | FY19P11
22 | 2019-06-23 | 1 | WK 44 | P11 | W4 | P11W4 | FY19 | FY19P11
23 | 2019-06-24 | 2 | WK 44 | P11 | W4 | P11W4 | FY19 | FY19P11
24 | 2019-06-25 | 3 | WK 44 | P11 | W4 | P11W4 | FY19 | FY19P11
25 | 2019-06-26 | 4 | WK 44 | P11 | W4 | P11W4 | FY19 | FY19P11
26 | 2019-06-27 | 5 | WK 44 | P11 | W4 | P11W4 | FY19 | FY19P11
27 | 2019-06-28 | 6 | WK 44 | P11 | W4 | P11W4 | FY19 | FY19P11
28 | 2019-06-29 | 7 | WK 44 | P11 | W4 | P11W4 | FY19 | FY19P11
1 | 2019-06-30 | 1 | WK 45 | P12 | W1 | P12W1 | FY19 | FY19P12
2 | 2019-07-01 | 2 | WK 45 | P12 | W1 | P12W1 | FY19 | FY19P12
3 | 2019-07-02 | 3 | WK 45 | P12 | W1 | P12W1 | FY19 | FY19P12
4 | 2019-07-03 | 4 | WK 45 | P12 | W1 | P12W1 | FY19 | FY19P12
5 | 2019-07-04 | 5 | WK 45 | P12 | W1 | P12W1 | FY19 | FY19P12
6 | 2019-07-05 | 6 | WK 45 | P12 | W1 | P12W1 | FY19 | FY19P12
7 | 2019-07-06 | 7 | WK 45 | P12 | W1 | P12W1 | FY19 | FY19P12
8 | 2019-07-07 | 1 | WK 46 | P12 | W2 | P12W2 | FY19 | FY19P12
9 | 2019-07-08 | 2 | WK 46 | P12 | W2 | P12W2 | FY19 | FY19P12
10 | 2019-07-09 | 3 | WK 46 | P12 | W2 | P12W2 | FY19 | FY19P12
11 | 2019-07-10 | 4 | WK 46 | P12 | W2 | P12W2 | FY19 | FY19P12
12 | 2019-07-11 | 5 | WK 46 | P12 | W2 | P12W2 | FY19 | FY19P12
13 | 2019-07-12 | 6 | WK 46 | P12 | W2 | P12W2 | FY19 | FY19P12
14 | 2019-07-13 | 7 | WK 46 | P12 | W2 | P12W2 | FY19 | FY19P12
15 | 2019-07-14 | 1 | WK 47 | P12 | W3 | P12W3 | FY19 | FY19P12
16 | 2019-07-15 | 2 | WK 47 | P12 | W3 | P12W3 | FY19 | FY19P12
17 | 2019-07-16 | 3 | WK 47 | P12 | W3 | P12W3 | FY19 | FY19P12
18 | 2019-07-17 | 4 | WK 47 | P12 | W3 | P12W3 | FY19 | FY19P12
19 | 2019-07-18 | 5 | WK 47 | P12 | W3 | P12W3 | FY19 | FY19P12
20 | 2019-07-19 | 6 | WK 47 | P12 | W3 | P12W3 | FY19 | FY19P12
21 | 2019-07-20 | 7 | WK 47 | P12 | W3 | P12W3 | FY19 | FY19P12
22 | 2019-07-21 | 1 | WK 48 | P12 | W4 | P12W4 | FY19 | FY19P12
23 | 2019-07-22 | 2 | WK 48 | P12 | W4 | P12W4 | FY19 | FY19P12
24 | 2019-07-23 | 3 | WK 48 | P12 | W4 | P12W4 | FY19 | FY19P12
25 | 2019-07-24 | 4 | WK 48 | P12 | W4 | P12W4 | FY19 | FY19P12
26 | 2019-07-25 | 5 | WK 48 | P12 | W4 | P12W4 | FY19 | FY19P12
27 | 2019-07-26 | 6 | WK 48 | P12 | W4 | P12W4 | FY19 | FY19P12
28 | 2019-07-27 | 7 | WK 48 | P12 | W4 | P12W4 | FY19 | FY19P12
1 | 2019-07-28 | 1 | WK 49 | P13 | W1 | P13W1 | FY19 | FY19P13
2 | 2019-07-29 | 2 | WK 49 | P13 | W1 | P13W1 | FY19 | FY19P13
3 | 2019-07-30 | 3 | WK 49 | P13 | W1 | P13W1 | FY19 | FY19P13
4 | 2019-07-31 | 4 | WK 49 | P13 | W1 | P13W1 | FY19 | FY19P13
5 | 2019-08-01 | 5 | WK 49 | P13 | W1 | P13W1 | FY19 | FY19P13
6 | 2019-08-02 | 6 | WK 49 | P13 | W1 | P13W1 | FY19 | FY19P13
7 | 2019-08-03 | 7 | WK 49 | P13 | W1 | P13W1 | FY19 | FY19P13
8 | 2019-08-04 | 1 | WK 50 | P13 | W2 | P13W2 | FY19 | FY19P13
9 | 2019-08-05 | 2 | WK 50 | P13 | W2 | P13W2 | FY19 | FY19P13
10 | 2019-08-06 | 3 | WK 50 | P13 | W2 | P13W2 | FY19 | FY19P13
11 | 2019-08-07 | 4 | WK 50 | P13 | W2 | P13W2 | FY19 | FY19P13
12 | 2019-08-08 | 5 | WK 50 | P13 | W2 | P13W2 | FY19 | FY19P13
13 | 2019-08-09 | 6 | WK 50 | P13 | W2 | P13W2 | FY19 | FY19P13
14 | 2019-08-10 | 7 | WK 50 | P13 | W2 | P13W2 | FY19 | FY19P13
15 | 2019-08-11 | 1 | WK 51 | P13 | W3 | P13W3 | FY19 | FY19P13
16 | 2019-08-12 | 2 | WK 51 | P13 | W3 | P13W3 | FY19 | FY19P13
17 | 2019-08-13 | 3 | WK 51 | P13 | W3 | P13W3 | FY19 | FY19P13
18 | 2019-08-14 | 4 | WK 51 | P13 | W3 | P13W3 | FY19 | FY19P13
19 | 2019-08-15 | 5 | WK 51 | P13 | W3 | P13W3 | FY19 | FY19P13
20 | 2019-08-16 | 6 | WK 51 | P13 | W3 | P13W3 | FY19 | FY19P13
21 | 2019-08-17 | 7 | WK 51 | P13 | W3 | P13W3 | FY19 | FY19P13
22 | 2019-08-18 | 1 | WK 52 | P13 | W4 | P13W4 | FY19 | FY19P13
23 | 2019-08-19 | 2 | WK 52 | P13 | W4 | P13W4 | FY19 | FY19P13
24 | 2019-08-20 | 3 | WK 52 | P13 | W4 | P13W4 | FY19 | FY19P13
25 | 2019-08-21 | 4 | WK 52 | P13 | W4 | P13W4 | FY19 | FY19P13
26 | 2019-08-22 | 5 | WK 52 | P13 | W4 | P13W4 | FY19 | FY19P13
27 | 2019-08-23 | 6 | WK 52 | P13 | W4 | P13W4 | FY19 | FY19P13
28 | 2019-08-24 | 7 | WK 52 | P13 | W4 | P13W4 | FY19 | FY19P13
29 | 2019-08-25 | 1 | WK 53 | P13 | W5 | P13W5 | FY19 | FY19P13
30 | 2019-08-26 | 2 | WK 53 | P13 | W5 | P13W5 | FY19 | FY19P13
31 | 2019-08-27 | 3 | WK 53 | P13 | W5 | P13W5 | FY19 | FY19P13
32 | 2019-08-28 | 4 | WK 53 | P13 | W5 | P13W5 | FY19 | FY19P13
33 | 2019-08-29 | 5 | WK 53 | P13 | W5 | P13W5 | FY19 | FY19P13
34 | 2019-08-30 | 6 | WK 53 | P13 | W5 | P13W5 | FY19 | FY19P13
35 | 2019-08-31 | 7 | WK 53 | P13 | W5 | P13W5 | FY19 | FY19P13
1 | 2019-09-01 | 1 | WK 1 | P1 | W1 | P1W1 | FY20 | FY20P1
2 | 2019-09-02 | 2 | WK 1 | P1 | W1 | P1W1 | FY20 | FY20P1
3 | 2019-09-03 | 3 | WK 1 | P1 | W1 | P1W1 | FY20 | FY20P1
4 | 2019-09-04 | 4 | WK 1 | P1 | W1 | P1W1 | FY20 | FY20P1
5 | 2019-09-05 | 5 | WK 1 | P1 | W1 | P1W1 | FY20 | FY20P1
6 | 2019-09-06 | 6 | WK 1 | P1 | W1 | P1W1 | FY20 | FY20P1
7 | 2019-09-07 | 7 | WK 1 | P1 | W1 | P1W1 | FY20 | FY20P1
8 | 2019-09-08 | 1 | WK 2 | P1 | W2 | P1W2 | FY20 | FY20P1
9 | 2019-09-09 | 2 | WK 2 | P1 | W2 | P1W2 | FY20 | FY20P1
10 | 2019-09-10 | 3 | WK 2 | P1 | W2 | P1W2 | FY20 | FY20P1
11 | 2019-09-11 | 4 | WK 2 | P1 | W2 | P1W2 | FY20 | FY20P1
12 | 2019-09-12 | 5 | WK 2 | P1 | W2 | P1W2 | FY20 | FY20P1
13 | 2019-09-13 | 6 | WK 2 | P1 | W2 | P1W2 | FY20 | FY20P1
14 | 2019-09-14 | 7 | WK 2 | P1 | W2 | P1W2 | FY20 | FY20P1
15 | 2019-09-15 | 1 | WK 3 | P1 | W3 | P1W3 | FY20 | FY20P1
16 | 2019-09-16 | 2 | WK 3 | P1 | W3 | P1W3 | FY20 | FY20P1
17 | 2019-09-17 | 3 | WK 3 | P1 | W3 | P1W3 | FY20 | FY20P1
18 | 2019-09-18 | 4 | WK 3 | P1 | W3 | P1W3 | FY20 | FY20P1
19 | 2019-09-19 | 5 | WK 3 | P1 | W3 | P1W3 | FY20 | FY20P1
20 | 2019-09-20 | 6 | WK 3 | P1 | W3 | P1W3 | FY20 | FY20P1
21 | 2019-09-21 | 7 | WK 3 | P1 | W3 | P1W3 | FY20 | FY20P1
22 | 2019-09-22 | 1 | WK 4 | P1 | W4 | P1W4 | FY20 | FY20P1
23 | 2019-09-23 | 2 | WK 4 | P1 | W4 | P1W4 | FY20 | FY20P1
24 | 2019-09-24 | 3 | WK 4 | P1 | W4 | P1W4 | FY20 | FY20P1
25 | 2019-09-25 | 4 | WK 4 | P1 | W4 | P1W4 | FY20 | FY20P1
26 | 2019-09-26 | 5 | WK 4 | P1 | W4 | P1W4 | FY20 | FY20P1
27 | 2019-09-27 | 6 | WK 4 | P1 | W4 | P1W4 | FY20 | FY20P1
28 | 2019-09-28 | 7 | WK 4 | P1 | W4 | P1W4 | FY20 | FY20P1
1 | 2019-09-29 | 1 | WK 5 | P2 | W1 | P2W1 | FY20 | FY20P2
2 | 2019-09-30 | 2 | WK 5 | P2 | W1 | P2W1 | FY20 | FY20P2
3 | 2019-10-01 | 3 | WK 5 | P2 | W1 | P2W1 | FY20 | FY20P2
4 | 2019-10-02 | 4 | WK 5 | P2 | W1 | P2W1 | FY20 | FY20P2
5 | 2019-10-03 | 5 | WK 5 | P2 | W1 | P2W1 | FY20 | FY20P2
6 | 2019-10-04 | 6 | WK 5 | P2 | W1 | P2W1 | FY20 | FY20P2
7 | 2019-10-05 | 7 | WK 5 | P2 | W1 | P2W1 | FY20 | FY20P2
8 | 2019-10-06 | 1 | WK 6 | P2 | W2 | P2W2 | FY20 | FY20P2
9 | 2019-10-07 | 2 | WK 6 | P2 | W2 | P2W2 | FY20 | FY20P2
10 | 2019-10-08 | 3 | WK 6 | P2 | W2 | P2W2 | FY20 | FY20P2
11 | 2019-10-09 | 4 | WK 6 | P2 | W2 | P2W2 | FY20 | FY20P2
12 | 2019-10-10 | 5 | WK 6 | P2 | W2 | P2W2 | FY20 | FY20P2
13 | 2019-10-11 | 6 | WK 6 | P2 | W2 | P2W2 | FY20 | FY20P2
14 | 2019-10-12 | 7 | WK 6 | P2 | W2 | P2W2 | FY20 | FY20P2
15 | 2019-10-13 | 1 | WK 7 | P2 | W3 | P2W3 | FY20 | FY20P2
16 | 2019-10-14 | 2 | WK 7 | P2 | W3 | P2W3 | FY20 | FY20P2
17 | 2019-10-15 | 3 | WK 7 | P2 | W3 | P2W3 | FY20 | FY20P2
18 | 2019-10-16 | 4 | WK 7 | P2 | W3 | P2W3 | FY20 | FY20P2
19 | 2019-10-17 | 5 | WK 7 | P2 | W3 | P2W3 | FY20 | FY20P2
20 | 2019-10-18 | 6 | WK 7 | P2 | W3 | P2W3 | FY20 | FY20P2
21 | 2019-10-19 | 7 | WK 7 | P2 | W3 | P2W3 | FY20 | FY20P2
22 | 2019-10-20 | 1 | WK 8 | P2 | W4 | P2W4 | FY20 | FY20P2
23 | 2019-10-21 | 2 | WK 8 | P2 | W4 | P2W4 | FY20 | FY20P2
24 | 2019-10-22 | 3 | WK 8 | P2 | W4 | P2W4 | FY20 | FY20P2
25 | 2019-10-23 | 4 | WK 8 | P2 | W4 | P2W4 | FY20 | FY20P2
26 | 2019-10-24 | 5 | WK 8 | P2 | W4 | P2W4 | FY20 | FY20P2
27 | 2019-10-25 | 6 | WK 8 | P2 | W4 | P2W4 | FY20 | FY20P2
28 | 2019-10-26 | 7 | WK 8 | P2 | W4 | P2W4 | FY20 | FY20P2
1 | 2019-10-27 | 1 | WK 9 | P3 | W1 | P3W1 | FY20 | FY20P3
2 | 2019-10-28 | 2 | WK 9 | P3 | W1 | P3W1 | FY20 | FY20P3
3 | 2019-10-29 | 3 | WK 9 | P3 | W1 | P3W1 | FY20 | FY20P3
4 | 2019-10-30 | 4 | WK 9 | P3 | W1 | P3W1 | FY20 | FY20P3
5 | 2019-10-31 | 5 | WK 9 | P3 | W1 | P3W1 | FY20 | FY20P3
6 | 2019-11-01 | 6 | WK 9 | P3 | W1 | P3W1 | FY20 | FY20P3
7 | 2019-11-02 | 7 | WK 9 | P3 | W1 | P3W1 | FY20 | FY20P3
8 | 2019-11-03 | 1 | WK 10 | P3 | W2 | P3W2 | FY20 | FY20P3
9 | 2019-11-04 | 2 | WK 10 | P3 | W2 | P3W2 | FY20 | FY20P3
10 | 2019-11-05 | 3 | WK 10 | P3 | W2 | P3W2 | FY20 | FY20P3
11 | 2019-11-06 | 4 | WK 10 | P3 | W2 | P3W2 | FY20 | FY20P3
12 | 2019-11-07 | 5 | WK 10 | P3 | W2 | P3W2 | FY20 | FY20P3
13 | 2019-11-08 | 6 | WK 10 | P3 | W2 | P3W2 | FY20 | FY20P3
14 | 2019-11-09 | 7 | WK 10 | P3 | W2 | P3W2 | FY20 | FY20P3
15 | 2019-11-10 | 1 | WK 11 | P3 | W3 | P3W3 | FY20 | FY20P3
16 | 2019-11-11 | 2 | WK 11 | P3 | W3 | P3W3 | FY20 | FY20P3
17 | 2019-11-12 | 3 | WK 11 | P3 | W3 | P3W3 | FY20 | FY20P3
18 | 2019-11-13 | 4 | WK 11 | P3 | W3 | P3W3 | FY20 | FY20P3
19 | 2019-11-14 | 5 | WK 11 | P3 | W3 | P3W3 | FY20 | FY20P3
20 | 2019-11-15 | 6 | WK 11 | P3 | W3 | P3W3 | FY20 | FY20P3
21 | 2019-11-16 | 7 | WK 11 | P3 | W3 | P3W3 | FY20 | FY20P3
22 | 2019-11-17 | 1 | WK 12 | P3 | W4 | P3W4 | FY20 | FY20P3
23 | 2019-11-18 | 2 | WK 12 | P3 | W4 | P3W4 | FY20 | FY20P3
24 | 2019-11-19 | 3 | WK 12 | P3 | W4 | P3W4 | FY20 | FY20P3
25 | 2019-11-20 | 4 | WK 12 | P3 | W4 | P3W4 | FY20 | FY20P3
26 | 2019-11-21 | 5 | WK 12 | P3 | W4 | P3W4 | FY20 | FY20P3
27 | 2019-11-22 | 6 | WK 12 | P3 | W4 | P3W4 | FY20 | FY20P3
28 | 2019-11-23 | 7 | WK 12 | P3 | W4 | P3W4 | FY20 | FY20P3
1 | 2019-11-24 | 1 | WK 13 | P4 | W1 | P4W1 | FY20 | FY20P4
2 | 2019-11-25 | 2 | WK 13 | P4 | W1 | P4W1 | FY20 | FY20P4
3 | 2019-11-26 | 3 | WK 13 | P4 | W1 | P4W1 | FY20 | FY20P4
4 | 2019-11-27 | 4 | WK 13 | P4 | W1 | P4W1 | FY20 | FY20P4
5 | 2019-11-28 | 5 | WK 13 | P4 | W1 | P4W1 | FY20 | FY20P4
6 | 2019-11-29 | 6 | WK 13 | P4 | W1 | P4W1 | FY20 | FY20P4
7 | 2019-11-30 | 7 | WK 13 | P4 | W1 | P4W1 | FY20 | FY20P4
8 | 2019-12-01 | 1 | WK 14 | P4 | W2 | P4W2 | FY20 | FY20P4
9 | 2019-12-02 | 2 | WK 14 | P4 | W2 | P4W2 | FY20 | FY20P4
10 | 2019-12-03 | 3 | WK 14 | P4 | W2 | P4W2 | FY20 | FY20P4
11 | 2019-12-04 | 4 | WK 14 | P4 | W2 | P4W2 | FY20 | FY20P4
12 | 2019-12-05 | 5 | WK 14 | P4 | W2 | P4W2 | FY20 | FY20P4
13 | 2019-12-06 | 6 | WK 14 | P4 | W2 | P4W2 | FY20 | FY20P4
14 | 2019-12-07 | 7 | WK 14 | P4 | W2 | P4W2 | FY20 | FY20P4
15 | 2019-12-08 | 1 | WK 15 | P4 | W3 | P4W3 | FY20 | FY20P4
16 | 2019-12-09 | 2 | WK 15 | P4 | W3 | P4W3 | FY20 | FY20P4
17 | 2019-12-10 | 3 | WK 15 | P4 | W3 | P4W3 | FY20 | FY20P4
18 | 2019-12-11 | 4 | WK 15 | P4 | W3 | P4W3 | FY20 | FY20P4
19 | 2019-12-12 | 5 | WK 15 | P4 | W3 | P4W3 | FY20 | FY20P4
20 | 2019-12-13 | 6 | WK 15 | P4 | W3 | P4W3 | FY20 | FY20P4
21 | 2019-12-14 | 7 | WK 15 | P4 | W3 | P4W3 | FY20 | FY20P4
22 | 2019-12-15 | 1 | WK 16 | P4 | W4 | P4W4 | FY20 | FY20P4
23 | 2019-12-16 | 2 | WK 16 | P4 | W4 | P4W4 | FY20 | FY20P4
24 | 2019-12-17 | 3 | WK 16 | P4 | W4 | P4W4 | FY20 | FY20P4
25 | 2019-12-18 | 4 | WK 16 | P4 | W4 | P4W4 | FY20 | FY20P4
26 | 2019-12-19 | 5 | WK 16 | P4 | W4 | P4W4 | FY20 | FY20P4
27 | 2019-12-20 | 6 | WK 16 | P4 | W4 | P4W4 | FY20 | FY20P4
28 | 2019-12-21 | 7 | WK 16 | P4 | W4 | P4W4 | FY20 | FY20P4
1 | 2019-12-22 | 1 | WK 17 | P5 | W1 | P5W1 | FY20 | FY20P5
2 | 2019-12-23 | 2 | WK 17 | P5 | W1 | P5W1 | FY20 | FY20P5
3 | 2019-12-24 | 3 | WK 17 | P5 | W1 | P5W1 | FY20 | FY20P5
4 | 2019-12-25 | 4 | WK 17 | P5 | W1 | P5W1 | FY20 | FY20P5
5 | 2019-12-26 | 5 | WK 17 | P5 | W1 | P5W1 | FY20 | FY20P5
6 | 2019-12-27 | 6 | WK 17 | P5 | W1 | P5W1 | FY20 | FY20P5
7 | 2019-12-28 | 7 | WK 17 | P5 | W1 | P5W1 | FY20 | FY20P5
8 | 2019-12-29 | 1 | WK 18 | P5 | W2 | P5W2 | FY20 | FY20P5
9 | 2019-12-30 | 2 | WK 18 | P5 | W2 | P5W2 | FY20 | FY20P5
10 | 2019-12-31 | 3 | WK 18 | P5 | W2 | P5W2 | FY20 | FY20P5
11 | 2020-01-01 | 4 | WK 18 | P5 | W2 | P5W2 | FY20 | FY20P5
12 | 2020-01-02 | 5 | WK 18 | P5 | W2 | P5W2 | FY20 | FY20P5
13 | 2020-01-03 | 6 | WK 18 | P5 | W2 | P5W2 | FY20 | FY20P5
14 | 2020-01-04 | 7 | WK 18 | P5 | W2 | P5W2 | FY20 | FY20P5
15 | 2020-01-05 | 1 | WK 19 | P5 | W3 | P5W3 | FY20 | FY20P5
16 | 2020-01-06 | 2 | WK 19 | P5 | W3 | P5W3 | FY20 | FY20P5
17 | 2020-01-07 | 3 | WK 19 | P5 | W3 | P5W3 | FY20 | FY20P5
18 | 2020-01-08 | 4 | WK 19 | P5 | W3 | P5W3 | FY20 | FY20P5
19 | 2020-01-09 | 5 | WK 19 | P5 | W3 | P5W3 | FY20 | FY20P5
20 | 2020-01-10 | 6 | WK 19 | P5 | W3 | P5W3 | FY20 | FY20P5
21 | 2020-01-11 | 7 | WK 19 | P5 | W3 | P5W3 | FY20 | FY20P5
22 | 2020-01-12 | 1 | WK 20 | P5 | W4 | P5W4 | FY20 | FY20P5
23 | 2020-01-13 | 2 | WK 20 | P5 | W4 | P5W4 | FY20 | FY20P5
24 | 2020-01-14 | 3 | WK 20 | P5 | W4 | P5W4 | FY20 | FY20P5
25 | 2020-01-15 | 4 | WK 20 | P5 | W4 | P5W4 | FY20 | FY20P5
26 | 2020-01-16 | 5 | WK 20 | P5 | W4 | P5W4 | FY20 | FY20P5
27 | 2020-01-17 | 6 | WK 20 | P5 | W4 | P5W4 | FY20 | FY20P5
28 | 2020-01-18 | 7 | WK 20 | P5 | W4 | P5W4 | FY20 | FY20P5
1 | 2020-01-19 | 1 | WK 21 | P6 | W1 | P6W1 | FY20 | FY20P6
2 | 2020-01-20 | 2 | WK 21 | P6 | W1 | P6W1 | FY20 | FY20P6
3 | 2020-01-21 | 3 | WK 21 | P6 | W1 | P6W1 | FY20 | FY20P6
4 | 2020-01-22 | 4 | WK 21 | P6 | W1 | P6W1 | FY20 | FY20P6
5 | 2020-01-23 | 5 | WK 21 | P6 | W1 | P6W1 | FY20 | FY20P6
6 | 2020-01-24 | 6 | WK 21 | P6 | W1 | P6W1 | FY20 | FY20P6
7 | 2020-01-25 | 7 | WK 21 | P6 | W1 | P6W1 | FY20 | FY20P6
8 | 2020-01-26 | 1 | WK 22 | P6 | W2 | P6W2 | FY20 | FY20P6
9 | 2020-01-27 | 2 | WK 22 | P6 | W2 | P6W2 | FY20 | FY20P6
10 | 2020-01-28 | 3 | WK 22 | P6 | W2 | P6W2 | FY20 | FY20P6
11 | 2020-01-29 | 4 | WK 22 | P6 | W2 | P6W2 | FY20 | FY20P6
12 | 2020-01-30 | 5 | WK 22 | P6 | W2 | P6W2 | FY20 | FY20P6
13 | 2020-01-31 | 6 | WK 22 | P6 | W2 | P6W2 | FY20 | FY20P6
14 | 2020-02-01 | 7 | WK 22 | P6 | W2 | P6W2 | FY20 | FY20P6
15 | 2020-02-02 | 1 | WK 23 | P6 | W3 | P6W3 | FY20 | FY20P6
16 | 2020-02-03 | 2 | WK 23 | P6 | W3 | P6W3 | FY20 | FY20P6
17 | 2020-02-04 | 3 | WK 23 | P6 | W3 | P6W3 | FY20 | FY20P6
18 | 2020-02-05 | 4 | WK 23 | P6 | W3 | P6W3 | FY20 | FY20P6
19 | 2020-02-06 | 5 | WK 23 | P6 | W3 | P6W3 | FY20 | FY20P6
20 | 2020-02-07 | 6 | WK 23 | P6 | W3 | P6W3 | FY20 | FY20P6
21 | 2020-02-08 | 7 | WK 23 | P6 | W3 | P6W3 | FY20 | FY20P6
22 | 2020-02-09 | 1 | WK 24 | P6 | W4 | P6W4 | FY20 | FY20P6
23 | 2020-02-10 | 2 | WK 24 | P6 | W4 | P6W4 | FY20 | FY20P6
24 | 2020-02-11 | 3 | WK 24 | P6 | W4 | P6W4 | FY20 | FY20P6
25 | 2020-02-12 | 4 | WK 24 | P6 | W4 | P6W4 | FY20 | FY20P6
26 | 2020-02-13 | 5 | WK 24 | P6 | W4 | P6W4 | FY20 | FY20P6
27 | 2020-02-14 | 6 | WK 24 | P6 | W4 | P6W4 | FY20 | FY20P6
28 | 2020-02-15 | 7 | WK 24 | P6 | W4 | P6W4 | FY20 | FY20P6
1 | 2020-02-16 | 1 | WK 25 | P7 | W1 | P7W1 | FY20 | FY20P7
2 | 2020-02-17 | 2 | WK 25 | P7 | W1 | P7W1 | FY20 | FY20P7
3 | 2020-02-18 | 3 | WK 25 | P7 | W1 | P7W1 | FY20 | FY20P7
4 | 2020-02-19 | 4 | WK 25 | P7 | W1 | P7W1 | FY20 | FY20P7
5 | 2020-02-20 | 5 | WK 25 | P7 | W1 | P7W1 | FY20 | FY20P7
6 | 2020-02-21 | 6 | WK 25 | P7 | W1 | P7W1 | FY20 | FY20P7
7 | 2020-02-22 | 7 | WK 25 | P7 | W1 | P7W1 | FY20 | FY20P7
8 | 2020-02-23 | 1 | WK 26 | P7 | W2 | P7W2 | FY20 | FY20P7
9 | 2020-02-24 | 2 | WK 26 | P7 | W2 | P7W2 | FY20 | FY20P7
10 | 2020-02-25 | 3 | WK 26 | P7 | W2 | P7W2 | FY20 | FY20P7
11 | 2020-02-26 | 4 | WK 26 | P7 | W2 | P7W2 | FY20 | FY20P7
12 | 2020-02-27 | 5 | WK 26 | P7 | W2 | P7W2 | FY20 | FY20P7
13 | 2020-02-28 | 6 | WK 26 | P7 | W2 | P7W2 | FY20 | FY20P7
14 | 2020-02-29 | 7 | WK 26 | P7 | W2 | P7W2 | FY20 | FY20P7
15 | 2020-03-01 | 1 | WK 27 | P7 | W3 | P7W3 | FY20 | FY20P7
16 | 2020-03-02 | 2 | WK 27 | P7 | W3 | P7W3 | FY20 | FY20P7
17 | 2020-03-03 | 3 | WK 27 | P7 | W3 | P7W3 | FY20 | FY20P7
18 | 2020-03-04 | 4 | WK 27 | P7 | W3 | P7W3 | FY20 | FY20P7
19 | 2020-03-05 | 5 | WK 27 | P7 | W3 | P7W3 | FY20 | FY20P7
20 | 2020-03-06 | 6 | WK 27 | P7 | W3 | P7W3 | FY20 | FY20P7
21 | 2020-03-07 | 7 | WK 27 | P7 | W3 | P7W3 | FY20 | FY20P7
22 | 2020-03-08 | 1 | WK 28 | P7 | W4 | P7W4 | FY20 | FY20P7
23 | 2020-03-09 | 2 | WK 28 | P7 | W4 | P7W4 | FY20 | FY20P7
24 | 2020-03-10 | 3 | WK 28 | P7 | W4 | P7W4 | FY20 | FY20P7
25 | 2020-03-11 | 4 | WK 28 | P7 | W4 | P7W4 | FY20 | FY20P7
26 | 2020-03-12 | 5 | WK 28 | P7 | W4 | P7W4 | FY20 | FY20P7
27 | 2020-03-13 | 6 | WK 28 | P7 | W4 | P7W4 | FY20 | FY20P7
28 | 2020-03-14 | 7 | WK 28 | P7 | W4 | P7W4 | FY20 | FY20P7
1 | 2020-03-15 | 1 | WK 29 | P8 | W1 | P8W1 | FY20 | FY20P8
2 | 2020-03-16 | 2 | WK 29 | P8 | W1 | P8W1 | FY20 | FY20P8
3 | 2020-03-17 | 3 | WK 29 | P8 | W1 | P8W1 | FY20 | FY20P8
4 | 2020-03-18 | 4 | WK 29 | P8 | W1 | P8W1 | FY20 | FY20P8
5 | 2020-03-19 | 5 | WK 29 | P8 | W1 | P8W1 | FY20 | FY20P8
6 | 2020-03-20 | 6 | WK 29 | P8 | W1 | P8W1 | FY20 | FY20P8
7 | 2020-03-21 | 7 | WK 29 | P8 | W1 | P8W1 | FY20 | FY20P8
8 | 2020-03-22 | 1 | WK 30 | P8 | W2 | P8W2 | FY20 | FY20P8
9 | 2020-03-23 | 2 | WK 30 | P8 | W2 | P8W2 | FY20 | FY20P8
10 | 2020-03-24 | 3 | WK 30 | P8 | W2 | P8W2 | FY20 | FY20P8
11 | 2020-03-25 | 4 | WK 30 | P8 | W2 | P8W2 | FY20 | FY20P8
12 | 2020-03-26 | 5 | WK 30 | P8 | W2 | P8W2 | FY20 | FY20P8
13 | 2020-03-27 | 6 | WK 30 | P8 | W2 | P8W2 | FY20 | FY20P8
14 | 2020-03-28 | 7 | WK 30 | P8 | W2 | P8W2 | FY20 | FY20P8
15 | 2020-03-29 | 1 | WK 31 | P8 | W3 | P8W3 | FY20 | FY20P8
16 | 2020-03-30 | 2 | WK 31 | P8 | W3 | P8W3 | FY20 | FY20P8
17 | 2020-03-31 | 3 | WK 31 | P8 | W3 | P8W3 | FY20 | FY20P8
18 | 2020-04-01 | 4 | WK 31 | P8 | W3 | P8W3 | FY20 | FY20P8
19 | 2020-04-02 | 5 | WK 31 | P8 | W3 | P8W3 | FY20 | FY20P8
20 | 2020-04-03 | 6 | WK 31 | P8 | W3 | P8W3 | FY20 | FY20P8
21 | 2020-04-04 | 7 | WK 31 | P8 | W3 | P8W3 | FY20 | FY20P8
22 | 2020-04-05 | 1 | WK 32 | P8 | W4 | P8W4 | FY20 | FY20P8
23 | 2020-04-06 | 2 | WK 32 | P8 | W4 | P8W4 | FY20 | FY20P8
24 | 2020-04-07 | 3 | WK 32 | P8 | W4 | P8W4 | FY20 | FY20P8
25 | 2020-04-08 | 4 | WK 32 | P8 | W4 | P8W4 | FY20 | FY20P8
26 | 2020-04-09 | 5 | WK 32 | P8 | W4 | P8W4 | FY20 | FY20P8
27 | 2020-04-10 | 6 | WK 32 | P8 | W4 | P8W4 | FY20 | FY20P8
28 | 2020-04-11 | 7 | WK 32 | P8 | W4 | P8W4 | FY20 | FY20P8
1 | 2020-04-12 | 1 | WK 33 | P9 | W1 | P9W1 | FY20 | FY20P9
2 | 2020-04-13 | 2 | WK 33 | P9 | W1 | P9W1 | FY20 | FY20P9
3 | 2020-04-14 | 3 | WK 33 | P9 | W1 | P9W1 | FY20 | FY20P9
4 | 2020-04-15 | 4 | WK 33 | P9 | W1 | P9W1 | FY20 | FY20P9
5 | 2020-04-16 | 5 | WK 33 | P9 | W1 | P9W1 | FY20 | FY20P9
6 | 2020-04-17 | 6 | WK 33 | P9 | W1 | P9W1 | FY20 | FY20P9
7 | 2020-04-18 | 7 | WK 33 | P9 | W1 | P9W1 | FY20 | FY20P9
8 | 2020-04-19 | 1 | WK 34 | P9 | W2 | P9W2 | FY20 | FY20P9
9 | 2020-04-20 | 2 | WK 34 | P9 | W2 | P9W2 | FY20 | FY20P9
10 | 2020-04-21 | 3 | WK 34 | P9 | W2 | P9W2 | FY20 | FY20P9
11 | 2020-04-22 | 4 | WK 34 | P9 | W2 | P9W2 | FY20 | FY20P9
12 | 2020-04-23 | 5 | WK 34 | P9 | W2 | P9W2 | FY20 | FY20P9
13 | 2020-04-24 | 6 | WK 34 | P9 | W2 | P9W2 | FY20 | FY20P9
14 | 2020-04-25 | 7 | WK 34 | P9 | W2 | P9W2 | FY20 | FY20P9
15 | 2020-04-26 | 1 | WK 35 | P9 | W3 | P9W3 | FY20 | FY20P9
16 | 2020-04-27 | 2 | WK 35 | P9 | W3 | P9W3 | FY20 | FY20P9
17 | 2020-04-28 | 3 | WK 35 | P9 | W3 | P9W3 | FY20 | FY20P9
18 | 2020-04-29 | 4 | WK 35 | P9 | W3 | P9W3 | FY20 | FY20P9
19 | 2020-04-30 | 5 | WK 35 | P9 | W3 | P9W3 | FY20 | FY20P9
20 | 2020-05-01 | 6 | WK 35 | P9 | W3 | P9W3 | FY20 | FY20P9
21 | 2020-05-02 | 7 | WK 35 | P9 | W3 | P9W3 | FY20 | FY20P9
22 | 2020-05-03 | 1 | WK 36 | P9 | W4 | P9W4 | FY20 | FY20P9
23 | 2020-05-04 | 2 | WK 36 | P9 | W4 | P9W4 | FY20 | FY20P9
24 | 2020-05-05 | 3 | WK 36 | P9 | W4 | P9W4 | FY20 | FY20P9
25 | 2020-05-06 | 4 | WK 36 | P9 | W4 | P9W4 | FY20 | FY20P9
26 | 2020-05-07 | 5 | WK 36 | P9 | W4 | P9W4 | FY20 | FY20P9
27 | 2020-05-08 | 6 | WK 36 | P9 | W4 | P9W4 | FY20 | FY20P9
28 | 2020-05-09 | 7 | WK 36 | P9 | W4 | P9W4 | FY20 | FY20P9
1 | 2020-05-10 | 1 | WK 37 | P10 | W1 | P10W1 | FY20 | FY20P10
2 | 2020-05-11 | 2 | WK 37 | P10 | W1 | P10W1 | FY20 | FY20P10
3 | 2020-05-12 | 3 | WK 37 | P10 | W1 | P10W1 | FY20 | FY20P10
4 | 2020-05-13 | 4 | WK 37 | P10 | W1 | P10W1 | FY20 | FY20P10
5 | 2020-05-14 | 5 | WK 37 | P10 | W1 | P10W1 | FY20 | FY20P10
6 | 2020-05-15 | 6 | WK 37 | P10 | W1 | P10W1 | FY20 | FY20P10
7 | 2020-05-16 | 7 | WK 37 | P10 | W1 | P10W1 | FY20 | FY20P10
8 | 2020-05-17 | 1 | WK 38 | P10 | W2 | P10W2 | FY20 | FY20P10
9 | 2020-05-18 | 2 | WK 38 | P10 | W2 | P10W2 | FY20 | FY20P10
10 | 2020-05-19 | 3 | WK 38 | P10 | W2 | P10W2 | FY20 | FY20P10
11 | 2020-05-20 | 4 | WK 38 | P10 | W2 | P10W2 | FY20 | FY20P10
12 | 2020-05-21 | 5 | WK 38 | P10 | W2 | P10W2 | FY20 | FY20P10
13 | 2020-05-22 | 6 | WK 38 | P10 | W2 | P10W2 | FY20 | FY20P10
14 | 2020-05-23 | 7 | WK 38 | P10 | W2 | P10W2 | FY20 | FY20P10
15 | 2020-05-24 | 1 | WK 39 | P10 | W3 | P10W3 | FY20 | FY20P10
16 | 2020-05-25 | 2 | WK 39 | P10 | W3 | P10W3 | FY20 | FY20P10
17 | 2020-05-26 | 3 | WK 39 | P10 | W3 | P10W3 | FY20 | FY20P10
18 | 2020-05-27 | 4 | WK 39 | P10 | W3 | P10W3 | FY20 | FY20P10
19 | 2020-05-28 | 5 | WK 39 | P10 | W3 | P10W3 | FY20 | FY20P10
20 | 2020-05-29 | 6 | WK 39 | P10 | W3 | P10W3 | FY20 | FY20P10
21 | 2020-05-30 | 7 | WK 39 | P10 | W3 | P10W3 | FY20 | FY20P10
22 | 2020-05-31 | 1 | WK 40 | P10 | W4 | P10W4 | FY20 | FY20P10
23 | 2020-06-01 | 2 | WK 40 | P10 | W4 | P10W4 | FY20 | FY20P10
24 | 2020-06-02 | 3 | WK 40 | P10 | W4 | P10W4 | FY20 | FY20P10
25 | 2020-06-03 | 4 | WK 40 | P10 | W4 | P10W4 | FY20 | FY20P10
26 | 2020-06-04 | 5 | WK 40 | P10 | W4 | P10W4 | FY20 | FY20P10
27 | 2020-06-05 | 6 | WK 40 | P10 | W4 | P10W4 | FY20 | FY20P10
28 | 2020-06-06 | 7 | WK 40 | P10 | W4 | P10W4 | FY20 | FY20P10
1 | 2020-06-07 | 1 | WK 41 | P11 | W1 | P11W1 | FY20 | FY20P11
2 | 2020-06-08 | 2 | WK 41 | P11 | W1 | P11W1 | FY20 | FY20P11
3 | 2020-06-09 | 3 | WK 41 | P11 | W1 | P11W1 | FY20 | FY20P11
4 | 2020-06-10 | 4 | WK 41 | P11 | W1 | P11W1 | FY20 | FY20P11
5 | 2020-06-11 | 5 | WK 41 | P11 | W1 | P11W1 | FY20 | FY20P11
6 | 2020-06-12 | 6 | WK 41 | P11 | W1 | P11W1 | FY20 | FY20P11
7 | 2020-06-13 | 7 | WK 41 | P11 | W1 | P11W1 | FY20 | FY20P11
8 | 2020-06-14 | 1 | WK 42 | P11 | W2 | P11W2 | FY20 | FY20P11
9 | 2020-06-15 | 2 | WK 42 | P11 | W2 | P11W2 | FY20 | FY20P11
10 | 2020-06-16 | 3 | WK 42 | P11 | W2 | P11W2 | FY20 | FY20P11
11 | 2020-06-17 | 4 | WK 42 | P11 | W2 | P11W2 | FY20 | FY20P11
12 | 2020-06-18 | 5 | WK 42 | P11 | W2 | P11W2 | FY20 | FY20P11
13 | 2020-06-19 | 6 | WK 42 | P11 | W2 | P11W2 | FY20 | FY20P11
14 | 2020-06-20 | 7 | WK 42 | P11 | W2 | P11W2 | FY20 | FY20P11
15 | 2020-06-21 | 1 | WK 43 | P11 | W3 | P11W3 | FY20 | FY20P11
16 | 2020-06-22 | 2 | WK 43 | P11 | W3 | P11W3 | FY20 | FY20P11
17 | 2020-06-23 | 3 | WK 43 | P11 | W3 | P11W3 | FY20 | FY20P11
18 | 2020-06-24 | 4 | WK 43 | P11 | W3 | P11W3 | FY20 | FY20P11
19 | 2020-06-25 | 5 | WK 43 | P11 | W3 | P11W3 | FY20 | FY20P11
20 | 2020-06-26 | 6 | WK 43 | P11 | W3 | P11W3 | FY20 | FY20P11
21 | 2020-06-27 | 7 | WK 43 | P11 | W3 | P11W3 | FY20 | FY20P11
22 | 2020-06-28 | 1 | WK 44 | P11 | W4 | P11W4 | FY20 | FY20P11
23 | 2020-06-29 | 2 | WK 44 | P11 | W4 | P11W4 | FY20 | FY20P11
24 | 2020-06-30 | 3 | WK 44 | P11 | W4 | P11W4 | FY20 | FY20P11
25 | 2020-07-01 | 4 | WK 44 | P11 | W4 | P11W4 | FY20 | FY20P11
26 | 2020-07-02 | 5 | WK 44 | P11 | W4 | P11W4 | FY20 | FY20P11
27 | 2020-07-03 | 6 | WK 44 | P11 | W4 | P11W4 | FY20 | FY20P11
28 | 2020-07-04 | 7 | WK 44 | P11 | W4 | P11W4 | FY20 | FY20P11
1 | 2020-07-05 | 1 | WK 45 | P12 | W1 | P12W1 | FY20 | FY20P12
2 | 2020-07-06 | 2 | WK 45 | P12 | W1 | P12W1 | FY20 | FY20P12
3 | 2020-07-07 | 3 | WK 45 | P12 | W1 | P12W1 | FY20 | FY20P12
4 | 2020-07-08 | 4 | WK 45 | P12 | W1 | P12W1 | FY20 | FY20P12
5 | 2020-07-09 | 5 | WK 45 | P12 | W1 | P12W1 | FY20 | FY20P12
6 | 2020-07-10 | 6 | WK 45 | P12 | W1 | P12W1 | FY20 | FY20P12
7 | 2020-07-11 | 7 | WK 45 | P12 | W1 | P12W1 | FY20 | FY20P12
8 | 2020-07-12 | 1 | WK 46 | P12 | W2 | P12W2 | FY20 | FY20P12
9 | 2020-07-13 | 2 | WK 46 | P12 | W2 | P12W2 | FY20 | FY20P12
10 | 2020-07-14 | 3 | WK 46 | P12 | W2 | P12W2 | FY20 | FY20P12
11 | 2020-07-15 | 4 | WK 46 | P12 | W2 | P12W2 | FY20 | FY20P12
12 | 2020-07-16 | 5 | WK 46 | P12 | W2 | P12W2 | FY20 | FY20P12
13 | 2020-07-17 | 6 | WK 46 | P12 | W2 | P12W2 | FY20 | FY20P12
14 | 2020-07-18 | 7 | WK 46 | P12 | W2 | P12W2 | FY20 | FY20P12
15 | 2020-07-19 | 1 | WK 47 | P12 | W3 | P12W3 | FY20 | FY20P12
16 | 2020-07-20 | 2 | WK 47 | P12 | W3 | P12W3 | FY20 | FY20P12
17 | 2020-07-21 | 3 | WK 47 | P12 | W3 | P12W3 | FY20 | FY20P12
18 | 2020-07-22 | 4 | WK 47 | P12 | W3 | P12W3 | FY20 | FY20P12
19 | 2020-07-23 | 5 | WK 47 | P12 | W3 | P12W3 | FY20 | FY20P12
20 | 2020-07-24 | 6 | WK 47 | P12 | W3 | P12W3 | FY20 | FY20P12
21 | 2020-07-25 | 7 | WK 47 | P12 | W3 | P12W3 | FY20 | FY20P12
22 | 2020-07-26 | 1 | WK 48 | P12 | W4 | P12W4 | FY20 | FY20P12
23 | 2020-07-27 | 2 | WK 48 | P12 | W4 | P12W4 | FY20 | FY20P12
24 | 2020-07-28 | 3 | WK 48 | P12 | W4 | P12W4 | FY20 | FY20P12
25 | 2020-07-29 | 4 | WK 48 | P12 | W4 | P12W4 | FY20 | FY20P12
26 | 2020-07-30 | 5 | WK 48 | P12 | W4 | P12W4 | FY20 | FY20P12
27 | 2020-07-31 | 6 | WK 48 | P12 | W4 | P12W4 | FY20 | FY20P12
28 | 2020-08-01 | 7 | WK 48 | P12 | W4 | P12W4 | FY20 | FY20P12
1 | 2020-08-02 | 1 | WK 49 | P13 | W1 | P13W1 | FY20 | FY20P13
2 | 2020-08-03 | 2 | WK 49 | P13 | W1 | P13W1 | FY20 | FY20P13
3 | 2020-08-04 | 3 | WK 49 | P13 | W1 | P13W1 | FY20 | FY20P13
4 | 2020-08-05 | 4 | WK 49 | P13 | W1 | P13W1 | FY20 | FY20P13
5 | 2020-08-06 | 5 | WK 49 | P13 | W1 | P13W1 | FY20 | FY20P13
6 | 2020-08-07 | 6 | WK 49 | P13 | W1 | P13W1 | FY20 | FY20P13
7 | 2020-08-08 | 7 | WK 49 | P13 | W1 | P13W1 | FY20 | FY20P13
8 | 2020-08-09 | 1 | WK 50 | P13 | W2 | P13W2 | FY20 | FY20P13
9 | 2020-08-10 | 2 | WK 50 | P13 | W2 | P13W2 | FY20 | FY20P13
10 | 2020-08-11 | 3 | WK 50 | P13 | W2 | P13W2 | FY20 | FY20P13
11 | 2020-08-12 | 4 | WK 50 | P13 | W2 | P13W2 | FY20 | FY20P13
12 | 2020-08-13 | 5 | WK 50 | P13 | W2 | P13W2 | FY20 | FY20P13
13 | 2020-08-14 | 6 | WK 50 | P13 | W2 | P13W2 | FY20 | FY20P13
14 | 2020-08-15 | 7 | WK 50 | P13 | W2 | P13W2 | FY20 | FY20P13
15 | 2020-08-16 | 1 | WK 51 | P13 | W3 | P13W3 | FY20 | FY20P13
16 | 2020-08-17 | 2 | WK 51 | P13 | W3 | P13W3 | FY20 | FY20P13
17 | 2020-08-18 | 3 | WK 51 | P13 | W3 | P13W3 | FY20 | FY20P13
18 | 2020-08-19 | 4 | WK 51 | P13 | W3 | P13W3 | FY20 | FY20P13
19 | 2020-08-20 | 5 | WK 51 | P13 | W3 | P13W3 | FY20 | FY20P13
20 | 2020-08-21 | 6 | WK 51 | P13 | W3 | P13W3 | FY20 | FY20P13
21 | 2020-08-22 | 7 | WK 51 | P13 | W3 | P13W3 | FY20 | FY20P13
22 | 2020-08-23 | 1 | WK 52 | P13 | W4 | P13W4 | FY20 | FY20P13
23 | 2020-08-24 | 2 | WK 52 | P13 | W4 | P13W4 | FY20 | FY20P13
24 | 2020-08-25 | 3 | WK 52 | P13 | W4 | P13W4 | FY20 | FY20P13
25 | 2020-08-26 | 4 | WK 52 | P13 | W4 | P13W4 | FY20 | FY20P13
26 | 2020-08-27 | 5 | WK 52 | P13 | W4 | P13W4 | FY20 | FY20P13
27 | 2020-08-28 | 6 | WK 52 | P13 | W4 | P13W4 | FY20 | FY20P13
28 | 2020-08-29 | 7 | WK 52 | P13 | W4 | P13W4 | FY20 | FY20P13
28 | 2020-08-30 | 7 | WK 52 | P13 | W4 | P13W4 | FY21 | FY21P13
Formulas:
DATA = [DATA, row above]+1